## Data (hidden)
Proc Status | Package Manager
1. Tender Docs & BOQ | Suhail
2. Bidder List | Ifthiqar
3. EOI | Prabhu
4. Tender Float | Manoj
5. Initial submission | Reyoon
6. Tech & Com Review | Jayantha
7. BAFO
8. Tech & Com Review
9. Award Rec. Approval
10. Issued to Contractor
11. Subcontract Agreement signed

## Summary
GFA (m2) |  | 1162634 |  |  | 1. Tender Docs & BOQ | 2. Bidder List | 3. EOI | 4. Tender Float | 5. Initial submission | 6. Tech & Com Review | 7. BAFO | 8. Tech & Com Review | 9. Award Rec. Approval | 10. Issued to Contractor | 11. Subcontract Agreement signed
Actual to date Impact on Value |  | Value |  | Project
PS - Contract Value (incl. OHP) |  | 5640999863.3 |  | Package Manager
Awards up to date (incl. OHP) |  | 1907706780.7 | 33.99% | Previous Step Date
Savings against contract PS |  | 29042682.3 | 0.5148% | Planned Award
Award Summary |  |  |  | Project
Total Packages |  | 334 |  | Package Manager
Finalized Packages |  | 34 |  | Previous Step Date
Total Packages % |  | 10.18% |  | Planned Award
Delay Summary | nos. | Max delay |  | Project
Current delayed remaining packages | 67 | -238 |  | Package Manager
Forecast Delay to Contract | 114 | -299 |  | Previous Step Date
Forecast Delay to Baseline | 135 | -341 |  | Planned Award
Projects |  |  |  | Project
Sheet | Include |  |  | Package Manager
Data | FALSE |  |  | Previous Step Date
Summary | FALSE |  |  | Planned Award
Grove 3&4 | TRUE
Nobu | TRUE |  |  | Project
Grove 6&7 | TRUE |  |  | Package Manager
Mamsha Palm | TRUE |  |  | Previous Step Date
Faya (SB45) | TRUE |  |  | Planned Award
Mamsha Gardens | FALSE
Sama Yas | TRUE |  |  | Project
Waldorf | TRUE |  |  | Package Manager
Fahid TA1-2 | TRUE |  |  | Previous Step Date
Fahid TA3-5 | TRUE |  |  | Planned Award
Fahid TA6-8 | TRUE
Verdes | TRUE |  |  | Project
Wilds | TRUE |  |  | Package Manager
Marjan | TRUE |  |  | Previous Step Date
Blank | FALSE |  |  | Planned Award

## Grove 3&4
Project |  | Components | Category | LDC | PMC | Supervision | Contractor | BUA (m2) | GFA (m2) | Award Date | Commencement |  |  | Value Summary |  |  |  |  | Actual to date Impact on Value | [5 empty] | Packages Summary |  |  | Delay Summary |  | nos. | Max delay
[14 empty] | Project Lump Sum Value in LAFO |  |  | 999000000 |  | Awards up to date (incl. OHP) |  |  | 270410508.7 | 93.32% |  | Total Packages (nos) |  | 39 | Forecast Delay to Baseline |  | 29 | -238
Source 1&2 Grove 3&4 |  | 3 Buildings - 2B+G+9 | Resi Buildings | Atkins | Hill | Atkins | Innovo | 169598 | 88020 | 2024-10-31 | 2025-03-01 |  |  | PS - Lump Sum Value in LAFO |  |  | 487533181 |  | Remaining to award |  |  | 19359205 | 6.681% |  | Finalized Packages (nos) |  | 19 | Current delayed remaining packages |  | 15 | -159
[14 empty] | PS - Contract Value (incl. OHP) |  |  | 253929721 |  | Finalized Packages Savings against Lump Sum |  |  | 168459424.3 | 16.86% |  | Days Since Award (days) |  | 516 | Forecast Delay to Contract |  | 38 | -341
[19 empty] | Finalized Packages Savings against contract PS |  |  | -35839992.7 | -3.588%
Data Date |  | 2026-03-31
SN | Pkg No. | Package | Package Manager | 15 |  | 7 |  | 6 |  | 3 |  | 30 |  | 10 |  | 20 |  | 7 |  | 7 |  | 5 |  | 10 |  | Variance from Today | PS Procurement Duration | PS - Lump Sum Value in LAFO | PS - Contract Value (excl. OHP) | PS - Contract Value (incl. OHP) | PS - Award Value (incl. OHP) | Saving (against PS in contract) | Awarded Sub-contractor | Cont Dur | Contract Date Nomination | Var | Float | Late Date in Programme | Var | Actual / Forecast Award | Current Stage (from 1-11) | 1. Tender Docs & BOQ | 2. Bidder List | 3. EOI | 4. Tender Float | 5. Initial submission | 6. Tech & Com Review | 7. BAFO | 8. Tech & Com Review | 9. Award Rec. Approval | 10. Issued to Contractor | 11. Subcontract signed
|  |  |  | 1. Tender Docs & BOQ |  | 2. Bidder List |  | 3. EOI |  | 4. Tender Float |  | 5. Initial submission |  | 6. Tech & Com Review |  | 7. BAFO |  | 8. Tech & Com Review |  | 9. Award Rec. Approval |  | 10. Issued to Contractor |  | 11. Subcontract Agreement signed
|  |  |  | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast
PC Rate Items
1 | PC1 | Light Fittings | Manoj | 2025-04-24 | 2025-07-11 | 2025-05-01 | 2025-07-30 | 2025-05-07 | 2025-07-30 | 2025-05-10 | 2025-08-12 | 2025-06-09 | 2025-10-08 | 2025-06-19 | 2025-10-08 | 2025-07-09 | 2025-10-08 | 2025-07-16 | 2025-10-27 | 2025-07-23 | 2025-10-29 | 2025-07-28 | 2025-11-05 | 2025-08-07 |  | - | 95 | 14843058 |  | 12869152 | 5439000 | 7430152 | Frater (AWRostamani) | 150 | 2025-07-28 | -100 | 10 | 2025-08-08 | -89 | 2025-11-05 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2 | PC2 | Sanitaryware | Manoj | 2025-04-24 | 2025-06-24 | 2025-05-01 | 2025-06-30 | 2025-05-07 | 2025-07-02 | 2025-05-10 | 2025-07-07 | 2025-06-09 | 2025-08-27 | 2025-06-19 | 2025-08-27 | 2025-07-09 | 2025-08-27 | 2025-07-16 | 2025-09-29 | 2025-07-23 | 2025-10-15 | 2025-07-28 | 2025-10-15 | 2025-08-07 |  | - | 95 | 15333199 |  | 11468672 | 7773699 | 3694973 | 1.Kitchen & Bath Gallery 2.Sarieddine 3.Sanipex 4.Ecobuild 5.Graniti | 150 | 2025-07-28 | -79 | 9 | 2025-08-07 | -69 | 2025-10-15 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
3 | PC3 | Tiles - Supply | Reyoon | 2025-04-24 | 2025-06-24 | 2025-05-01 | 2025-06-30 | 2025-05-07 | 2025-07-02 | 2025-05-10 | 2025-07-10 | 2025-06-09 | 2025-08-28 | 2025-06-19 | 2025-08-28 | 2025-07-09 | 2025-08-28 | 2025-07-16 | 2025-09-12 | 2025-07-23 | 2025-10-28 | 2025-07-28 | 2025-10-28 | 2025-08-07 |  | - | 95 | 13038915 |  | 7813237 | 4377403 | 3435834 | RAK Ceramics PJSC | 150 | 2025-07-28 | -92 | 23 | 2025-08-23 | -66 | 2025-10-28 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
MEP Works
Aluminum & Metal Works
4 | PS2 | Aluminium & Glazing | Prabhu | 2025-03-25 | 2025-03-04 | 2025-04-01 | 2025-03-14 | 2025-04-07 | 2025-03-21 | 2025-04-10 | 2025-04-04 | 2025-05-10 | 2025-05-09 | 2025-05-20 | 2025-05-09 | 2025-06-09 | 2025-05-09 | 2025-06-16 | 2025-05-23 | 2025-06-23 | 2025-06-10 | 2025-06-28 | 2025-07-01 | 2025-07-08 |  | - | 95 | 125192292 |  | 73292888 | 94419020 | -21126132 | Fibrex (Aluglex) | 120 | 2025-06-28 | -3 | 25 | 2025-07-28 | 27 | 2025-07-01 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
5 | PS3&4 | GRC Façade including External suspended ceiling | Prabhu | 2025-03-25 | 2025-03-04 | 2025-04-01 | 2025-03-14 | 2025-04-07 | 2025-03-21 | 2025-04-10 | 2025-04-04 | 2025-05-10 | 2025-06-21 | 2025-05-20 | 2025-06-21 | 2025-06-09 | 2025-06-21 | 2025-06-16 | 2025-06-21 | 2025-06-23 | 2025-07-16 | 2025-06-28 | 2025-07-28 | 2025-07-08 |  | - | 95 | 45216205 |  | 15382618 | 24397800 | -9015182 | Fibrex | 120 | 2025-06-28 | -30 | 25 | 2025-07-28 | 0 | 2025-07-28 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
6 | PS5 | Façade Structural Steel | Prabhu | 2025-03-25 | 2025-03-04 | 2025-04-01 | 2025-03-14 | 2025-04-07 | 2025-03-21 | 2025-04-10 | 2025-04-04 | 2025-05-10 | 2025-06-21 | 2025-05-20 | 2025-06-21 | 2025-06-09 | 2025-06-21 | 2025-06-16 | 2025-06-21 | 2025-06-23 | 2025-07-16 | 2025-06-28 | 2025-07-28 | 2025-07-08 |  | - | 95 | 10400471 |  | 5641252 | 2919723 | 2721529 | German Steel | 120 | 2025-06-28 | -30 | 25 | 2025-07-28 | 0 | 2025-07-28 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
7 | PS8a | Aluminium and Glazing Works (Internal), Shower Partitions and Glass Doors | Prabhu | 2025-05-24 | 2025-10-10 | 2025-05-31 | 2025-10-20 | 2025-06-06 | 2025-10-20 | 2025-06-09 | 2025-11-26 | 2025-07-09 | 2026-01-16 | 2025-07-19 | 2026-01-16 | 2025-08-08 | 2026-01-16 | 2025-08-15 | 2026-01-18 | 2025-08-22 | 2026-03-11 | 2025-08-27 | 2026-03-15 | 2025-09-06 |  | - | 95 | 19573678 |  | 10607053 | 18688510 | -8081457 | Aluglex | 180 | 2025-08-27 | -200 | 0 | 2025-08-27 | -200 | 2026-03-15 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
8 | PS8a | Non Structural Metal Works (Handrail ) | Prabhu | 2025-05-24 | 2025-10-10 | 2025-05-31 | 2025-10-20 | 2025-06-06 | 2025-10-20 | 2025-06-09 | 2025-11-26 | 2025-07-09 |  | 2025-07-19 |  | 2025-08-08 |  | 2025-08-15 | 2026-01-18 | 2025-08-22 | 2026-03-12 | 2025-08-27 | 2026-03-17 | 2025-09-06 |  | -131 | 95 | 4583155 |  | 2122484 | Included | 2122484 | Aluglex | 180 | 2025-08-27 | -202 | 73 | 2025-11-20 | -117 | 2026-03-17 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE
Joinery and Carpentry
9 | PS6 | Joinery/ Wood Works | Saathieth | 2025-05-24 | 2025-05-03 | 2025-05-31 | 2025-06-09 | 2025-06-06 | 2025-06-09 | 2025-06-09 | 2025-07-12 | 2025-07-09 | 2025-08-21 | 2025-07-19 | 2025-08-21 | 2025-08-08 | 2025-08-21 | 2025-08-15 | 2025-10-10 | 2025-08-22 | 2025-11-20 | 2025-08-27 | 2025-11-26 | 2025-09-06 |  | - | 95 | 48184481 |  | 25523887 | 27477022 | -1953135 | Abaad | 180 | 2025-08-27 | -91 | 23 | 2025-09-23 | -64 | 2025-11-26 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
10 | PS8a | Penthouse Doors | Saathieth | 2025-05-24 | 2025-10-10 | 2025-05-31 | 2025-10-20 | 2025-06-06 | 2025-10-20 | 2025-06-09 | 2025-11-26 | 2025-07-09 | 2026-01-16 | 2025-07-19 | 2026-01-16 | 2025-08-08 | 2026-01-16 | 2025-08-15 | 2026-01-18 | 2025-08-22 | 2026-03-10 | 2025-08-27 | 2026-03-15 | 2025-09-06 |  | - | 95 | 4800000 |  | 2603711 | incl. above | 2603711 | Abaad | 180 | 2025-08-27 | -200 | 147 | 2026-02-14 | -29 | 2026-03-15 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
11 | PS8a | Wooden cladding & flooring | Saathieth | 2025-05-24 | 2025-10-10 | 2025-05-31 | 2025-10-20 | 2025-06-06 | 2025-10-20 | 2025-06-09 | 2025-11-26 | 2025-07-09 | 2026-01-16 | 2025-07-19 | 2026-01-16 | 2025-08-08 | 2026-01-16 | 2025-08-15 | 2026-01-18 | 2025-08-22 | 2026-01-29 | 2025-08-27 | 2026-02-20 | 2025-09-06 |  | - | 95 | 8366393 |  | 5321931 | incl. above | 5321931 | Abaad | 180 | 2025-08-27 | -177 | 39 | 2025-10-11 | -132 | 2026-02-20 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
12 | PS8a | Penthouse Kitchen Cabinet and Wardrobes | Saathieth | 2025-05-24 | 2025-10-10 | 2025-05-31 | 2025-10-20 | 2025-06-06 | 2025-10-20 | 2025-06-09 |  | 2025-07-09 |  | 2025-07-19 |  | 2025-08-08 |  | 2025-08-15 |  | 2025-08-22 | 2026-01-20 | 2025-08-27 | 2026-02-20 | 2025-09-06 |  | -131 | 95 | 6000000 |  | 3254639 |  |  |  | 180 | 2025-08-27 | -177 | 73 | 2025-11-20 | -92 | 2026-02-20 | 4. Tender Float | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE
Finishes
13 | PS11 | Marble | Reyoon | 2025-04-24 | 2025-07-16 | 2025-05-01 | 2025-07-16 | 2025-05-07 | 2025-07-16 | 2025-05-10 | 2025-10-01 | 2025-06-09 | 2025-10-15 | 2025-06-19 | 2025-10-15 | 2025-07-09 | 2025-10-15 | 2025-07-16 | 2025-10-27 | 2025-07-23 | 2025-11-24 | 2025-07-28 | 2025-11-26 | 2025-08-07 |  | - | 95 | 11175324 |  | 6583325 | 4058375 | 2524950 | Valencia Marble | 150 | 2025-07-28 | -121 | 123 | 2025-12-18 | 22 | 2025-11-26 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
14 | PS8a | Metal Works (Floor, Wall and Skirting) | Reyoon | 2025-05-24 | 2025-10-10 | 2025-05-31 | 2025-10-20 | 2025-06-06 | 2025-10-20 | 2025-06-09 | 2025-11-26 | 2025-07-09 |  | 2025-07-19 |  | 2025-08-08 |  | 2025-08-15 | 2026-01-18 | 2025-08-22 | 2026-03-08 | 2025-08-27 | 2026-03-12 | 2025-09-06 |  | -131 | 95 | 14932946 |  | 8288395 |  |  |  | 180 | 2025-08-27 | -197 | 73 | 2025-11-20 | -112 | 2026-03-12 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE
15 | PS8a | Floor Underlay | Reyoon | 2025-05-24 | 2025-10-10 | 2025-05-31 | 2025-10-20 | 2025-06-06 | 2025-10-20 | 2025-06-09 | 2026-02-02 | 2025-07-09 |  | 2025-07-19 |  | 2025-08-08 |  | 2025-08-15 | 2026-01-18 | 2025-08-22 |  | 2025-08-27 |  | 2025-09-06 |  | -91 | 95 | 2767418 |  | 1450786 | 1342120.7 | 108665.3 | Pliteq | 180 | 2025-08-27 | -295 | 107 | 2025-12-30 | -170 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE
16 | PS8a | Suspended Ceilings (Internal) including bulkheads, access panels & GRC works | Reyoon | 2025-05-24 | 2025-10-10 | 2025-05-31 | 2025-10-20 | 2025-06-06 | 2025-10-20 | 2025-06-09 | 2025-12-17 | 2025-07-09 |  | 2025-07-19 |  | 2025-08-08 |  | 2025-08-15 | 2026-01-18 | 2025-08-22 |  | 2025-08-27 |  | 2025-09-06 |  | -154 | 95 | 7543646 |  | 9358326 | 9994515 | -636189 | Obaid Al Abdi | 180 | 2025-08-27 | -295 | 53 | 2025-10-28 | -233 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE
17 | PS8a | Mirrors | Prabhu | 2025-05-24 | 2025-10-10 | 2025-05-31 | 2025-10-20 | 2025-06-06 | 2025-10-20 | 2025-06-09 | 2025-12-17 | 2025-07-09 |  | 2025-07-19 |  | 2025-08-08 |  | 2025-08-15 | 2026-01-18 | 2025-08-22 |  | 2025-08-27 |  | 2025-09-06 |  | -137 | 95 | 1276486 |  | 691725 |  |  |  | 180 | 2025-08-27 | -295 | 68 | 2025-11-14 | -216 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE
18 | PS8a | Specialties including Cistern tank wall and cover, Bathtub ledge and side panel, GRP Ladders | Reyoon | 2025-05-24 | 2025-10-10 | 2025-05-31 | 2025-10-20 | 2025-06-06 | 2025-10-20 | 2025-06-09 | 2025-12-17 | 2025-07-09 |  | 2025-07-19 |  | 2025-08-08 |  | 2025-08-15 |  | 2025-08-22 |  | 2025-08-27 |  | 2025-09-06 |  | -159 | 95 | 1444352 |  | 733700 | included | 733700 | Obaid Al Abdi | 180 | 2025-08-27 | -295 | 49 | 2025-10-23 | -238 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
19 | PS8a | Dry Wall and Lining | Reyoon | 2025-05-24 | 2025-10-10 | 2025-05-31 | 2025-10-20 | 2025-06-06 | 2025-10-20 | 2025-06-09 | 2025-12-17 | 2025-07-09 |  | 2025-07-19 |  | 2025-08-08 |  | 2025-08-15 | 2026-01-18 | 2025-08-22 |  | 2025-08-27 |  | 2025-09-06 |  | -148 | 95 | 1145959 |  | 971726 | included | 971726 | Obaid Al Abdi | 180 | 2025-08-27 | -295 | 58 | 2025-11-03 | -227 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE
20 | PS8a | Micro concrete | Reyoon | 2025-05-24 | 2025-10-10 | 2025-05-31 | 2025-10-20 | 2025-06-06 | 2025-10-20 | 2025-06-09 |  | 2025-07-09 |  | 2025-07-19 |  | 2025-08-08 |  | 2025-08-15 |  | 2025-08-22 |  | 2025-08-27 |  | 2025-09-06 |  | -82 | 95 | 193990 |  | 104120 |  |  |  | 180 | 2025-08-27 | -298 | 115 | 2026-01-08 | -164 | 2026-06-21 | 4. Tender Float | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
21 | PS8b | Carpets | Reyoon | 2025-09-21 | 2025-10-10 | 2025-09-28 | 2025-10-20 | 2025-10-04 | 2025-10-20 | 2025-10-07 | 2026-01-26 | 2025-11-06 |  | 2025-11-16 |  | 2025-12-06 |  | 2025-12-13 |  | 2025-12-20 |  | 2025-12-25 |  | 2026-01-04 |  | -19 | 95 | 168780 |  | 91554 |  |  |  | 300 | 2025-12-25 | -175 | 66 | 2026-03-12 | -98 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
22 | PS8b | Rubber Flooring including vinyl flooring and skirting | Reyoon | 2025-09-21 | 2025-10-10 | 2025-09-28 | 2025-10-20 | 2025-10-04 | 2025-10-20 | 2025-10-07 | 2026-01-26 | 2025-11-06 |  | 2025-11-16 |  | 2025-12-06 |  | 2025-12-13 |  | 2025-12-20 |  | 2025-12-25 |  | 2026-01-04 |  | 4 | 95 | 1077763 |  | 691276 |  |  |  | 300 | 2025-12-25 | -175 | 86 | 2026-04-04 | -75 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
23 | PS8b | Entrance Mat | Reyoon | 2025-09-21 | 2025-10-10 | 2025-09-28 | 2025-10-20 | 2025-10-04 | 2025-10-20 | 2025-10-07 | 2026-01-26 | 2025-11-06 |  | 2025-11-16 |  | 2025-12-06 |  | 2025-12-13 |  | 2025-12-20 |  | 2025-12-25 |  | 2026-01-04 |  | 181 | 95 | 675556 |  | 336448 |  |  |  | 300 | 2025-12-25 | -175 | 237 | 2026-09-28 | 102 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
24 | PS8b | Wall Paper/Coverings | Reyoon | 2025-09-21 | 2025-10-10 | 2025-09-28 | 2025-10-20 | 2025-10-04 | 2025-10-20 | 2025-10-07 | 2026-01-26 | 2025-11-06 |  | 2025-11-16 |  | 2025-12-06 |  | 2025-12-13 |  | 2025-12-20 |  | 2025-12-25 |  | 2026-01-04 |  | -39 | 95 | 3144970 |  | 1904005 | 709940 | 1194065 | NGS | 300 | 2025-12-25 | -175 | 49 | 2026-02-20 | -118 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
25 | PC3 | Tiles (Ceramic, Porcelain…Etc.) - Installation | Prabhu | 2025-04-24 |  | 2025-05-01 |  | 2025-05-07 |  | 2025-05-10 |  | 2025-06-09 |  | 2025-06-19 |  | 2025-07-09 |  | 2025-07-16 |  | 2025-07-23 |  | 2025-07-28 |  | 2025-08-07 |  | -71 | 95 | 15936451 |  | 6605389 | included | 6605389 | Innovo | 150 | 2025-07-28 | -341 | 150 | 2026-01-19 | -166 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
External Works
26 | PS13 | Swimming Pools/ Features | Saathieth | 2025-03-25 | 2025-04-21 | 2025-04-01 | 2025-04-27 | 2025-04-07 | 2025-04-27 | 2025-04-10 | 2025-05-04 | 2025-05-10 | 2025-06-13 | 2025-05-20 | 2025-06-13 | 2025-06-09 | 2025-06-13 | 2025-06-16 | 2025-08-13 | 2025-06-23 | 2025-08-22 | 2025-06-28 | 2025-09-04 | 2025-07-08 |  | - | 95 | 13994162 |  | 18179645 | 13098000 | 5081645 | Brook & Ripples | 120 | 2025-06-28 | -68 | 13 | 2025-07-14 | -52 | 2025-09-04 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
27 | PS14 | Landscaping (Hard & Soft) | Saathieth | 2025-03-25 | 2025-04-21 | 2025-04-01 | 2025-04-27 | 2025-04-07 | 2025-04-27 | 2025-04-10 | 2025-05-04 | 2025-05-10 | 2025-06-13 | 2025-05-20 | 2025-06-13 | 2025-06-09 | 2025-06-13 | 2025-06-16 | 2025-08-13 | 2025-06-23 | 2025-08-28 | 2025-06-28 | 2025-09-17 | 2025-07-08 |  | - | 95 | 42735000 |  |  | 38402060 | -38402060 | Basatin | 120 | 2025-06-28 | -81 | 33 | 2025-08-06 | -42 | 2025-09-17 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
Equipments & Accessories
28 | PS1 | Lifts & Escalators | Manoj | 2025-02-23 | 2025-02-23 | 2025-03-02 | 2025-03-02 | 2025-03-08 | 2025-03-08 | 2025-03-11 | 2025-03-11 | 2025-04-10 | 2025-04-10 | 2025-04-20 | 2025-04-20 | 2025-05-10 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-24 | 2025-05-24 | 2025-05-29 | 2025-05-14 | 2025-06-08 |  | - | 95 | 11395020 |  | 6515893 | 8423790 | -1907897 | Kone | 90 | 2025-05-29 | 15 | 37 | 2025-07-11 | 58 | 2025-05-14 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
29 | PS9 | BMU | Prabhu | 2025-04-24 | 2025-07-16 | 2025-05-01 | 2025-07-16 | 2025-05-07 | 2025-07-16 | 2025-05-10 | 2025-07-21 | 2025-06-09 | 2025-08-22 | 2025-06-19 | 2025-08-22 | 2025-07-09 | 2025-08-22 | 2025-07-16 | 2025-09-18 | 2025-07-23 | 2025-10-16 | 2025-07-28 | 2025-10-16 | 2025-08-07 |  | - | 95 | 5445633 |  | 2993100 | 2636250 | 356850 | Keesafety | 150 | 2025-07-28 | -80 | 67 | 2025-10-14 | -2 | 2025-10-16 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
30 | PS10 | Garbage Chute | Jayantha | 2025-04-24 | 2025-07-16 | 2025-05-01 | 2025-07-08 | 2025-05-07 | 2025-07-10 | 2025-05-10 | 2025-07-21 | 2025-06-09 | 2025-09-01 | 2025-06-19 | 2025-09-01 | 2025-07-09 | 2025-09-01 | 2025-07-16 | 2025-09-25 | 2025-07-23 | 2025-09-29 | 2025-07-28 | 2025-10-09 | 2025-08-07 |  | - | 95 | 3106693 |  | 1782931 | 1229048 | 553883 | Pearl Industries | 150 | 2025-07-28 | -73 | 17 | 2025-08-16 | -54 | 2025-10-09 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
31 | PS7 | Metal Doors | Jayantha | 2025-05-24 | 2025-07-16 | 2025-05-31 | 2025-07-16 | 2025-06-06 | 2025-07-16 | 2025-06-09 | 2025-07-16 | 2025-07-09 | 2025-08-28 | 2025-07-19 | 2025-08-28 | 2025-08-08 | 2025-08-28 | 2025-08-15 | 2025-09-22 | 2025-08-22 | 2025-10-16 | 2025-08-27 | 2025-10-16 | 2025-09-06 |  | - | 95 | 3788724 |  | 1603180 | 1885506 | -282326 | Momentum | 180 | 2025-08-27 | -50 | 23 | 2025-09-23 | -23 | 2025-10-16 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
32 | PS16 | Steam & Sauna | Jayantha | 2025-05-24 | 2025-07-28 | 2025-05-31 | 2025-09-29 | 2025-06-06 | 2025-09-26 | 2025-06-09 | 2025-09-30 | 2025-07-09 | 2025-10-13 | 2025-07-19 | 2025-10-13 | 2025-08-08 | 2025-10-13 | 2025-08-15 | 2025-10-27 | 2025-08-22 | 2025-12-09 | 2025-08-27 | 2025-12-17 | 2025-09-06 |  | - | 95 | 296460 |  | 216987 | 1212106 | -995119 | Sportsline | 180 | 2025-08-27 | -112 | 42 | 2025-10-15 | -63 | 2025-12-17 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
33 | PS16 | Spa Equipment | Jayantha | 2025-05-24 | 2025-07-28 | 2025-05-31 | 2025-09-29 | 2025-06-06 | 2025-09-26 | 2025-06-09 | 2025-09-30 | 2025-07-09 | 2025-10-13 | 2025-07-19 | 2025-10-13 | 2025-08-08 | 2025-10-13 | 2025-08-15 | 2025-10-27 | 2025-08-22 | 2025-12-09 | 2025-08-27 | 2025-12-17 | 2025-09-06 |  | - | 95 | 2000000 |  | 1084880 | incl. above | 1084880 | Sportsline | 180 | 2025-08-27 | -112 | 129 | 2026-01-24 | 38 | 2025-12-17 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
34 | PS8b | Loose Furniture & Artworks (Internal) | Jayantha | 2025-09-21 | 2025-10-10 | 2025-09-28 | 2025-10-20 | 2025-10-04 | 2025-10-20 | 2025-10-07 |  | 2025-11-06 |  | 2025-11-16 |  | 2025-12-06 |  | 2025-12-13 |  | 2025-12-20 |  | 2025-12-25 |  | 2026-01-04 |  | 170 | 95 | 8064466 |  | 1613190 |  |  |  | 300 | 2025-12-25 | -178 | 228 | 2026-09-17 | 88 | 2026-06-21 | 4. Tender Float | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
35 | PS8b | Waste Bins | Jayantha | 2025-09-21 | 2025-10-10 | 2025-09-28 | 2025-10-20 | 2025-10-04 | 2025-10-20 | 2025-10-07 |  | 2025-11-06 |  | 2025-11-16 |  | 2025-12-06 |  | 2025-12-13 |  | 2025-12-20 |  | 2025-12-25 |  | 2026-01-04 |  | 170 | 95 | Partially Included in Kitchen cabinets |  |  | Incl on Joinery | 0 | Abaad | 300 | 2025-12-25 | -178 | 228 | 2026-09-17 | 88 | 2026-06-21 | 4. Tender Float | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
36 | PS8b | Gym Equipment - FW Lifefitness | Jayantha | 2025-09-21 | 2025-10-10 | 2025-09-28 | 2025-10-20 | 2025-10-04 | 2025-10-20 | 2025-10-07 | 2026-01-26 | 2025-11-06 |  | 2025-11-16 |  | 2025-12-06 |  | 2025-12-13 |  | 2025-12-20 |  | 2025-12-25 |  | 2026-01-04 |  | -32 | 95 | 1937980 |  | 1051238 |  |  |  | 300 | 2025-12-25 | -175 | 55 | 2026-02-27 | -111 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
37 | PS8b | Parking Accessories | Jayantha | 2025-09-21 | 2025-10-10 | 2025-09-28 | 2025-10-20 | 2025-10-04 | 2025-10-20 | 2025-10-07 | 2026-01-26 | 2025-11-06 |  | 2025-11-16 |  | 2025-12-06 |  | 2025-12-13 |  | 2025-12-20 |  | 2025-12-25 |  | 2026-01-04 |  | -39 | 95 | 1463114 |  | 835315 | 450321 | 384994 | Ocean Rubber | 300 | 2025-12-25 | -175 | 49 | 2026-02-20 | -118 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
38 | PS12 | Signage | Jayantha | 2025-09-21 | 2025-07-16 | 2025-09-28 | 2025-07-16 | 2025-10-04 | 2025-07-16 | 2025-10-07 | 2026-01-21 | 2025-11-06 |  | 2025-11-16 |  | 2025-12-06 |  | 2025-12-13 |  | 2025-12-20 |  | 2025-12-25 |  | 2026-01-04 |  | -39 | 95 | 1955160 |  | 1104443 | 1476300 | -371857 | Axon Singage | 300 | 2025-12-25 | -175 | 49 | 2026-02-20 | -118 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
39 | PS15 | White Goods | Jayantha | 2025-09-21 | 2025-07-28 | 2025-09-28 | 2025-07-28 | 2025-10-04 | 2025-11-17 | 2025-10-07 | 2025-11-24 | 2025-11-06 |  | 2025-11-16 |  | 2025-12-06 |  | 2025-12-13 |  | 2025-12-20 |  | 2025-12-25 |  | 2026-01-04 |  | 112 | 95 | 14335281 |  | 3236620 |  |  |  | 300 | 2025-12-25 | -175 | 178 | 2026-07-21 | 33 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | Total | [25 empty] | 487533181 | 0 | 253929721 | 270410508.7 | -35839992.7
Pearl 3
| 1 | GRC S/C agreement signed still remaing scaffolding
| 2 | Garbage chutre S/C performance - Mitigation plan done Innova
| 3 | Marble Valencia Marble - will be solved this week - Additional IFC is solved this week | [25 empty] | Adendum to the nomination
| 4 | RAK :- excluding third party testing for tiles | [25 empty] | Waive no requirements
| 5 | Drywall S/C Obaid Al Abedly - Objection from Innovo | [25 empty] | S/C agreement already sent on 13 April 2026
| 6 | Pent House | [25 empty] | VO in case of same items
| 7 | Glass Update for U Value
8
9
10
11
Formulas:
LDC = [Supervision]-H7
Supervision = [BUA (m2)]-J7
BUA (m2) = [Award Date]-L7
Award Date = [Plan]-N7
Plan = [Value Summary]-P7
Plan = [Plan]-T7
Value Summary = [Plan]-R7

## Nobu
Project |  | Components | Category | LDC | PMC | Supervision | Contractor | BUA (m2) | GFA (m2) | Award Date | Commencement |  |  | Value Summary |  |  |  |  | Actual to date Impact on Value | [5 empty] | Packages Summary |  |  | Delay Summary |  | nos. | Max delay
[14 empty] | Project Lump Sum Value in LAFO |  |  |  |  | Awards up to date (incl. OHP) |  |  | 453029998 | 92% |  | Total Packages (nos) |  | 19 | Current delayed remaining packages |  | 8 | -206
Nobu Hotel & Branded Residences |  | 4 Buildings 2B+G+7 floors | Hotel & Branded Resi | RSP | Hill | Egis | Fibrex | 67039 | 50773 | 2025-05-01 | 2025-05-26 |  |  | PS - Lump Sum Value in LAFO |  |  | 638589585 |  | Remaining to award |  |  | 39399815 | 8.001% |  | Finalized Packages (nos) |  | 7 | Forecast Delay to Contract |  | 18 | -299
[14 empty] | PS - Contract Value (incl. OHP) |  |  | 474400000 |  | Finalized Packages Savings against Lump Sum |  |  | 123229542 | #DIV/0! |  | Days Since Award (days) |  | 334 | Forecast Delay to Baseline |  | 16 | -225
[19 empty] | Finalized Packages Savings against contract PS |  |  | -18029813 | #DIV/0!
Data Date |  | 2026-03-31
SN | Pkg No. | Package | Package Manager | 15 |  | 7 |  | 6 |  | 3 |  | 30 |  | 10 |  | 20 |  | 7 |  | 7 |  | 5 |  | 10 |  | Variance from Today | PS Procurement Duration | PS - Lump Sum Value in LAFO | PS - Contract Value (excl. OHP) | PS - Contract Value (incl. OHP) | PS - Award Value (incl. OHP) | Saving (against PS in contract) | Awarded Sub-contractor | Cont Dur | Contract Date Nomination | Var | Float | Late Date in Programme | Var | Actual / Forecast Award | Current Stage (from 1-11) | 1. Tender Docs & BOQ | 2. Bidder List | 3. EOI | 4. Tender Float | 5. Initial submission | 6. Tech & Com Review | 7. BAFO | 8. Tech & Com Review | 9. Award Rec. Approval | 10. Issued to Contractor | 11. Subcontract signed
|  |  |  | 1. Tender Docs & BOQ |  | 2. Bidder List |  | 3. EOI |  | 4. Tender Float |  | 5. Initial submission |  | 6. Tech & Com Review |  | 7. BAFO |  | 8. Tech & Com Review |  | 9. Award Rec. Approval |  | 10. Issued to Contractor |  | 11. Subcontract Agreement signed
|  |  |  | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast
MEP Works
1 | PS13 | MEP Works | Manoj | 2025-04-20 | 2025-03-20 | 2025-04-27 | 2025-03-30 | 2025-05-03 | 2025-04-06 | 2025-05-06 | 2025-04-20 | 2025-06-05 | 2025-06-03 | 2025-06-15 | 2025-06-03 | 2025-07-05 | 2025-06-03 | 2025-07-12 | 2025-06-24 | 2025-07-19 | 2025-07-23 | 2025-07-24 | 2025-07-29 | 2025-08-03 |  | - | 95 | 269189625 |  | 165000000 | 172649400 | -7649400 | ARCO | 60 | 2025-07-24 | -5 | 0 | 2025-07-24 | -5 | 2025-07-29 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2 | PS9 | Sanitaryware | Manoj | 2025-08-18 | 2025-05-20 | 2025-08-25 | 2025-06-06 | 2025-08-31 | 2025-06-06 | 2025-09-03 | 2025-06-10 | 2025-10-03 | 2025-06-30 | 2025-10-13 | 2025-06-30 | 2025-11-02 | 2025-06-30 | 2025-11-09 | 2025-07-02 | 2025-11-16 | 2025-09-30 | 2025-11-21 | 2025-10-06 | 2025-12-01 |  | - | 95 | 24159342 |  | 18000000 | 13913708 | 4086292 | Al futtaim, Metallica, Sobokuva | 180 | 2025-11-21 | 46 | 45 | 2026-01-13 | 99 | 2025-10-06 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
3 | PS10 | Light Fittings | Manoj | 2025-12-16 | 2025-09-01 | 2025-12-23 | 2025-09-03 | 2025-12-29 | 2025-07-30 | 2026-01-01 | 2025-11-15 | 2026-01-31 |  | 2026-02-10 |  | 2026-03-02 |  | 2026-03-09 |  | 2026-03-16 |  | 2026-03-21 |  | 2026-03-31 |  | 25 | 95 | 9766385 |  | 10000000 |  |  |  | 300 | 2026-03-21 | -89 | 30 | 2026-04-25 | -54 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Aluminum & Metal Works
4 | PS11 | Aluminium And Glazing | Prabhu | 2025-07-19 | 2025-07-16 | 2025-07-26 | 2025-09-11 | 2025-08-01 | 2025-09-11 | 2025-08-04 | 2025-09-18 | 2025-09-03 | 2025-10-30 | 2025-09-13 | 2025-10-30 | 2025-10-03 | 2025-10-30 | 2025-10-10 | 2025-11-18 | 2025-10-17 | 2026-01-14 | 2025-10-22 | 2026-01-28 | 2025-11-01 |  | - | 95 | 97091898 |  | 80000000 | 99755700 | -19755700 | Aluglex | 150 | 2025-10-22 | -98 | 0 | 2025-10-22 | -98 | 2026-01-28 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
5 | PS12 | GRC | Prabhu | 2025-07-19 | 2025-09-18 | 2025-07-26 | 2025-10-03 | 2025-08-01 | 2025-10-06 | 2025-08-04 | 2025-09-29 | 2025-09-03 | 2025-10-29 | 2025-09-13 | 2025-10-29 | 2025-10-03 | 2025-10-29 | 2025-10-10 | 2025-11-24 | 2025-10-17 | 2026-01-30 | 2025-10-22 |  | 2025-11-01 |  | - | 95 | 17382491 |  | 4000000 | 15291232 | -11291232 | Fibrex | 150 | 2025-10-22 | -165 | 45 | 2025-12-13 | -113 | 2026-04-05 | 10. Issued to Contractor | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
Joinery and Carpentry
6 | PS7 | Timber doors | Suhail | 2025-10-17 | 2025-08-14 | 2025-10-24 | 2025-08-14 | 2025-10-30 | 2025-08-14 | 2025-11-02 | 2025-07-09 | 2025-12-02 | 2025-10-28 | 2025-12-12 | 2025-10-28 | 2026-01-01 | 2025-10-28 | 2026-01-08 | 2025-10-28 | 2026-01-15 |  | 2026-01-20 |  | 2026-01-30 |  | -35 | 95 | 12496084 |  | 8500000 | 57014469 | -48514469 | Fibrex | 240 | 2026-01-20 | -82 | 30 | 2026-02-24 | -47 | 2026-04-12 | 9. Award Rec. Approval | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
7 | PS6 | Wood Works (engineered wood,wood ceiling ,wood wall, kitchen, wardrobes, vanity, fixed furniture for guest rooms) | Suhail | 2025-10-17 | 2025-08-14 | 2025-10-24 | 2025-08-14 | 2025-10-30 | 2025-08-14 | 2025-11-02 | 2025-07-09 | 2025-12-02 | 2025-10-28 | 2025-12-12 | 2025-10-28 | 2026-01-01 | 2025-10-28 | 2026-01-08 | 2025-10-28 | 2026-01-15 |  | 2026-01-20 |  | 2026-01-30 |  | -35 | 95 | 59597134 |  | 74000000 | incl. above | 74000000 | Fibrex | 240 | 2026-01-20 | -82 | 30 | 2026-02-24 | -47 | 2026-04-12 | 9. Award Rec. Approval | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
8 | PS7 | Kitchen & Wardrobes |  | 2025-10-17 | 2025-08-15 | 2025-10-24 | 2025-08-15 | 2025-10-30 | 2025-08-15 | 2025-11-02 | 2026-01-25 | 2025-12-02 |  | 2025-12-12 |  | 2026-01-01 |  | 2026-01-08 |  | 2026-01-15 |  | 2026-01-20 |  | 2026-01-30 |  | -34 | 95 | [6 empty] | 240 | 2026-01-20 | -149 | 31 | 2026-02-25 | -113 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Finishes
9 | PS1 | Finishes (internal,tiles,stone ,paints,ceiling, Polished/Decorative /Acoustic plaster, Vinyl, Carpets etc..) | Prabhu | 2025-08-18 | 2025-08-14 | 2025-08-25 | 2025-08-14 | 2025-08-31 | 2025-08-14 | 2025-09-03 | 2025-07-09 | 2025-10-03 | 2025-10-28 | 2025-10-13 | 2025-10-28 | 2025-11-02 | 2025-10-28 | 2025-11-09 | 2025-10-28 | 2025-11-16 | 2025-12-03 | 2025-11-21 | 2025-12-03 | 2025-12-01 |  | - | 95 | 41187545 |  | 65000000 | 57393120 | 7606880 | Fibrex | 180 | 2025-11-21 | -12 | 45 | 2026-01-13 | 41 | 2025-12-03 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
10 | PS14 | External Stone Wall Cladding | Prabhu | 2025-07-19 | 2025-09-18 | 2025-07-26 | 2025-10-03 | 2025-08-01 | 2025-10-06 | 2025-08-04 | 2025-09-29 | 2025-09-03 | 2025-10-30 | 2025-09-13 | 2025-10-30 | 2025-10-03 | 2025-10-30 | 2025-10-10 | 2025-11-18 | 2025-10-17 | 2026-01-14 | 2025-10-22 | 2026-01-28 | 2025-11-01 |  | - | 95 | 2622246 |  | 5000000 | 2952460 | 2047540 | Stonetta | 150 | 2025-10-22 | -98 | 45 | 2025-12-13 | -46 | 2026-01-28 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
11 | PS2 | Dry Wall Partitions | Reyoon | 2025-05-20 | 2025-09-03 | 2025-05-27 | 2025-09-10 | 2025-06-02 | 2025-09-10 | 2025-06-05 | 2025-09-17 | 2025-07-05 | 2025-10-20 | 2025-07-15 | 2025-10-20 | 2025-08-04 | 2025-10-20 | 2025-08-11 |  | 2025-08-18 |  | 2025-08-23 |  | 2025-09-02 |  | -206 | 95 | 9314948 |  | 2661592 | 7621550 | -4959958 | Perfect Building Materials | 90 | 2025-08-23 | -239 | 12 | 2025-09-06 | -225 | 2026-04-19 | 8. Tech & Com Review | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE
External Works
12 | PS3 | Swimming Pools | Suhail | 2025-05-20 | 2025-07-21 | 2025-05-27 | 2025-07-30 | 2025-06-02 | 2025-07-30 | 2025-06-05 | 2025-08-29 | 2025-07-05 | 2025-10-30 | 2025-07-15 | 2025-10-30 | 2025-08-04 | 2025-10-30 | 2025-08-11 | 2025-11-18 | 2025-08-18 | 2025-12-11 | 2025-08-23 | 2025-12-12 | 2025-09-02 |  | - | 95 | 28197056 |  | 4100000 | 17602759 | -13502759 | Donrite | 90 | 2025-08-23 | -111 | 60 | 2025-11-01 | -41 | 2025-12-12 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
Equipments & Accessories
13 | PS5 | Lifts | Manoj | 2025-05-20 | 2025-06-11 | 2025-05-27 | 2025-06-12 | 2025-06-02 | 2025-06-16 | 2025-06-05 | 2025-07-03 | 2025-07-05 | 2025-07-17 | 2025-07-15 | 2025-07-17 | 2025-08-04 | 2025-07-17 | 2025-08-11 | 2025-08-26 | 2025-08-18 | 2025-08-29 | 2025-08-23 | 2025-09-03 | 2025-09-02 |  | - | 95 | 12436266 |  | 8000000 | 7503600 | 496400 | Kone | 90 | 2025-08-23 | -11 | 0 | 2025-08-23 | -11 | 2025-09-03 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
14 | PS18 | Steam and Sauna | Jayantha | 2025-08-18 | 2025-09-10 | 2025-08-25 | 2025-10-21 | 2025-08-31 | 2025-10-21 | 2025-09-03 | 2025-11-27 | 2025-10-03 | 2025-12-05 | 2025-10-13 | 2025-12-05 | 2025-11-02 | 2025-12-05 | 2025-11-09 |  | 2025-11-16 |  | 2025-11-21 |  | 2025-12-01 |  | -60 | 95 | 2074817 |  | 592844 |  |  |  | 180 | 2025-11-21 | -149 | 60 | 2026-01-30 | -79 | 2026-04-19 | 8. Tech & Com Review | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE
15 | PS16 | BMU | Prabhu | 2025-08-18 | 2025-07-25 | 2025-08-25 | 2025-10-21 | 2025-08-31 | 2025-10-21 | 2025-09-03 | 2025-11-10 | 2025-10-03 | 2025-11-18 | 2025-10-13 | 2025-11-18 | 2025-11-02 | 2025-11-18 | 2025-11-09 |  | 2025-11-16 |  | 2025-11-21 |  | 2025-12-01 |  | -60 | 95 | 2584905 |  | 738593 | 1332000 | -593407 |  | 180 | 2025-11-21 | -149 | 60 | 2026-01-30 | -79 | 2026-04-19 | 8. Tech & Com Review | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE
16 | PS17 | Laundry Equipment | Jayantha | 2025-08-18 | 2025-11-10 | 2025-08-25 | 2025-11-10 | 2025-08-31 | 2025-11-10 | 2025-09-03 |  | 2025-10-03 |  | 2025-10-13 |  | 2025-11-02 |  | 2025-11-09 |  | 2025-11-16 |  | 2025-11-21 |  | 2025-12-01 |  | -12 | 95 | 712276.4 |  | 477225.998 |  |  |  | 180 | 2025-11-21 | -212 | 101 | 2026-03-19 | -94 | 2026-06-21 | 4. Tender Float | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
17 | PS8 | Kitchen equipments & White goods | Jayantha | 2025-08-18 | 2025-11-10 | 2025-08-25 | 2025-11-10 | 2025-08-31 | 2025-11-10 | 2025-09-03 | 2026-02-02 | 2025-10-03 |  | 2025-10-13 |  | 2025-11-02 |  | 2025-11-09 |  | 2025-11-16 |  | 2025-11-21 |  | 2025-12-01 |  | -77 | 95 | 26380869.6 |  | 17522774.002 |  |  |  | 180 | 2025-11-21 | -209 | 45 | 2026-01-13 | -156 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
18 | PS4 | Furnishing (curtain track) | Jayantha | 2025-10-17 | 2025-11-10 | 2025-10-24 | 2025-11-10 | 2025-10-30 | 2025-11-10 | 2025-11-02 |  | 2025-12-02 |  | 2025-12-12 |  | 2026-01-01 |  | 2026-01-08 |  | 2026-01-15 |  | 2026-01-20 |  | 2026-01-30 |  | 163 | 95 | 8322316 |  | 6500000 |  |  |  | 240 | 2026-01-20 | -152 | 200 | 2026-09-10 | 81 | 2026-06-21 | 4. Tender Float | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
19 | PS3 | Accessories (Others - Parking accessories, signage, movable partitions, cubicle) | Jayantha | 2025-05-20 | 2026-01-01 | 2025-05-27 | 2026-01-05 | 2025-06-02 | 2026-01-10 | 2025-06-05 | 2026-02-02 | 2025-07-05 |  | 2025-07-15 |  | 2025-08-04 |  | 2025-08-11 |  | 2025-08-18 |  | 2025-08-23 |  | 2025-09-02 |  | 72 | 95 | 15073381 |  | 4306971 |  |  |  | 90 | 2025-08-23 | -299 | 250 | 2026-06-11 | -7 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | Total | [25 empty] | 638589585 | 0 | 474400000 | 453029998 | -18029813
Fibrex
| 1 | Kitchen & Wardobes | [25 empty] | This week will be finalized , alternative proposed ( check what |  |  | By early next week
| 2 | Light fitting | [25 empty] | Floated in the market
| 3 | Whaite Goods
4
5
6
7
8
9
10
Formulas:
LDC = [Supervision]-H7
Supervision = [BUA (m2)]-J7
BUA (m2) = [Award Date]-L7
Award Date = [Plan]-N7
Plan = [Value Summary]-P7
Plan = [Plan]-T7
Value Summary = [Plan]-R7

## Grove 6&7
Project |  | Components | Category | LDC | PMC | Supervision | Contractor | BUA (m2) | GFA (m2) | Award Date | Commencement |  |  | Value Summary |  |  |  |  | Actual to date Impact on Value | [5 empty] | Packages Summary |  |  | Delay Summary |  | nos. | Max delay | [21 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
[14 empty] | Project Lump Sum Value in LAFO |  |  |  |  | Awards up to date (incl. OHP) |  |  | 200928000 | 33.22% |  | Total Packages (nos) |  | 52 | Current delayed remaining packages |  | 3 | -1 | [21 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE
Arthouse Grove 6&7 |  | 3 Buildings 2B+G+9 | Resi Buildings | Atkins | Hill | Atkins | Dutco | 146848 | 71043 | 2025-12-31 | 2026-03-31 |  |  | PS - Lump Sum Value in LAFO |  |  | 0 |  | Remaining to award |  |  | 403862496 | 66.78% |  | Finalized Packages (nos) |  | 1 | Forecast Delay to Contract |  | 32 | -96 | [21 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE
[14 empty] | PS - Contract Value (incl. OHP) |  |  | 630893318 |  | Finalized Packages Savings against Lump Sum |  |  | -200928000 | #DIV/0! |  | Days Since Award (days) |  | 90 | Forecast Delay to Baseline |  | 32 | -96 | [21 empty] | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
[19 empty] | Finalized Packages Savings against contract PS |  |  | 26102822 | #DIV/0!
Data Date |  | 2026-03-31 | [31 empty] | Tentative | [18 empty] | 21
SN | Pkg No. | Package | Package Manager | 15 |  | 7 |  | 6 |  | 3 |  | 30 |  | 10 |  | 20 |  | 7 |  | 7 |  | 5 |  | 10 |  | Variance from Today | PS Procurement Duration | PS - Lump Sum Value in LAFO | PS - Contract Value (excl. OHP) | PS - Contract Value (incl. OHP) | PS - Award Value (incl. OHP) | Saving (against PS in contract) | Awarded Sub-contractor | Cont Dur | Contract Date Nomination | Var | Float | Late Date in Programme | Var | Actual / Forecast Award | Current Stage (from 1-11) | 1. Tender Docs & BOQ | 2. Bidder List | 3. EOI | 4. Tender Float | 5. Initial submission | 6. Tech & Com Review | 7. BAFO | 8. Tech & Com Review | 9. Award Rec. Approval | 10. Issued to Contractor | 11. Subcontract signed
|  |  |  | 1. Tender Docs & BOQ |  | 2. Bidder List |  | 3. EOI |  | 4. Tender Float |  | 5. Initial submission |  | 6. Tech & Com Review |  | 7. BAFO |  | 8. Tech & Com Review |  | 9. Award Rec. Approval |  | 10. Issued to Contractor |  | 11. Subcontract Agreement signed
|  |  |  | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast
MEP Works
1 |  | MEP Works | Manoj | 2025-12-25 | 2025-12-25 | 2026-01-01 | 2026-01-01 | 2026-01-07 | 2026-01-07 | 2026-01-10 | 2026-01-10 | 2026-02-09 | 2026-02-09 | 2026-02-19 | 2026-02-19 | 2026-03-11 | 2026-03-11 | 2026-03-18 | 2026-03-18 | 2026-03-25 | 2026-03-25 | 2026-03-30 | 2026-03-30 | 2026-04-09 |  | - | 95 |  |  | 227030822 | 200928000 | 26102822 | ARCO | 0 | 2026-03-30 | 0 |  | 2026-03-30 | 0 | 2026-03-30 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2 |  | FOH light fittings | Manoj | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09; 2026-03-18: 2026-07-16; 2026-03-25: 2026-07-23; 2026-03-30: 2026-07-28; 2026-04-09: 2026-08-07 |  | 119 | 95 |  |  | 14824000 |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3 |  | BOH light fittings | Manoj | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09; 2026-03-18: 2026-07-16; 2026-03-25: 2026-07-23; 2026-03-30: 2026-07-28; 2026-04-09: 2026-08-07 |  | 119 | 95 |  |  | 24128344 |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4 |  | Sanitary fixtures | Manoj | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09; 2026-03-18: 2026-07-16; 2026-03-25: 2026-07-23; 2026-03-30: 2026-07-28; 2026-04-09: 2026-08-07 |  | 119 | 95 |  |  | 29792022 |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Aluminum & Metal Works
5 |  | Non - structural metal works | Prabhu | 2025-12-25: 2026-03-10; 2026-01-01: 2026-03-17; 2026-01-07: 2026-03-23; 2026-01-10: 2026-03-26; 2026-02-09: 2026-04-25; 2026-02-19: 2026-05-05; 2026-03-11: 2026-05-25; 2026-03-18: 2026-06-01; 2026-03-25: 2026-06-08; 2026-03-30: 2026-06-13; 2026-04-09: 2026-06-23 |  | 74 | 95 |  |  | 27835330 |  |  |  | 75 | 2026-06-13 | -21 |  | 2026-06-13 | -21 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
6 |  | Structural metal works | Prabhu | 2025-12-25: 2026-03-10; 2026-01-01: 2026-03-17; 2026-01-07: 2026-03-23; 2026-01-10: 2026-03-26; 2026-02-09: 2026-04-25; 2026-02-19: 2026-05-05; 2026-03-11: 2026-05-25; 2026-03-18: 2026-06-01; 2026-03-25: 2026-06-08; 2026-03-30: 2026-06-13; 2026-04-09: 2026-06-23 |  | 74 | 95 |  |  | incl. above |  |  |  | 75 | 2026-06-13 | -21 |  | 2026-06-13 | -21 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
7 |  | Steel Door | Prabhu | 2025-12-25: 2026-03-10; 2026-01-01: 2026-03-17; 2026-01-07: 2026-03-23; 2026-01-10: 2026-03-26; 2026-02-09: 2026-04-25; 2026-02-19: 2026-05-05; 2026-03-11: 2026-05-25; 2026-03-18: 2026-06-01; 2026-03-25: 2026-06-08; 2026-03-30: 2026-06-13; 2026-04-09: 2026-06-23 |  | 74 | 95 |  |  | 71870400 |  |  |  | 75 | 2026-06-13 | -21 |  | 2026-06-13 | -21 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
8 |  | Glazed Door, Curtain Wall, Louver Door | Prabhu | 2025-12-25: 2026-03-10; 2026-01-01: 2026-03-17; 2026-01-07: 2026-03-23; 2026-01-10: 2026-03-26; 2026-02-09: 2026-04-25; 2026-02-19: 2026-05-05; 2026-03-11: 2026-05-25; 2026-03-18: 2026-06-01; 2026-03-25: 2026-06-08; 2026-03-30: 2026-06-13; 2026-04-09: 2026-06-23 |  | 74 | 95 |  |  | incl. above |  |  |  | 75 | 2026-06-13 | -21 |  | 2026-06-13 | -21 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
9 |  | Ironmongery | Prabhu | 2025-12-25: 2026-03-10; 2026-01-01: 2026-03-17; 2026-01-07: 2026-03-23; 2026-01-10: 2026-03-26; 2026-02-09: 2026-04-25; 2026-02-19: 2026-05-05; 2026-03-11: 2026-05-25; 2026-03-18: 2026-06-01; 2026-03-25: 2026-06-08; 2026-03-30: 2026-06-13; 2026-04-09: 2026-06-23 |  | 74 | 95 |  |  | incl. above |  |  |  | 75 | 2026-06-13 | -21 |  | 2026-06-13 | -21 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Joinery and Carpentry
10 |  | Wardrobes | Suhail | 2025-12-25: 2026-04-04; 2026-01-01: 2026-04-11; 2026-01-07: 2026-04-17; 2026-01-10: 2026-04-20; 2026-02-09: 2026-05-20; 2026-02-19: 2026-05-30; 2026-03-11: 2026-06-19; 2026-03-18: 2026-06-26; 2026-03-25: 2026-07-03; 2026-03-30: 2026-07-08; 2026-04-09: 2026-07-18 |  | 99 | 95 |  |  | 43705730 |  |  |  | 100 | 2026-07-08 | 4 |  | 2026-07-08 | 4 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
[42 empty] | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
11 |  | Vanity units | Suhail | 2025-12-25: 2025-12-25; 2026-01-01: 2026-01-01; 2026-01-07: 2026-01-07; 2026-01-10: 2026-01-10; 2026-02-09: 2026-02-09; 2026-02-19: 2026-02-19; 2026-03-11: 2026-03-11; 2026-03-18: 2026-03-18; 2026-03-25: 2026-03-25; 2026-03-30: 2026-03-30; 2026-04-09: 2026-04-09 |  | -1 | 95 |  |  | incl. above |  |  |  | 0 | 2026-03-30 | -96 |  | 2026-03-30 | -96 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
12 |  | TV Shelves, Lockers | Suhail | 2025-12-25: 2025-12-25; 2026-01-01: 2026-01-01; 2026-01-07: 2026-01-07; 2026-01-10: 2026-01-10; 2026-02-09: 2026-02-09; 2026-02-19: 2026-02-19; 2026-03-11: 2026-03-11; 2026-03-18: 2026-03-18; 2026-03-25: 2026-03-25; 2026-03-30: 2026-03-30; 2026-04-09: 2026-04-09 |  | -1 | 95 |  |  | incl. above |  |  |  | 0 | 2026-03-30 | -96 |  | 2026-03-30 | -96 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
13 |  | Other Millwork | Suhail | 2025-12-25: 2025-12-25; 2026-01-01: 2026-01-01; 2026-01-07: 2026-01-07; 2026-01-10: 2026-01-10; 2026-02-09: 2026-02-09; 2026-02-19: 2026-02-19; 2026-03-11: 2026-03-11; 2026-03-18: 2026-03-18; 2026-03-25: 2026-03-25; 2026-03-30: 2026-03-30; 2026-04-09: 2026-04-09 |  | -1 | 95 |  |  | incl. above |  |  |  | 0 | 2026-03-30 | -96 |  | 2026-03-30 | -96 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Finishes
14 |  | Acosutic Underlayment | Reyoon | 2025-12-25: 2026-03-15; 2026-01-01: 2026-03-22; 2026-01-07: 2026-03-28; 2026-01-10: 2026-03-31; 2026-02-09: 2026-04-30; 2026-02-19: 2026-05-10; 2026-03-11: 2026-05-30; 2026-03-18: 2026-06-06; 2026-03-25: 2026-06-13; 2026-03-30: 2026-06-18; 2026-04-09: 2026-06-28 |  | 79 | 95 |  |  | 107602620 |  |  |  | 80 | 2026-06-18 | -16 |  | 2026-06-18 | -16 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
15 |  | Tiles - Floor, Walls, Skirting, Threshold | Reyoon | 2025-12-25: 2026-03-15; 2026-01-01: 2026-03-22; 2026-01-07: 2026-03-28; 2026-01-10: 2026-03-31; 2026-02-09: 2026-04-30; 2026-02-19: 2026-05-10; 2026-03-11: 2026-05-30; 2026-03-18: 2026-06-06; 2026-03-25: 2026-06-13; 2026-03-30: 2026-06-18; 2026-04-09: 2026-06-28 |  | 79 | 95 |  |  | incl. above |  |  |  | 80 | 2026-06-18 | -16 |  | 2026-06-18 | -16 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
16 |  | Resilleint Flooring | Reyoon | 2025-12-25: 2026-03-15; 2026-01-01: 2026-03-22; 2026-01-07: 2026-03-28; 2026-01-10: 2026-03-31; 2026-02-09: 2026-04-30; 2026-02-19: 2026-05-10; 2026-03-11: 2026-05-30; 2026-03-18: 2026-06-06; 2026-03-25: 2026-06-13; 2026-03-30: 2026-06-18; 2026-04-09: 2026-06-28 |  | 79 | 95 |  |  | incl. above |  |  |  | 80 | 2026-06-18 | -16 |  | 2026-06-18 | -16 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
17 |  | Wooden Flooring | Reyoon | 2025-12-25: 2026-03-15; 2026-01-01: 2026-03-22; 2026-01-07: 2026-03-28; 2026-01-10: 2026-03-31; 2026-02-09: 2026-04-30; 2026-02-19: 2026-05-10; 2026-03-11: 2026-05-30; 2026-03-18: 2026-06-06; 2026-03-25: 2026-06-13; 2026-03-30: 2026-06-18; 2026-04-09: 2026-06-28 |  | 79 | 95 |  |  | incl. above |  |  |  | 80 | 2026-06-18 | -16 |  | 2026-06-18 | -16 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
18 |  | Paint - Internal and External | Reyoon | 2025-12-25: 2026-03-15; 2026-01-01: 2026-03-22; 2026-01-07: 2026-03-28; 2026-01-10: 2026-03-31; 2026-02-09: 2026-04-30; 2026-02-19: 2026-05-10; 2026-03-11: 2026-05-30; 2026-03-18: 2026-06-06; 2026-03-25: 2026-06-13; 2026-03-30: 2026-06-18; 2026-04-09: 2026-06-28 |  | 79 | 95 |  |  | incl. above |  |  |  | 80 | 2026-06-18 | -16 |  | 2026-06-18 | -16 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
19 |  | Wallpaper | Reyoon | 2025-12-25: 2026-03-15; 2026-01-01: 2026-03-22; 2026-01-07: 2026-03-28; 2026-01-10: 2026-03-31; 2026-02-09: 2026-04-30; 2026-02-19: 2026-05-10; 2026-03-11: 2026-05-30; 2026-03-18: 2026-06-06; 2026-03-25: 2026-06-13; 2026-03-30: 2026-06-18; 2026-04-09: 2026-06-28 |  | 79 | 95 |  |  | incl. above |  |  |  | 80 | 2026-06-18 | -16 |  | 2026-06-18 | -16 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
20 |  | Acoustic Panels | Reyoon | 2025-12-25: 2026-03-15; 2026-01-01: 2026-03-22; 2026-01-07: 2026-03-28; 2026-01-10: 2026-03-31; 2026-02-09: 2026-04-30; 2026-02-19: 2026-05-10; 2026-03-11: 2026-05-30; 2026-03-18: 2026-06-06; 2026-03-25: 2026-06-13; 2026-03-30: 2026-06-18; 2026-04-09: 2026-06-28 |  | 79 | 95 |  |  | incl. above |  |  |  | 80 | 2026-06-18 | -16 |  | 2026-06-18 | -16 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
21 |  | Wood Panels | Reyoon | 2025-12-25: 2026-03-15; 2026-01-01: 2026-03-22; 2026-01-07: 2026-03-28; 2026-01-10: 2026-03-31; 2026-02-09: 2026-04-30; 2026-02-19: 2026-05-10; 2026-03-11: 2026-05-30; 2026-03-18: 2026-06-06; 2026-03-25: 2026-06-13; 2026-03-30: 2026-06-18; 2026-04-09: 2026-06-28 |  | 79 | 95 |  |  | incl. above |  |  |  | 80 | 2026-06-18 | -16 |  | 2026-06-18 | -16 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
22 |  | Stone Cladding | Reyoon | 2025-12-25: 2026-03-15; 2026-01-01: 2026-03-22; 2026-01-07: 2026-03-28; 2026-01-10: 2026-03-31; 2026-02-09: 2026-04-30; 2026-02-19: 2026-05-10; 2026-03-11: 2026-05-30; 2026-03-18: 2026-06-06; 2026-03-25: 2026-06-13; 2026-03-30: 2026-06-18; 2026-04-09: 2026-06-28 |  | 79 | 95 |  |  | incl. above |  |  |  | 80 | 2026-06-18 | -16 |  | 2026-06-18 | -16 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
23 |  | Suspended ceiling | Reyoon | 2025-12-25: 2026-03-15; 2026-01-01: 2026-03-22; 2026-01-07: 2026-03-28; 2026-01-10: 2026-03-31; 2026-02-09: 2026-04-30; 2026-02-19: 2026-05-10; 2026-03-11: 2026-05-30; 2026-03-18: 2026-06-06; 2026-03-25: 2026-06-13; 2026-03-30: 2026-06-18; 2026-04-09: 2026-06-28 |  | 79 | 95 |  |  | incl. above |  |  |  | 80 | 2026-06-18 | -16 |  | 2026-06-18 | -16 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
24 |  | Aluminium Fins, Aluminium Canopy | Prabhu | 2025-12-25: 2026-03-15; 2026-01-01: 2026-03-22; 2026-01-07: 2026-03-28; 2026-01-10: 2026-03-31; 2026-02-09: 2026-04-30; 2026-02-19: 2026-05-10; 2026-03-11: 2026-05-30; 2026-03-18: 2026-06-06; 2026-03-25: 2026-06-13; 2026-03-30: 2026-06-18; 2026-04-09: 2026-06-28 |  | 79 | 95 |  |  | incl. above |  |  |  | 80 | 2026-06-18 | -16 |  | 2026-06-18 | -16 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
25 |  | ACP Cladding | Prabhu | 2025-12-25: 2026-03-15; 2026-01-01: 2026-03-22; 2026-01-07: 2026-03-28; 2026-01-10: 2026-03-31; 2026-02-09: 2026-04-30; 2026-02-19: 2026-05-10; 2026-03-11: 2026-05-30; 2026-03-18: 2026-06-06; 2026-03-25: 2026-06-13; 2026-03-30: 2026-06-18; 2026-04-09: 2026-06-28 |  | 79 | 95 |  |  | incl. above |  |  |  | 80 | 2026-06-18 | -16 |  | 2026-06-18 | -16 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
26 |  | Wild Air | Reyoon | 2025-12-25: 2026-03-15; 2026-01-01: 2026-03-22; 2026-01-07: 2026-03-28; 2026-01-10: 2026-03-31; 2026-02-09: 2026-04-30; 2026-02-19: 2026-05-10; 2026-03-11: 2026-05-30; 2026-03-18: 2026-06-06; 2026-03-25: 2026-06-13; 2026-03-30: 2026-06-18; 2026-04-09: 2026-06-28 |  | 79 | 95 |  |  | 5450000 |  |  |  | 80 | 2026-06-18 | -16 |  | 2026-06-18 | -16 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
External Works
27 |  | Landscape works outside plot boundary | Suhail | 2025-12-25: 2026-03-25; 2026-01-01: 2026-04-01; 2026-01-07: 2026-04-07; 2026-01-10: 2026-04-10; 2026-02-09: 2026-05-10; 2026-02-19: 2026-05-20; 2026-03-11: 2026-06-09; 2026-03-18: 2026-06-16; 2026-03-25: 2026-06-23; 2026-03-30: 2026-06-28; 2026-04-09: 2026-07-08 |  | 89 | 95 |  |  | 3869500 |  |  |  | 90 | 2026-06-28 | -6 |  | 2026-06-28 | -6 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
28 |  | Hardscape | Suhail | 2025-12-25: 2026-03-25; 2026-01-01: 2026-04-01; 2026-01-07: 2026-04-07; 2026-01-10: 2026-04-10; 2026-02-09: 2026-05-10; 2026-02-19: 2026-05-20; 2026-03-11: 2026-06-09; 2026-03-18: 2026-06-16; 2026-03-25: 2026-06-23; 2026-03-30: 2026-06-28; 2026-04-09: 2026-07-08 |  | 89 | 95 |  |  | 37591920 |  |  |  | 90 | 2026-06-28 | -6 |  | 2026-06-28 | -6 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
29 |  | Softscape | Suhail | 2025-12-25: 2026-03-25; 2026-01-01: 2026-04-01; 2026-01-07: 2026-04-07; 2026-01-10: 2026-04-10; 2026-02-09: 2026-05-10; 2026-02-19: 2026-05-20; 2026-03-11: 2026-06-09; 2026-03-18: 2026-06-16; 2026-03-25: 2026-06-23; 2026-03-30: 2026-06-28; 2026-04-09: 2026-07-08 |  | 89 | 95 |  |  | incl. above |  |  |  | 90 | 2026-06-28 | -6 |  | 2026-06-28 | -6 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
30 |  | Signages and Wayfindings | Jayantha | 2025-12-25: 2026-03-25; 2026-01-01: 2026-04-01; 2026-01-07: 2026-04-07; 2026-01-10: 2026-04-10; 2026-02-09: 2026-05-10; 2026-02-19: 2026-05-20; 2026-03-11: 2026-06-09; 2026-03-18: 2026-06-16; 2026-03-25: 2026-06-23; 2026-03-30: 2026-06-28; 2026-04-09: 2026-07-08 |  | 89 | 95 |  |  | incl. above |  |  |  | 90 | 2026-06-28 | -6 |  | 2026-06-28 | -6 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
31 |  | Irrigation, Drainage Installation | Manoj | 2025-12-25: 2026-03-25; 2026-01-01: 2026-04-01; 2026-01-07: 2026-04-07; 2026-01-10: 2026-04-10; 2026-02-09: 2026-05-10; 2026-02-19: 2026-05-20; 2026-03-11: 2026-06-09; 2026-03-18: 2026-06-16; 2026-03-25: 2026-06-23; 2026-03-30: 2026-06-28; 2026-04-09: 2026-07-08 |  | 89 | 95 |  |  | incl. above |  |  |  | 90 | 2026-06-28 | -6 |  | 2026-06-28 | -6 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
32 |  | Ladnscape Lighting | Manoj | 2025-12-25: 2026-03-25; 2026-01-01: 2026-04-01; 2026-01-07: 2026-04-07; 2026-01-10: 2026-04-10; 2026-02-09: 2026-05-10; 2026-02-19: 2026-05-20; 2026-03-11: 2026-06-09; 2026-03-18: 2026-06-16; 2026-03-25: 2026-06-23; 2026-03-30: 2026-06-28; 2026-04-09: 2026-07-08 |  | 89 | 95 |  |  | incl. above |  |  |  | 90 | 2026-06-28 | -6 |  | 2026-06-28 | -6 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
33 |  | Swimming pool, Skyvilla pool | Suhail | 2025-12-25: 2026-03-25; 2026-01-01: 2026-04-01; 2026-01-07: 2026-04-07; 2026-01-10: 2026-04-10; 2026-02-09: 2026-05-10; 2026-02-19: 2026-05-20; 2026-03-11: 2026-06-09; 2026-03-18: 2026-06-16; 2026-03-25: 2026-06-23; 2026-03-30: 2026-06-28; 2026-04-09: 2026-07-08 |  | 89 | 95 |  |  | incl. above |  |  |  | 90 | 2026-06-28 | -6 |  | 2026-06-28 | -6 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
34 |  | Waterfeature | Suhail | 2025-12-25: 2026-03-25; 2026-01-01: 2026-04-01; 2026-01-07: 2026-04-07; 2026-01-10: 2026-04-10; 2026-02-09: 2026-05-10; 2026-02-19: 2026-05-20; 2026-03-11: 2026-06-09; 2026-03-18: 2026-06-16; 2026-03-25: 2026-06-23; 2026-03-30: 2026-06-28; 2026-04-09: 2026-07-08 |  | 89 | 95 |  |  | incl. above |  |  |  | 90 | 2026-06-28 | -6 |  | 2026-06-28 | -6 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
35 |  | CCTV | Manoj | 2025-12-25: 2026-03-25; 2026-01-01: 2026-04-01; 2026-01-07: 2026-04-07; 2026-01-10: 2026-04-10; 2026-02-09: 2026-05-10; 2026-02-19: 2026-05-20; 2026-03-11: 2026-06-09; 2026-03-18: 2026-06-16; 2026-03-25: 2026-06-23; 2026-03-30: 2026-06-28; 2026-04-09: 2026-07-08 |  | 89 | 95 |  |  | incl. above |  |  |  | 90 | 2026-06-28 | -6 |  | 2026-06-28 | -6 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Equipments & Accessories
36 |  | Lifts | Manoj | 2025-12-25: 2026-01-09; 2026-01-01: 2026-01-16; 2026-01-07: 2026-01-22; 2026-01-10: 2026-01-25; 2026-02-09: 2026-02-24; 2026-02-19: 2026-03-06; 2026-03-11: 2026-03-26; 2026-03-18: 2026-04-02; 2026-03-25: 2026-04-09; 2026-03-30: 2026-04-14; 2026-04-09: 2026-04-24 |  | 14 | 95 |  |  | 7515200 |  |  |  | 15 | 2026-04-14 | -81 |  | 2026-04-14 | -81 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
37 |  | White Goods. | Jayantha | 2025-12-25: 2026-01-24; 2026-01-01: 2026-01-31; 2026-01-07: 2026-02-06; 2026-01-10: 2026-02-09; 2026-02-09: 2026-03-11; 2026-02-19: 2026-03-21; 2026-03-11: 2026-04-10; 2026-03-18: 2026-04-17; 2026-03-25: 2026-04-24; 2026-03-30: 2026-04-29; 2026-04-09: 2026-05-09 |  | 29 | 95 |  |  | 5232000 |  |  |  | 30 | 2026-04-29 | -66 |  | 2026-04-29 | -66 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
38 |  | Gym Equipment | Jayantha | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09; 2026-03-18: 2026-07-16; 2026-03-25: 2026-07-23; 2026-03-30: 2026-07-28; 2026-04-09: 2026-08-07 |  | 119 | 95 |  |  | 2779500 |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
39 |  | Loose Furniture to Common spaces/Amenities | Jayantha | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09; 2026-03-18: 2026-07-16; 2026-03-25: 2026-07-23; 2026-03-30: 2026-07-28; 2026-04-09: 2026-08-07 |  | 119 | 95 |  |  | 9374000 |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
40 |  | Glass partitions | Prabhu | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09; 2026-03-18: 2026-07-16; 2026-03-25: 2026-07-23; 2026-03-30: 2026-07-28; 2026-04-09: 2026-08-07 |  | 119 | 95 |  |  | 4332750 |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
41 |  | Parking Accessories | Suhail | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09; 2026-03-18: 2026-07-16; 2026-03-25: 2026-07-23; 2026-03-30: 2026-07-28; 2026-04-09: 2026-08-07 |  | 119 | 95 |  |  | incl. above |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
42 |  | Garbage Chute | Jayantha | 2025-12-25: 2026-10-21; 2026-01-01: 2026-10-28; 2026-01-07: 2026-11-03; 2026-01-10: 2026-11-06; 2026-02-09: 2026-12-06; 2026-02-19: 2026-12-16; 2026-03-11: 2027-01-05; 2026-03-18: 2027-01-12; 2026-03-25: 2027-01-19; 2026-03-30: 2027-01-24; 2026-04-09: 2027-02-03 |  | 299 | 95 |  |  | 5833680 |  |  |  | 300 | 2027-01-24 | 204 |  | 2027-01-24 | 204 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
43 |  | BMU | Jayantha | 2025-12-25: 2026-10-21; 2026-01-01: 2026-10-28; 2026-01-07: 2026-11-03; 2026-01-10: 2026-11-06; 2026-02-09: 2026-12-06; 2026-02-19: 2026-12-16; 2026-03-11: 2027-01-05; 2026-03-18: 2027-01-12; 2026-03-25: 2027-01-19; 2026-03-30: 2027-01-24; 2026-04-09: 2027-02-03 |  | 299 | 95 |  |  | incl. above |  |  |  | 300 | 2027-01-24 | 204 |  | 2027-01-24 | 204 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
44 |  | Docking Equipment | Jayantha | 2025-12-25: 2026-10-21; 2026-01-01: 2026-10-28; 2026-01-07: 2026-11-03; 2026-01-10: 2026-11-06; 2026-02-09: 2026-12-06; 2026-02-19: 2026-12-16; 2026-03-11: 2027-01-05; 2026-03-18: 2027-01-12; 2026-03-25: 2027-01-19; 2026-03-30: 2027-01-24; 2026-04-09: 2027-02-03 |  | 299 | 95 |  |  | incl. above |  |  |  | 300 | 2027-01-24 | 204 |  | 2027-01-24 | 204 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
45 |  | White Goods | Jayantha | 2025-12-25: 2026-10-21; 2026-01-01: 2026-10-28; 2026-01-07: 2026-11-03; 2026-01-10: 2026-11-06; 2026-02-09: 2026-12-06; 2026-02-19: 2026-12-16; 2026-03-11: 2027-01-05; 2026-03-18: 2027-01-12; 2026-03-25: 2027-01-19; 2026-03-30: 2027-01-24; 2026-04-09: 2027-02-03 |  | 299 | 95 |  |  | incl. above |  |  |  | 300 | 2027-01-24 | 204 |  | 2027-01-24 | 204 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
46 |  | Gym Equipments | Jayantha | 2025-12-25: 2026-10-21; 2026-01-01: 2026-10-28; 2026-01-07: 2026-11-03; 2026-01-10: 2026-11-06; 2026-02-09: 2026-12-06; 2026-02-19: 2026-12-16; 2026-03-11: 2027-01-05; 2026-03-18: 2027-01-12; 2026-03-25: 2027-01-19; 2026-03-30: 2027-01-24; 2026-04-09: 2027-02-03 |  | 299 | 95 |  |  | incl. above |  |  |  | 300 | 2027-01-24 | 204 |  | 2027-01-24 | 204 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
47 |  | Loose Furniture | Jayantha | 2025-12-25: 2026-10-21; 2026-01-01: 2026-10-28; 2026-01-07: 2026-11-03; 2026-01-10: 2026-11-06; 2026-02-09: 2026-12-06; 2026-02-19: 2026-12-16; 2026-03-11: 2027-01-05; 2026-03-18: 2027-01-12; 2026-03-25: 2027-01-19; 2026-03-30: 2027-01-24; 2026-04-09: 2027-02-03 |  | 299 | 95 |  |  | 2125500 |  |  |  | 300 | 2027-01-24 | 204 |  | 2027-01-24 | 204 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
48 |  | Artwork | Jayantha | 2025-12-25: 2026-10-21; 2026-01-01: 2026-10-28; 2026-01-07: 2026-11-03; 2026-01-10: 2026-11-06; 2026-02-09: 2026-12-06; 2026-02-19: 2026-12-16; 2026-03-11: 2027-01-05; 2026-03-18: 2027-01-12; 2026-03-25: 2027-01-19; 2026-03-30: 2027-01-24; 2026-04-09: 2027-02-03 |  | 299 | 95 |  |  | incl. above |  |  |  | 300 | 2027-01-24 | 204 |  | 2027-01-24 | 204 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
49 |  | Curtains | Reyoon | 2025-12-25: 2026-10-21; 2026-01-01: 2026-10-28; 2026-01-07: 2026-11-03; 2026-01-10: 2026-11-06; 2026-02-09: 2026-12-06; 2026-02-19: 2026-12-16; 2026-03-11: 2027-01-05; 2026-03-18: 2027-01-12; 2026-03-25: 2027-01-19; 2026-03-30: 2027-01-24; 2026-04-09: 2027-02-03 |  | 299 | 95 |  |  | incl. above |  |  |  | 300 | 2027-01-24 | 204 |  | 2027-01-24 | 204 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
50 |  | Signages and Wayfindings | Jayantha | 2025-12-25: 2026-10-21; 2026-01-01: 2026-10-28; 2026-01-07: 2026-11-03; 2026-01-10: 2026-11-06; 2026-02-09: 2026-12-06; 2026-02-19: 2026-12-16; 2026-03-11: 2027-01-05; 2026-03-18: 2027-01-12; 2026-03-25: 2027-01-19; 2026-03-30: 2027-01-24; 2026-04-09: 2027-02-03 |  | 299 | 95 |  |  | incl. above |  |  |  | 300 | 2027-01-24 | 204 |  | 2027-01-24 | 204 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
51 |  | Carpet Flooring | Reyoon | 2025-12-25: 2026-10-21; 2026-01-01: 2026-10-28; 2026-01-07: 2026-11-03; 2026-01-10: 2026-11-06; 2026-02-09: 2026-12-06; 2026-02-19: 2026-12-16; 2026-03-11: 2027-01-05; 2026-03-18: 2027-01-12; 2026-03-25: 2027-01-19; 2026-03-30: 2027-01-24; 2026-04-09: 2027-02-03 |  | 299 | 95 |  |  | incl. above |  |  |  | 300 | 2027-01-24 | 204 |  | 2027-01-24 | 204 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
52 |  | Mirrors | Prabhu | 2025-12-25: 2026-10-21; 2026-01-01: 2026-10-28; 2026-01-07: 2026-11-03; 2026-01-10: 2026-11-06; 2026-02-09: 2026-12-06; 2026-02-19: 2026-12-16; 2026-03-11: 2027-01-05; 2026-03-18: 2027-01-12; 2026-03-25: 2027-01-19; 2026-03-30: 2027-01-24; 2026-04-09: 2027-02-03 |  | 299 | 95 |  |  | incl. above |  |  |  | 300 | 2027-01-24 | 204 |  | 2027-01-24 | 204 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | Total | [25 empty] | 0 | 0 | 630893318 | 200928000 | 26102822
|  | Dutco | [25 empty] | 2026-03-31
| 1 | MEP - | [25 empty] | Arco with selected
| 2 | Elevator | [25 empty] | Pit depth given, Kone prefered
3
4
5
6
7

## Mamsha Palm
Project |  | Components | Category | LDC | PMC | Supervision | Contractor | BUA (m2) | GFA (m2) | Award Date | Commencement |  |  | Value Summary |  |  |  |  | Actual to date Impact on Value | [5 empty] | Packages Summary |  |  | Delay Summary |  | nos. | Max delay
[14 empty] | Project Lump Sum Value in LAFO |  |  |  |  | Awards up to date (incl. OHP) |  |  | 0 | 0% |  | Total Packages (nos) |  | 37 | Current delayed remaining packages |  | 1 | -1
Mamsha Palm |  | 1 Building 2B+G+6 | Resi Building |  |  | Dewan | Dutco | 23227 | 11722 | 2025-01-31 | 2026-03-31 |  |  | PS - Lump Sum Value in LAFO |  |  | 0 |  | Remaining to award |  |  | 98594000 | 100% |  | Finalized Packages (nos) |  | 0 | Forecast Delay to Contract |  | 2 | -81
[14 empty] | PS - Contract Value (incl. OHP) |  |  | 98594000 |  | Finalized Packages Savings against Lump Sum |  |  | 0 | #DIV/0! |  | Days Since Award (days) |  | 424 | Forecast Delay to Baseline |  | 2 | -81
[19 empty] | Finalized Packages Savings against contract PS |  |  | 0 | #DIV/0!
Data Date |  | 2026-03-31 | [31 empty] | Tentative
SN | Pkg No. | Package | Package Manager | 15 |  | 7 |  | 6 |  | 3 |  | 30 |  | 10 |  | 20 |  | 7 |  | 7 |  | 5 |  | 10 |  | Variance from Today | PS Procurement Duration | PS - Lump Sum Value in LAFO | PS - Contract Value (excl. OHP) | PS - Contract Value (incl. OHP) | PS - Award Value (incl. OHP) | Saving (against PS in contract) | Awarded Sub-contractor | Cont Dur | Contract Date Nomination | Var | Float | Late Date in Programme | Var | Actual / Forecast Award | Current Stage (from 1-11) | 1. Tender Docs & BOQ | 2. Bidder List | 3. EOI | 4. Tender Float | 5. Initial submission | 6. Tech & Com Review | 7. BAFO | 8. Tech & Com Review | 9. Award Rec. Approval | 10. Issued to Contractor | 11. Subcontract signed
|  |  |  | 1. Tender Docs & BOQ |  | 2. Bidder List |  | 3. EOI |  | 4. Tender Float |  | 5. Initial submission |  | 6. Tech & Com Review |  | 7. BAFO |  | 8. Tech & Com Review |  | 9. Award Rec. Approval |  | 10. Issued to Contractor |  | 11. Subcontract Agreement signed
|  |  |  | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast
PC Rate Items
1 |  | Sanitary items | Ifthiqar | 2026-04-24 |  | 2026-05-01 |  | 2026-05-07 |  | 2026-05-10 |  | 2026-06-09 |  | 2026-06-19 |  | 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-08-07 |  | 119 | 95 |  |  | 1889000 |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2 |  | Light fittings | Ifthiqar | 2026-04-24 |  | 2026-05-01 |  | 2026-05-07 |  | 2026-05-10 |  | 2026-06-09 |  | 2026-06-19 |  | 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-08-07 |  | 119 | 95 |  |  | 5748000 |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
MEP Works
3 |  | MEP Works | Manoj | 2025-12-25 | 2025-12-25 | 2026-01-01 | 2026-01-01 | 2026-01-07 | 2026-01-07 | 2026-01-10 | 2026-01-10 | 2026-02-09 | 2026-02-09 | 2026-02-19 | 2026-02-19 | 2026-03-11 |  | 2026-03-18 |  | 2026-03-25 |  | 2026-03-30 |  | 2026-04-09 |  | -1 | 95 |  |  | 34000000 |  |  |  | 0 | 2026-03-30 | -40 |  | 2026-03-30 | -40 | 2026-05-09 | 7. BAFO | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
Aluminum & Metal Works
4 |  | Metal Doors | Prabhu | 2025-12-25: 2026-04-04; 2026-01-01: 2026-04-11; 2026-01-07: 2026-04-17; 2026-01-10: 2026-04-20; 2026-02-09: 2026-05-20; 2026-02-19: 2026-05-30; 2026-03-11: 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-08 |  | 2026-07-18 |  | 99 | 95 |  |  | incl. above |  |  |  | 100 | 2026-07-08 | 4 |  | 2026-07-08 | 4 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
5 |  | Aluminium Doors,Glass Doors, Curtain Walls, Glass Balustrade, External Louver | Prabhu | 2025-12-25: 2026-04-04; 2026-01-01: 2026-04-11; 2026-01-07: 2026-04-17; 2026-01-10: 2026-04-20; 2026-02-09: 2026-05-20; 2026-02-19: 2026-05-30; 2026-03-11: 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-08 |  | 2026-07-18 |  | 99 | 95 |  |  | incl. above |  |  |  | 100 | 2026-07-08 | 4 |  | 2026-07-08 | 4 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
6 |  | Structural Steel | Prabhu | 2025-12-25: 2026-04-04; 2026-01-01: 2026-04-11; 2026-01-07: 2026-04-17; 2026-01-10: 2026-04-20; 2026-02-09: 2026-05-20; 2026-02-19: 2026-05-30; 2026-03-11: 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-08 |  | 2026-07-18 |  | 99 | 95 |  |  | 2000000 |  |  |  | 100 | 2026-07-08 | 4 |  | 2026-07-08 | 4 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
7 |  | Non Structural Steel | Prabhu | 2025-12-25: 2026-04-04; 2026-01-01: 2026-04-11; 2026-01-07: 2026-04-17; 2026-01-10: 2026-04-20; 2026-02-09: 2026-05-20; 2026-02-19: 2026-05-30; 2026-03-11: 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-08 |  | 2026-07-18 |  | 99 | 95 |  |  | incl. above |  |  |  | 100 | 2026-07-08 | 4 |  | 2026-07-08 | 4 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Joinery and Carpentry
8 |  | Timber Doors | Suhail | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-08-07 |  | 119 | 95 |  |  | 12500000 |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
9 |  | HPL Doors | Prabhu | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-08-07 |  | 119 | 95 |  |  | incl. above |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
10 |  | Ironmongery | Prabhu | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-08-07 |  | 119 | 95 |  |  | incl. above |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Finishes
11 |  | Attic Stock for all PC rate items | Reyoon | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-08-07 |  | 119 | 95 |  |  | 49000 |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
12 |  | Tiles - Floor, Walls, Skirting, Threshold | Reyoon | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-08-07 |  | 119 | 95 |  |  | 19000000 |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
13 |  | Metal Trims | Reyoon | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-08-07 |  | 119 | 95 |  |  | incl. above |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
14 |  | Suspended ceiling | Reyoon | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-08-07 |  | 119 | 95 |  |  | incl. above |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
15 |  | Paint - Internal and External | Reyoon | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-08-07 |  | 119 | 95 |  |  | incl. above |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
16 |  | GRC Cladding | Prabhu | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-08-07 |  | 119 | 95 |  |  | incl. above |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
17 |  | Aluminium Louver | Prabhu | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-08-07 |  | 119 | 95 |  |  | incl. above |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
18 |  | Wallpaper | Reyoon | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-08-07 |  | 119 | 95 |  |  | incl. above |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
19 |  | Signages & Way Findings | Jayantha | 2025-12-25: 2026-04-24; 2026-01-01: 2026-05-01; 2026-01-07: 2026-05-07; 2026-01-10: 2026-05-10; 2026-02-09: 2026-06-09; 2026-02-19: 2026-06-19; 2026-03-11: 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-08-07 |  | 119 | 95 |  |  | incl. above |  |  |  | 120 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
External Works
20 |  | Steam, Suana and Plunge Pool | Jayantha | 2025-12-25: 2026-05-24; 2026-01-01: 2026-05-31; 2026-01-07: 2026-06-06; 2026-01-10: 2026-06-09; 2026-02-09: 2026-07-09; 2026-02-19: 2026-07-19; 2026-03-11: 2026-08-08 |  | 2026-08-15 |  | 2026-08-22 |  | 2026-08-27 |  | 2026-09-06 |  | 149 | 95 |  |  | 7000000 |  |  |  | 150 | 2026-08-27 | 54 |  | 2026-08-27 | 54 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
21 |  | BMU | Prabhu | 2025-12-25: 2026-05-24; 2026-01-01: 2026-05-31; 2026-01-07: 2026-06-06; 2026-01-10: 2026-06-09; 2026-02-09: 2026-07-09; 2026-02-19: 2026-07-19; 2026-03-11: 2026-08-08 |  | 2026-08-15 |  | 2026-08-22 |  | 2026-08-27 |  | 2026-09-06 |  | 149 | 95 |  |  | incl. above |  |  |  | 150 | 2026-08-27 | 54 |  | 2026-08-27 | 54 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
22 |  | Hardscape & Softscape | Suhail | 2025-12-25: 2026-05-24; 2026-01-01: 2026-05-31; 2026-01-07: 2026-06-06; 2026-01-10: 2026-06-09; 2026-02-09: 2026-07-09; 2026-02-19: 2026-07-19; 2026-03-11: 2026-08-08 |  | 2026-08-15 |  | 2026-08-22 |  | 2026-08-27 |  | 2026-09-06 |  | 149 | 95 |  |  | 7000000 |  |  |  | 150 | 2026-08-27 | 54 |  | 2026-08-27 | 54 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
23 |  | Balustrades and Handrails | Prabhu | 2025-12-25: 2026-05-24; 2026-01-01: 2026-05-31; 2026-01-07: 2026-06-06; 2026-01-10: 2026-06-09; 2026-02-09: 2026-07-09; 2026-02-19: 2026-07-19; 2026-03-11: 2026-08-08 |  | 2026-08-15 |  | 2026-08-22 |  | 2026-08-27 |  | 2026-09-06 |  | 149 | 95 |  |  | incl. above |  |  |  | 150 | 2026-08-27 | 54 |  | 2026-08-27 | 54 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
24 |  | Swimming Pool | Suhail | 2025-12-25: 2026-05-24; 2026-01-01: 2026-05-31; 2026-01-07: 2026-06-06; 2026-01-10: 2026-06-09; 2026-02-09: 2026-07-09; 2026-02-19: 2026-07-19; 2026-03-11: 2026-08-08 |  | 2026-08-15 |  | 2026-08-22 |  | 2026-08-27 |  | 2026-09-06 |  | 149 | 95 |  |  | incl. above |  |  |  | 150 | 2026-08-27 | 54 |  | 2026-08-27 | 54 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
25 |  | Irrigation System | Manoj | 2025-12-25: 2026-05-24; 2026-01-01: 2026-05-31; 2026-01-07: 2026-06-06; 2026-01-10: 2026-06-09; 2026-02-09: 2026-07-09; 2026-02-19: 2026-07-19; 2026-03-11: 2026-08-08 |  | 2026-08-15 |  | 2026-08-22 |  | 2026-08-27 |  | 2026-09-06 |  | 149 | 95 |  |  | incl. above |  |  |  | 150 | 2026-08-27 | 54 |  | 2026-08-27 | 54 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
26 |  | Landscape Furniture | Jayantha | 2025-12-25: 2026-05-24; 2026-01-01: 2026-05-31; 2026-01-07: 2026-06-06; 2026-01-10: 2026-06-09; 2026-02-09: 2026-07-09; 2026-02-19: 2026-07-19; 2026-03-11: 2026-08-08 |  | 2026-08-15 |  | 2026-08-22 |  | 2026-08-27 |  | 2026-09-06 |  | 149 | 95 |  |  | incl. above |  |  |  | 150 | 2026-08-27 | 54 |  | 2026-08-27 | 54 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
27 |  | Signage and Wayfindings | Jayantha | 2025-12-25: 2026-05-24; 2026-01-01: 2026-05-31; 2026-01-07: 2026-06-06; 2026-01-10: 2026-06-09; 2026-02-09: 2026-07-09; 2026-02-19: 2026-07-19; 2026-03-11: 2026-08-08 |  | 2026-08-15 |  | 2026-08-22 |  | 2026-08-27 |  | 2026-09-06 |  | 149 | 95 |  |  | incl. above |  |  |  | 150 | 2026-08-27 | 54 |  | 2026-08-27 | 54 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
28 |  | Light Fittings | Manoj | 2025-12-25: 2026-05-24; 2026-01-01: 2026-05-31; 2026-01-07: 2026-06-06; 2026-01-10: 2026-06-09; 2026-02-09: 2026-07-09; 2026-02-19: 2026-07-19; 2026-03-11: 2026-08-08 |  | 2026-08-15 |  | 2026-08-22 |  | 2026-08-27 |  | 2026-09-06 |  | 149 | 95 |  |  | incl. above |  |  |  | 150 | 2026-08-27 | 54 |  | 2026-08-27 | 54 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
29 |  | Security system | Manoj | 2025-12-25: 2026-05-24; 2026-01-01: 2026-05-31; 2026-01-07: 2026-06-06; 2026-01-10: 2026-06-09; 2026-02-09: 2026-07-09; 2026-02-19: 2026-07-19; 2026-03-11: 2026-08-08 |  | 2026-08-15 |  | 2026-08-22 |  | 2026-08-27 |  | 2026-09-06 |  | 149 | 95 |  |  | incl. above |  |  |  | 150 | 2026-08-27 | 54 |  | 2026-08-27 | 54 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Equipments & Accessories
30 |  | Conveying Systems | Manoj | 2025-12-25: 2026-01-09; 2026-01-01: 2026-01-16; 2026-01-07: 2026-01-22; 2026-01-10: 2026-01-25; 2026-02-09: 2026-02-24; 2026-02-19: 2026-03-06; 2026-03-11: 2026-03-26 |  | 2026-04-02 |  | 2026-04-09 |  | 2026-04-14 |  | 2026-04-24 |  | 14 | 95 |  |  | 800000 |  |  |  | 15 | 2026-04-14 | -81 |  | 2026-04-14 | -81 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
31 |  | Accessories | Jayantha | 2025-12-25: 2026-05-24; 2026-01-01: 2026-05-31; 2026-01-07: 2026-06-06; 2026-01-10: 2026-06-09; 2026-02-09: 2026-07-09; 2026-02-19: 2026-07-19; 2026-03-11: 2026-08-08 |  | 2026-08-15 |  | 2026-08-22 |  | 2026-08-27 |  | 2026-09-06 |  | 149 | 95 |  |  | 6500000 |  |  |  | 150 | 2026-08-27 | 54 |  | 2026-08-27 | 54 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
32 |  | Supply and installation Gym Equipments | Jayantha | 2025-12-25: 2026-06-23; 2026-01-01: 2026-06-30; 2026-01-07: 2026-07-06; 2026-01-10: 2026-07-09; 2026-02-09: 2026-08-08; 2026-02-19: 2026-08-18; 2026-03-11: 2026-09-07 |  | 2026-09-14 |  | 2026-09-21 |  | 2026-09-26 |  | 2026-10-06 |  | 179 | 95 |  |  | 170000 |  |  |  | 180 | 2026-09-26 | 84 |  | 2026-09-26 | 84 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
33 |  | Supply and installation Loose Furniture | Jayantha | 2025-12-25: 2026-06-23; 2026-01-01: 2026-06-30; 2026-01-07: 2026-07-06; 2026-01-10: 2026-07-09; 2026-02-09: 2026-08-08; 2026-02-19: 2026-08-18; 2026-03-11: 2026-09-07 |  | 2026-09-14 |  | 2026-09-21 |  | 2026-09-26 |  | 2026-10-06 |  | 179 | 95 |  |  | 177000 |  |  |  | 180 | 2026-09-26 | 84 |  | 2026-09-26 | 84 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
34 |  | Supply and installation Kids Play Equipment | Jayantha | 2025-12-25: 2026-06-23; 2026-01-01: 2026-06-30; 2026-01-07: 2026-07-06; 2026-01-10: 2026-07-09; 2026-02-09: 2026-08-08; 2026-02-19: 2026-08-18; 2026-03-11: 2026-09-07 |  | 2026-09-14 |  | 2026-09-21 |  | 2026-09-26 |  | 2026-10-06 |  | 179 | 95 |  |  | 91000 |  |  |  | 180 | 2026-09-26 | 84 |  | 2026-09-26 | 84 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
35 |  | Supply and installation curtains and curtain tracks | Jayantha | 2025-12-25: 2026-06-23; 2026-01-01: 2026-06-30; 2026-01-07: 2026-07-06; 2026-01-10: 2026-07-09; 2026-02-09: 2026-08-08; 2026-02-19: 2026-08-18; 2026-03-11: 2026-09-07 |  | 2026-09-14 |  | 2026-09-21 |  | 2026-09-26 |  | 2026-10-06 |  | 179 | 95 |  |  | 142000 |  |  |  | 180 | 2026-09-26 | 84 |  | 2026-09-26 | 84 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
36 |  | Equipments | Prabhu | 2025-12-25: 2026-10-21; 2026-01-01: 2026-10-28; 2026-01-07: 2026-11-03; 2026-01-10: 2026-11-06; 2026-02-09: 2026-12-06; 2026-02-19: 2026-12-16; 2026-03-11: 2027-01-05 |  | 2027-01-12 |  | 2027-01-19 |  | 2027-01-24 |  | 2027-02-03 |  | 299 | 95 |  |  | 800000 |  |  |  | 300 | 2027-01-24 | 204 |  | 2027-01-24 | 204 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
37 |  | Supply and installation Kitchen Equipments | Manoj | 2025-12-25: 2026-10-21; 2026-01-01: 2026-10-28; 2026-01-07: 2026-11-03; 2026-01-10: 2026-11-06; 2026-02-09: 2026-12-06; 2026-02-19: 2026-12-16; 2026-03-11: 2027-01-05 |  | 2027-01-12 |  | 2027-01-19 |  | 2027-01-24 |  | 2027-02-03 |  | 299 | 95 |  |  | 728000 |  |  |  | 300 | 2027-01-24 | 204 |  | 2027-01-24 | 204 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | Total | [25 empty] | 0 | 0 | 98594000 | 0 | 0
Dutco
2026-04-14
| 1 | MEP works | [25 empty] | Dutco PK Gulf will be awarded
2
3
4
5
6
7
8
9
Formulas:
LDC = [Supervision]-H7
Supervision = [BUA (m2)]-J7
BUA (m2) = [Award Date]-L7
Award Date = [Plan]-N7
Plan = [Value Summary]-P7
Plan = [Plan]-T7
Value Summary = [Plan]-R7

## Faya (SB45)
Project |  | Components | Category | LDC | PMC | Supervision | Contractor | BUA (m2) | GFA (m2) | Award Date | Commencement |  |  | Value Summary |  |  |  |  | Actual to date Impact on Value | [5 empty] | Packages Summary |  |  | Delay Summary |  | nos. | Max delay
[14 empty] | Project Lump Sum Value in LAFO |  |  |  |  | Awards up to date (incl. OHP) |  |  | 0 | 0% |  | Total Packages (nos) |  | 20 | Current delayed remaining packages |  | 0 | 45
Faya Saadiyat SB 45 & SB456 |  | SB45-19 Villas, 2 Mansions, Infra & Roads SB46-4 Villas, Infra & Roads | Villas & Infra | Dar | Hill | Dar | Al Kharafi | 49972 | 42400 | 2026-03-01 | 2026-04-16 |  |  | PS - Lump Sum Value in LAFO |  |  | 0 |  | Remaining to award |  |  | 380310593.3 | 100% |  | Finalized Packages (nos) |  | 0 | Forecast Delay to Contract |  | 3 | -50
[14 empty] | PS - Contract Value (incl. OHP) |  |  | 380310593.3 |  | Finalized Packages Savings against Lump Sum |  |  | 0 | #DIV/0! |  | Days Since Award (days) |  | 30 | Forecast Delay to Baseline |  | 3 | -50
[19 empty] | Finalized Packages Savings against contract PS |  |  | 0 | #DIV/0!
Data Date |  | 2026-03-31 | [31 empty] | Tentative
SN | Pkg No. | Package | Package Manager | 15 |  | 7 |  | 6 |  | 3 |  | 30 |  | 10 |  | 20 |  | 7 |  | 7 |  | 5 |  | 10 |  | Variance from Today | PS Procurement Duration | PS - Lump Sum Value in LAFO | PS - Contract Value (excl. OHP) | PS - Contract Value (incl. OHP) | PS - Award Value (incl. OHP) | Saving (against PS in contract) | Awarded Sub-contractor | Cont Dur | Contract Date Nomination | Var | Float | Late Date in Programme | Var | Actual / Forecast Award | Current Stage (from 1-11) | 1. Tender Docs & BOQ | 2. Bidder List | 3. EOI | 4. Tender Float | 5. Initial submission | 6. Tech & Com Review | 7. BAFO | 8. Tech & Com Review | 9. Award Rec. Approval | 10. Issued to Contractor | 11. Subcontract signed
|  |  |  | 1. Tender Docs & BOQ |  | 2. Bidder List |  | 3. EOI |  | 4. Tender Float |  | 5. Initial submission |  | 6. Tech & Com Review |  | 7. BAFO |  | 8. Tech & Com Review |  | 9. Award Rec. Approval |  | 10. Issued to Contractor |  | 11. Subcontract Agreement signed
|  |  |  | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast
Structural and Civil Works
1 |  | Infrastructure works |  | 2026-03-11 |  | 2026-03-18 |  | 2026-03-24 |  | 2026-03-27 |  | 2026-04-26 |  | 2026-05-06 |  | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-06-14 |  | 2026-06-24 |  | 75 | 95 |  |  | 26400000 |  |  |  | 60 | 2026-06-14 | -20 |  | 2026-06-14 | -20 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2 |  | Boundary Wall |  | 2026-03-11 |  | 2026-03-18 |  | 2026-03-24 |  | 2026-03-27 |  | 2026-04-26 |  | 2026-05-06 |  | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-06-14 |  | 2026-06-24 |  | 75 | 95 |  |  | incl. Landscape PS |  |  |  | 60 | 2026-06-14 | -20 |  | 2026-06-14 | -20 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3 |  | Ancillary building |  | 2026-04-10 |  | 2026-04-17 |  | 2026-04-23 |  | 2026-04-26 |  | 2026-05-26 |  | 2026-06-05 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-07-14 |  | 2026-07-24 |  | 105 | 95 |  |  | 22000000 |  |  |  | 90 | 2026-07-14 | 10 |  | 2026-07-14 | 10 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4 |  | Extrnal work for villas except Landscaping works |  | 2026-04-10 |  | 2026-04-17 |  | 2026-04-23 |  | 2026-04-26 |  | 2026-05-26 |  | 2026-06-05 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-07-14 |  | 2026-07-24 |  | 105 | 95 |  |  | incl. Ancillary Building PS |  |  |  | 90 | 2026-07-14 | 10 |  | 2026-07-14 | 10 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
5 |  | Golf Tunnel |  | 2026-04-10 |  | 2026-04-17 |  | 2026-04-23 |  | 2026-04-26 |  | 2026-05-26 |  | 2026-06-05 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-07-14 |  | 2026-07-24 |  | 105 | 95 |  |  | incl. Ancillary Building PS |  |  |  | 90 | 2026-07-14 | 10 |  | 2026-07-14 | 10 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
6 |  | Dewatering | Jayantha | 2026-04-10 |  | 2026-04-17 |  | 2026-04-23 |  | 2026-04-26 |  | 2026-05-26 |  | 2026-06-05 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-07-14 |  | 2026-07-24 |  | 105 | 95 |  |  | 2750000 |  |  |  | 90 | 2026-07-14 | 10 |  | 2026-07-14 | 10 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
PC Rate Items
7 |  | Sanitary items | Manoj | 2026-05-10 |  | 2026-05-17 |  | 2026-05-23 |  | 2026-05-26 |  | 2026-06-25 |  | 2026-07-05 |  | 2026-07-25 |  | 2026-08-01 |  | 2026-08-08 |  | 2026-08-13 |  | 2026-08-23 |  | 135 | 95 |  |  | 19800000 |  |  |  | 120 | 2026-08-13 | 40 |  | 2026-08-13 | 40 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
8 |  | Light fittings | Manoj | 2026-05-10 |  | 2026-05-17 |  | 2026-05-23 |  | 2026-05-26 |  | 2026-06-25 |  | 2026-07-05 |  | 2026-07-25 |  | 2026-08-01 |  | 2026-08-08 |  | 2026-08-13 |  | 2026-08-23 |  | 135 | 95 |  |  | incl. above |  |  |  | 120 | 2026-08-13 | 40 |  | 2026-08-13 | 40 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Aluminum & Metal Works
9 |  | Metal works | Prabhu | 2026-04-10 |  | 2026-04-17 |  | 2026-04-23 |  | 2026-04-26 |  | 2026-05-26 |  | 2026-06-05 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-07-14 |  | 2026-07-24 |  | 105 | 95 |  |  | 17600000 |  |  |  | 90 | 2026-07-14 | 10 |  | 2026-07-14 | 10 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
10 |  | Doors and Windows | Prabhu | 2026-04-10 |  | 2026-04-17 |  | 2026-04-23 |  | 2026-04-26 |  | 2026-05-26 |  | 2026-06-05 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-07-14 |  | 2026-07-24 |  | 105 | 95 |  |  | 46200000 |  |  |  | 90 | 2026-07-14 | 10 |  | 2026-07-14 | 10 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
11 |  | UHPC Cladding | Prabhu | 2026-04-10 |  | 2026-04-17 |  | 2026-04-23 |  | 2026-04-26 |  | 2026-05-26 |  | 2026-06-05 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-07-14 |  | 2026-07-24 |  | 105 | 95 |  |  | 55000000 |  |  |  | 90 | 2026-07-14 | 10 |  | 2026-07-14 | 10 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Joinery and Carpentry
12 |  | Carpentary and Woodworks | Suhail | 2026-05-10 |  | 2026-05-17 |  | 2026-05-23 |  | 2026-05-26 |  | 2026-06-25 |  | 2026-07-05 |  | 2026-07-25 |  | 2026-08-01 |  | 2026-08-08 |  | 2026-08-13 |  | 2026-08-23 |  | 135 | 95 |  |  | 35200000 |  |  |  | 120 | 2026-08-13 | 40 |  | 2026-08-13 | 40 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Finishes
13 |  | Finishes | Reyoon | 2026-04-10 |  | 2026-04-17 |  | 2026-04-23 |  | 2026-04-26 |  | 2026-05-26 |  | 2026-06-05 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-07-14 |  | 2026-07-24 |  | 105 | 95 |  |  | 70660593.3 |  |  |  | 90 | 2026-07-14 | 10 |  | 2026-07-14 | 10 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
14 |  | Thermal and Moisture Protection | Reyoon | 2026-04-10 |  | 2026-04-17 |  | 2026-04-23 |  | 2026-04-26 |  | 2026-05-26 |  | 2026-06-05 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-07-14 |  | 2026-07-24 |  | 105 | 95 |  |  | 39600000 |  |  |  | 90 | 2026-07-14 | 10 |  | 2026-07-14 | 10 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
External Works
15 |  | Landscaping | Suhail | 2026-04-10 |  | 2026-04-17 |  | 2026-04-23 |  | 2026-04-26 |  | 2026-05-26 |  | 2026-06-05 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-07-14 |  | 2026-07-24 |  | 105 | 95 |  |  | 26400000 |  |  |  | 90 | 2026-07-14 | 10 |  | 2026-07-14 | 10 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Equipments & Accessories
16 |  | Vertical Transportation | Manoj | 2026-02-09 |  | 2026-02-16 |  | 2026-02-22 |  | 2026-02-25 |  | 2026-03-27 |  | 2026-04-06 |  | 2026-04-26 |  | 2026-05-03 |  | 2026-05-10 |  | 2026-05-15 |  | 2026-05-25 |  | 45 | 95 |  |  | 5500000 |  |  |  | 30 | 2026-05-15 | -50 |  | 2026-05-15 | -50 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
17 |  | Accessories | Prabhu | 2026-05-10 |  | 2026-05-17 |  | 2026-05-23 |  | 2026-05-26 |  | 2026-06-25 |  | 2026-07-05 |  | 2026-07-25 |  | 2026-08-01 |  | 2026-08-08 |  | 2026-08-13 |  | 2026-08-23 |  | 135 | 95 |  |  | 5500000 |  |  |  | 120 | 2026-08-13 | 40 |  | 2026-08-13 | 40 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
18 |  | Furniture | Jayantha | 2026-05-10 |  | 2026-05-17 |  | 2026-05-23 |  | 2026-05-26 |  | 2026-06-25 |  | 2026-07-05 |  | 2026-07-25 |  | 2026-08-01 |  | 2026-08-08 |  | 2026-08-13 |  | 2026-08-23 |  | 135 | 95 |  |  | incl. Woodwork PS |  |  |  | 120 | 2026-08-13 | 40 |  | 2026-08-13 | 40 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
19 |  | Equipment | Jayantha | 2026-05-10 |  | 2026-05-17 |  | 2026-05-23 |  | 2026-05-26 |  | 2026-06-25 |  | 2026-07-05 |  | 2026-07-25 |  | 2026-08-01 |  | 2026-08-08 |  | 2026-08-13 |  | 2026-08-23 |  | 135 | 95 |  |  | 6600000 |  |  |  | 120 | 2026-08-13 | 40 |  | 2026-08-13 | 40 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
20 |  | Kids play equipment & Turkish Bath | Jayantha | 2026-05-10 |  | 2026-05-17 |  | 2026-05-23 |  | 2026-05-26 |  | 2026-06-25 |  | 2026-07-05 |  | 2026-07-25 |  | 2026-08-01 |  | 2026-08-08 |  | 2026-08-13 |  | 2026-08-23 |  | 135 | 95 |  |  | 1100000 |  |  |  | 120 | 2026-08-13 | 40 |  | 2026-08-13 | 40 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | Total | [25 empty] | 0 | 0 | 380310593.3 | 0 | 0
Formulas:
LDC = [Supervision]-H7
Supervision = [BUA (m2)]-J7
BUA (m2) = [Award Date]-L7
Award Date = [Plan]-N7
Plan = [Value Summary]-P7
Plan = [Plan]-T7
Value Summary = [Plan]-R7

## Mamsha Gardens
Project |  | Components | Category | LDC | PMC | Supervision | Contractor | BUA (m2) | GFA (m2) | Award Date | Commencement |  |  | Value Summary |  |  |  |  | Actual to date Impact on Value | [5 empty] | Packages Summary |  |  | Delay Summary |  | nos. | Max delay
[14 empty] | Project Lump Sum Value in LAFO |  |  |  |  | Awards up to date (incl. OHP) |  |  | 0 | #DIV/0! |  | Total Packages (nos) |  | 39 | Current delayed remaining packages |  | 0 | 19
Mamsha Gardens |  | 7 Buildings 2B+G+7 | Resi Buildings | AECOM | Hill | AECOM | Fibrex | 255,160 m2 | 122,271 m2 | 2025-12-31 | 2026-04-20 |  |  | PS - Lump Sum Value in LAFO |  |  | 0 |  | Remaining to award |  |  | 0 | #DIV/0! |  | Finalized Packages (nos) |  | 0 | Forecast Delay to Contract |  | 39 | -76
[14 empty] | PS - Contract Value (incl. OHP) |  |  | 0 |  | Finalized Packages Savings against Lump Sum |  |  | 0 | #DIV/0! |  | Days Since Award (days) |  | 90 | Forecast Delay to Baseline |  | 39 | -76
[19 empty] | Finalized Packages Savings against contract PS |  |  | 0 | #DIV/0!
Data Date |  | 2026-03-31 | [31 empty] | Tentative
SN | Pkg No. | Package | Package Manager | 15 |  | 7 |  | 6 |  | 3 |  | 30 |  | 10 |  | 20 |  | 7 |  | 7 |  | 5 |  | 10 |  | Variance from Today | PS Procurement Duration | PS - Lump Sum Value in LAFO | PS - Contract Value (excl. OHP) | PS - Contract Value (incl. OHP) | PS - Award Value (incl. OHP) | Saving (against PS in contract) | Awarded Sub-contractor | Cont Dur | Contract Date Nomination | Var | Float | Late Date in Programme | Var | Actual / Forecast Award | Current Stage (from 1-11) | 1. Tender Docs & BOQ | 2. Bidder List | 3. EOI | 4. Tender Float | 5. Initial submission | 6. Tech & Com Review | 7. BAFO | 8. Tech & Com Review | 9. Award Rec. Approval | 10. Issued to Contractor | 11. Subcontract signed
|  |  |  | 1. Tender Docs & BOQ |  | 2. Bidder List |  | 3. EOI |  | 4. Tender Float |  | 5. Initial submission |  | 6. Tech & Com Review |  | 7. BAFO |  | 8. Tech & Com Review |  | 9. Award Rec. Approval |  | 10. Issued to Contractor |  | 11. Subcontract Agreement signed
|  |  |  | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast
PC Rate Items
1 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
MEP Works
Aluminum & Metal Works
4 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
5 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
6 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
7 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
8 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Joinery and Carpentry
9 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
10 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
11 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
12 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Finishes
13 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
14 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
15 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
16 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
17 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
18 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
19 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
20 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
21 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
22 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
23 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
24 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
25 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
External Works
26 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
27 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Equipments & Accessories
28 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
29 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
30 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
31 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
32 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
33 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
34 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
35 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
36 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
37 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
38 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
39 |  |  |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-03-01 |  | 2026-03-11 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-19 |  | 2026-04-29 |  | 19 | 95 | [7 empty] | 2026-04-19 | -76 |  | 2026-04-19 | -76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | Total | [25 empty] | 0 | 0 | 0 | 0 | 0
Formulas:
LDC = [Supervision]-H7
Supervision = [BUA (m2)]-J7
BUA (m2) = [Award Date]-L7
Award Date = [Plan]-N7
Plan = [Value Summary]-P7
Plan = [Plan]-T7
Value Summary = [Plan]-R7

## Sama Yas
Project |  | Components | Category | LDC | PMC | Supervision | Contractor | BUA (m2) | GFA (m2) | Award Date | Commencement |  |  | Value Summary |  |  |  |  | Actual to date Impact on Value | [5 empty] | Packages Summary |  |  | Delay Summary |  | nos. | Max delay
[14 empty] | Project Lump Sum Value in LAFO |  |  |  |  | Awards up to date (incl. OHP) |  |  | 6077673 | 9.118% |  | Total Packages (nos) |  | 13 | Current delayed remaining packages |  | 12 | -94
Sama Yas |  | 3 Buildings 1B+G+7 | Resi Buildings | Mott Macdonald | Hill | Mott Macdonald | MEC | 65,666 m2 | 51,999 m2 | 2025-06-01 | 2025-07-01 |  |  | PS - Lump Sum Value in LAFO |  |  | 91984309 |  | Remaining to award |  |  | 60575000 | 90.88% |  | Finalized Packages (nos) |  | 1 | Forecast Delay to Contract |  | 13 | -159
[14 empty] | PS - Contract Value (incl. OHP) |  |  | 79778000 |  | Finalized Packages Savings against Lump Sum |  |  | 15919656 | #DIV/0! |  | Days Since Award (days) |  | 303 | Forecast Delay to Baseline |  | 13 | -159
[19 empty] | Finalized Packages Savings against contract PS |  |  | 13125327 | #DIV/0!
Data Date |  | 2026-03-31
SN | Pkg No. | Package | Package Manager | 15 |  | 7 |  | 6 |  | 3 |  | 30 |  | 10 |  | 20 |  | 7 |  | 7 |  | 5 |  | 10 |  | Variance from Today | PS Procurement Duration | PS - Lump Sum Value in LAFO | PS - Contract Value (excl. OHP) | PS - Contract Value (incl. OHP) | PS - Award Value (incl. OHP) | Saving (against PS in contract) | Awarded Sub-contractor | Cont Dur | Contract Date Nomination | Var | Float | Late Date in Programme | Var | Actual / Forecast Award | Current Stage (from 1-11) | 1. Tender Docs & BOQ | 2. Bidder List | 3. EOI | 4. Tender Float | 5. Initial submission | 6. Tech & Com Review | 7. BAFO | 8. Tech & Com Review | 9. Award Rec. Approval | 10. Issued to Contractor | 11. Subcontract signed
|  |  |  | 1. Tender Docs & BOQ |  | 2. Bidder List |  | 3. EOI |  | 4. Tender Float |  | 5. Initial submission |  | 6. Tech & Com Review |  | 7. BAFO |  | 8. Tech & Com Review |  | 9. Award Rec. Approval |  | 10. Issued to Contractor |  | 11. Subcontract Agreement signed
|  |  |  | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast
PC Rate Items
1 |  | Sanitaryware and Acessories | Manoj | 2025-09-23 | 2025-08-06 | 2025-09-30 | 2025-08-12 | 2025-10-06 | 2025-08-08 | 2025-10-09 | 2025-09-11 | 2025-11-08 | 2025-09-11 | 2025-11-18 | 2025-09-11 | 2025-12-08 | 2025-11-13 | 2025-12-15 | 2025-10-20 | 2025-12-22 | 2025-12-30 | 2025-12-27 | 2025-12-30 | 2026-01-06 |  | - | 95 | 10026777 |  | 9213000 | 4355584 | 4857416 | • Hashmiya (KOHLER) • Sanitary Material (ROCA) | 180 | 2025-12-27 | -3 |  | 2025-12-27 | -3 | 2025-12-30 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2 |  | Landscape Lighting | Manoj | 2025-10-23 | 2025-08-31 | 2025-10-30 | 2025-08-07 | 2025-11-05 | 2025-07-08 | 2025-11-08 | 2025-08-31 | 2025-12-08 | 2025-08-31 | 2025-12-18 | 2025-08-31 | 2026-01-07 | 2025-02-04 | 2026-01-14 | 2025-02-11 | 2026-01-21 |  | 2026-01-26 |  | 2026-02-05 |  | -64 | 95 | 1356425 |  | 1110000 | 1722089 | -612089 | Istanboul | 210 | 2026-01-26 | -76 |  | 2026-01-26 | -76 | 2026-04-12 | 9. Award Rec. Approval | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
3 |  | Light Fittings | Manoj | 2025-09-23 | 2025-08-31 | 2025-09-30 | 2025-08-07 | 2025-10-06 | 2025-07-08 | 2025-10-09 | 2025-10-21 | 2025-11-08 | 2025-10-21 | 2025-11-18 | 2025-10-21 | 2025-12-08 | 2025-02-04 | 2025-12-15 | 2025-02-11 | 2025-12-22 |  | 2025-12-27 |  | 2026-01-06 |  | -94 | 95 | 10614127 |  | 8880000 | incl. above | 8880000 | Istanboul | 180 | 2025-12-27 | -106 |  | 2025-12-27 | -106 | 2026-04-12 | 9. Award Rec. Approval | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE
MEP Works
4 |  | Penthouse MEP |  | 2025-10-23 |  | 2025-10-30 |  | 2025-11-05 |  | 2025-11-08 |  | 2025-12-08 |  | 2025-12-18 |  | 2026-01-07 |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-26 |  | 2026-02-05 |  | -64 | 95 |  |  | 2000000 |  |  |  | 210 | 2026-01-26 | -159 |  | 2026-01-26 | -159 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Joinery and Carpentry
5 |  | Kitchen cabinets | Suhail | 2025-10-23 |  | 2025-10-30 |  | 2025-11-05 |  | 2025-11-08 |  | 2025-12-08 |  | 2025-12-18 |  | 2026-01-07 |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-26 |  | 2026-02-05 |  | -64 | 95 | 20010091 |  | 17760000 |  |  |  | 210 | 2026-01-26 | -159 |  | 2026-01-26 | -159 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
6 |  | Timber Doors | Suhail | 2025-11-22 |  | 2025-11-29 |  | 2025-12-05 |  | 2025-12-08 |  | 2026-01-07 |  | 2026-01-17 |  | 2026-02-06 |  | 2026-02-13 |  | 2026-02-20 |  | 2026-02-25 |  | 2026-03-07 |  | -34 | 95 | 12902741 |  | 11100000 |  |  |  | 240 | 2026-02-25 | -129 |  | 2026-02-25 | -129 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
7 |  | Wardrobes | Suhail | 2025-11-22 |  | 2025-11-29 |  | 2025-12-05 |  | 2025-12-08 |  | 2026-01-07 |  | 2026-01-17 |  | 2026-02-06 |  | 2026-02-13 |  | 2026-02-20 |  | 2026-02-25 |  | 2026-03-07 |  | -34 | 95 | 7884722 |  | 6660000 |  |  |  | 240 | 2026-02-25 | -129 |  | 2026-02-25 | -129 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
8 |  | Laundry Cabinet | Suhail | 2025-11-22 |  | 2025-11-29 |  | 2025-12-05 |  | 2025-12-08 |  | 2026-01-07 |  | 2026-01-17 |  | 2026-02-06 |  | 2026-02-13 |  | 2026-02-20 |  | 2026-02-25 |  | 2026-03-07 |  | -34 | 95 | 1043761 |  | 888000 |  |  |  | 240 | 2026-02-25 | -129 |  | 2026-02-25 | -129 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
9 |  | Penthouse Wood | Suhail | 2025-12-22 |  | 2025-12-29 |  | 2026-01-04 |  | 2026-01-07 |  | 2026-02-06 |  | 2026-02-16 |  | 2026-03-08 |  | 2026-03-15 |  | 2026-03-22 |  | 2026-03-27 |  | 2026-04-06 |  | -4 | 95 | 1480740 |  | 1200000 |  |  |  | 270 | 2026-03-27 | -99 |  | 2026-03-27 | -99 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
10 |  | Penthouse Doors | Suhail | 2025-12-22 |  | 2025-12-29 |  | 2026-01-04 |  | 2026-01-07 |  | 2026-02-06 |  | 2026-02-16 |  | 2026-03-08 |  | 2026-03-15 |  | 2026-03-22 |  | 2026-03-27 |  | 2026-04-06 |  | -4 | 95 |  |  | 210000 |  |  |  | 270 | 2026-03-27 | -99 |  | 2026-03-27 | -99 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Equipments & Accessories
11 |  | BMU | Prabhu | 2025-10-23 |  | 2025-10-30 |  | 2025-11-05 |  | 2025-11-08 |  | 2025-12-08 |  | 2025-12-18 |  | 2026-01-07 |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-26 |  | 2026-02-05 |  | -64 | 95 | 4337607 |  | 3330000 |  |  |  | 210 | 2026-01-26 | -159 |  | 2026-01-26 | -159 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
12 |  | White goods | Jayantha | 2025-11-22 |  | 2025-11-29 |  | 2025-12-05 |  | 2025-12-08 |  | 2026-01-07 |  | 2026-01-17 |  | 2026-02-06 |  | 2026-02-13 |  | 2026-02-20 |  | 2026-02-25 |  | 2026-03-07 |  | -34 | 95 | 15657787 |  | 11100000 |  |  |  | 240 | 2026-02-25 | -129 |  | 2026-02-25 | -129 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
13 |  | Loose Furniture & Art works | Jayantha | 2025-12-22 |  | 2025-12-29 |  | 2026-01-04 |  | 2026-01-07 |  | 2026-02-06 |  | 2026-02-16 |  | 2026-03-08 |  | 2026-03-15 |  | 2026-03-22 |  | 2026-03-27 |  | 2026-04-06 |  | -4 | 95 | 6669531 |  | 6327000 |  |  |  | 270 | 2026-03-27 | -99 |  | 2026-03-27 | -99 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | Total | [25 empty] | 91984309 | 0 | 79778000 | 6077673 | 13125327
| 1 | Joinery works | [25 empty] | Will have tomorrow , Innovo Solutions
2
Formulas:
LDC = [Supervision]-H7
Supervision = [BUA (m2)]-J7
BUA (m2) = [Award Date]-L7
Award Date = [Plan]-N7
Plan = [Value Summary]-P7
Plan = [Plan]-T7
Value Summary = [Plan]-R7

## Waldorf
Project |  | Components | Category | LDC | PMC | Supervision | Contractor | BUA (m2) | GFA (m2) | Award Date | Commencement |  |  | Value Summary |  |  |  |  | Actual to date Impact on Value | [5 empty] | Packages Summary |  |  | Delay Summary |  | nos. | Max delay
[14 empty] | Project Lump Sum Value in LAFO |  |  |  |  | Awards up to date (incl. OHP) |  |  | 0 | #DIV/0! |  | Total Packages (nos) |  | 10 | Current delayed remaining packages |  | 0 | 21
Waldorf Astoria (Yas Links) |  | 3 Buildings 1B+G+7 | Resi Buildings | KEO | Atkins | Atkins | Freiburg | 61433 | 40574 | 2025-11-18 | 2026-04-22 |  |  | PS - Lump Sum Value in LAFO |  |  | 0 |  | Remaining to award |  |  | 0 | #DIV/0! |  | Finalized Packages (nos) |  | 0 | Forecast Delay to Contract |  | 1 | -74
[14 empty] | PS - Contract Value (incl. OHP) |  |  | 0 |  | Finalized Packages Savings against Lump Sum |  |  | 0 | #DIV/0! |  | Days Since Award (days) |  | 133 | Forecast Delay to Baseline |  | 1 | -74
[19 empty] | Finalized Packages Savings against contract PS |  |  | 0 | #DIV/0!
Data Date |  | 2026-03-31 | [31 empty] | Tentative
SN | Pkg No. | Package | Package Manager | 15 |  | 7 |  | 6 |  | 3 |  | 30 |  | 10 |  | 20 |  | 7 |  | 7 |  | 5 |  | 10 |  | Variance from Today | PS Procurement Duration | PS - Lump Sum Value in LAFO | PS - Contract Value (excl. OHP) | PS - Contract Value (incl. OHP) | PS - Award Value (incl. OHP) | Saving (against PS in contract) | Awarded Sub-contractor | Cont Dur | Contract Date Nomination | Var | Float | Late Date in Programme | Var | Actual / Forecast Award | Current Stage (from 1-11) | 1. Tender Docs & BOQ | 2. Bidder List | 3. EOI | 4. Tender Float | 5. Initial submission | 6. Tech & Com Review | 7. BAFO | 8. Tech & Com Review | 9. Award Rec. Approval | 10. Issued to Contractor | 11. Subcontract signed
|  |  |  | 1. Tender Docs & BOQ |  | 2. Bidder List |  | 3. EOI |  | 4. Tender Float |  | 5. Initial submission |  | 6. Tech & Com Review |  | 7. BAFO |  | 8. Tech & Com Review |  | 9. Award Rec. Approval |  | 10. Issued to Contractor |  | 11. Subcontract Agreement signed
|  |  |  | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast
Mock-up
1 |  | Mock-up |  | 2026-01-16 |  | 2026-01-23 |  | 2026-01-29 |  | 2026-02-01 |  | 2026-03-03 |  | 2026-03-13 |  | 2026-04-02 |  | 2026-04-09 |  | 2026-04-16 |  | 2026-04-21 |  | 2026-05-01 |  | 21 | 95 | [6 empty] | 0 | 2026-04-21 | -74 |  | 2026-04-21 | -74 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
PC Rate Items
2 |  | Sanitary Fixture |  | 2026-05-16 |  | 2026-05-23 |  | 2026-05-29 |  | 2026-06-01 |  | 2026-07-01 |  | 2026-07-11 |  | 2026-07-31 |  | 2026-08-07 |  | 2026-08-14 |  | 2026-08-19 |  | 2026-08-29 |  | 141 | 95 | [6 empty] | 120 | 2026-08-19 | 46 |  | 2026-08-19 | 46 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3 |  | Lighting fixtures |  | 2026-06-15 |  | 2026-06-22 |  | 2026-06-28 |  | 2026-07-01 |  | 2026-07-31 |  | 2026-08-10 |  | 2026-08-30 |  | 2026-09-06 |  | 2026-09-13 |  | 2026-09-18 |  | 2026-09-28 |  | 171 | 95 | [6 empty] | 150 | 2026-09-18 | 76 |  | 2026-09-18 | 76 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Joinery and Carpentry
4 |  | Timber doors |  | 2026-07-15 |  | 2026-07-22 |  | 2026-07-28 |  | 2026-07-31 |  | 2026-08-30 |  | 2026-09-09 |  | 2026-09-29 |  | 2026-10-06 |  | 2026-10-13 |  | 2026-10-18 |  | 2026-10-28 |  | 201 | 95 | [6 empty] | 180 | 2026-10-18 | 106 |  | 2026-10-18 | 106 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
5 |  | Woodworks |  | 2026-07-15 |  | 2026-07-22 |  | 2026-07-28 |  | 2026-07-31 |  | 2026-08-30 |  | 2026-09-09 |  | 2026-09-29 |  | 2026-10-06 |  | 2026-10-13 |  | 2026-10-18 |  | 2026-10-28 |  | 201 | 95 | [6 empty] | 180 | 2026-10-18 | 106 |  | 2026-10-18 | 106 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
6 |  | Kitchen cabinets |  | 2026-11-12 |  | 2026-11-19 |  | 2026-11-25 |  | 2026-11-28 |  | 2026-12-28 |  | 2027-01-07 |  | 2027-01-27 |  | 2027-02-03 |  | 2027-02-10 |  | 2027-02-15 |  | 2027-02-25 |  | 321 | 95 | [6 empty] | 300 | 2027-02-15 | 226 |  | 2027-02-15 | 226 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
External Works
7 |  | Softlandscape & irrigation |  | 2026-04-16 |  | 2026-04-23 |  | 2026-04-29 |  | 2026-05-02 |  | 2026-06-01 |  | 2026-06-11 |  | 2026-07-01 |  | 2026-07-08 |  | 2026-07-15 |  | 2026-07-20 |  | 2026-07-30 |  | 111 | 95 | [6 empty] | 90 | 2026-07-20 | 16 |  | 2026-07-20 | 16 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Equipments & Accessories
8 |  | Loose furniture |  | 2026-11-12 |  | 2026-11-19 |  | 2026-11-25 |  | 2026-11-28 |  | 2026-12-28 |  | 2027-01-07 |  | 2027-01-27 |  | 2027-02-03 |  | 2027-02-10 |  | 2027-02-15 |  | 2027-02-25 |  | 321 | 95 | [6 empty] | 300 | 2027-02-15 | 226 |  | 2027-02-15 | 226 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
9 |  | Gym equipment |  | 2027-01-16 |  | 2027-01-23 |  | 2027-01-29 |  | 2027-02-01 |  | 2027-03-03 |  | 2027-03-13 |  | 2027-04-02 |  | 2027-04-09 |  | 2027-04-16 |  | 2027-04-21 |  | 2027-05-01 |  | 386 | 95 | [6 empty] | 365 | 2027-04-21 | 291 |  | 2027-04-21 | 291 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
10 |  | Whitegoods |  | 2026-07-15 |  | 2026-07-22 |  | 2026-07-28 |  | 2026-07-31 |  | 2026-08-30 |  | 2026-09-09 |  | 2026-09-29 |  | 2026-10-06 |  | 2026-10-13 |  | 2026-10-18 |  | 2026-10-28 |  | 201 | 95 | [6 empty] | 180 | 2026-10-18 | 106 |  | 2026-10-18 | 106 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | Total | [25 empty] | 0 | 0 | 0 | 0 | 0
Fabrex for Mocup
2026-04-14
| 1 | Mock up, ptocureed before Nov 2026 | [25 empty] | Design in VE, 5.7m to 3m
| 2 | Sanitaryware & Light fitings | [25 empty] | will be start in advance due to the mcokup
| 3 | Piling ongoing
4
Formulas:
LDC = [Supervision]-H7
Supervision = [BUA (m2)]-J7
BUA (m2) = [Award Date]-L7
Award Date = [Plan]-N7
Plan = [Value Summary]-P7
Plan = [Plan]-T7
Value Summary = [Plan]-R7

## Fahid TA1-2
Project |  | Components | Category | LDC | PMC | Supervision | Contractor | BUA (m2) | GFA (m2) | Award Date | Commencement |  |  | Value Summary |  |  |  |  | Actual to date Impact on Value | [5 empty] | Packages Summary |  |  | Delay Summary |  | nos. | Max delay
[14 empty] | Project Lump Sum Value in LAFO |  |  |  |  | Awards up to date (incl. OHP) |  |  | 266400000 | 47.63% |  | Total Packages (nos) |  | 43 | Current delayed remaining packages |  | 0 | 49
Fahid TA1-2 |  | 7 Buildings G+P+10 | Resi Buildings | Mot Macdoland | Atkins | Atkins | Shapoorji | 180652 | 105417 | 2025-12-31 | 2026-04-20 |  |  | PS - Lump Sum Value in LAFO |  |  | 0 |  | Remaining to award |  |  | 292937687 | 52.37% |  | Finalized Packages (nos) |  | 0 | Forecast Delay to Contract |  | 5 | -1
[14 empty] | PS - Contract Value (incl. OHP) |  |  | 533566151 |  | Finalized Packages Savings against Lump Sum |  |  | -266400000 | #DIV/0! |  | Days Since Award (days) |  | 90 | Forecast Delay to Baseline |  | 5 | -1
[19 empty] | Finalized Packages Savings against contract PS |  |  | -25771536 | #DIV/0!
Data Date |  | 2026-03-31 | [31 empty] | Tentative
SN | Pkg No. | Package | Package Manager | 15 |  | 7 |  | 6 |  | 3 |  | 30 |  | 10 |  | 20 |  | 7 |  | 7 |  | 5 |  | 10 |  | Variance from Today | PS Procurement Duration | PS - Lump Sum Value in LAFO | PS - Contract Value (excl. OHP) | PS - Contract Value (incl. OHP) | PS - Award Value (incl. OHP) | Saving (against PS in contract) | Awarded Sub-contractor | Cont Dur | Contract Date Nomination | Var | Float | Late Date in Programme | Var | Actual / Forecast Award | Current Stage (from 1-11) | 1. Tender Docs & BOQ | 2. Bidder List | 3. EOI | 4. Tender Float | 5. Initial submission | 6. Tech & Com Review | 7. BAFO | 8. Tech & Com Review | 9. Award Rec. Approval | 10. Issued to Contractor | 11. Subcontract signed
|  |  |  | 1. Tender Docs & BOQ |  | 2. Bidder List |  | 3. EOI |  | 4. Tender Float |  | 5. Initial submission |  | 6. Tech & Com Review |  | 7. BAFO |  | 8. Tech & Com Review |  | 9. Award Rec. Approval |  | 10. Issued to Contractor |  | 11. Subcontract Agreement signed
|  |  |  | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast
PC Rate Items
1 |  | Sanitary Fixture | Ifthiqar | 2026-05-14 |  | 2026-05-21 |  | 2026-05-27 |  | 2026-05-30 |  | 2026-06-29 |  | 2026-07-09 |  | 2026-07-29 |  | 2026-08-05 |  | 2026-08-12 |  | 2026-08-17 |  | 2026-08-27 |  | 139 | 95 |  |  | 10026186 |  |  |  | 120 | 2026-08-17 | 44 |  | 2026-08-17 | 44 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2 |  | Lighting fixtures | Ifthiqar | 2026-05-14 |  | 2026-05-21 |  | 2026-05-27 |  | 2026-05-30 |  | 2026-06-29 |  | 2026-07-09 |  | 2026-07-29 |  | 2026-08-05 |  | 2026-08-12 |  | 2026-08-17 |  | 2026-08-27 |  | 139 | 95 |  |  | 6015712 |  |  |  | 120 | 2026-08-17 | 44 |  | 2026-08-17 | 44 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
MEP Works
3 |  | MEP Works | Manoj | 2026-01-29 | 2026-01-27 | 2026-02-05 | 2026-01-27 | 2026-02-11 | 2026-01-27 | 2026-02-14 | 2026-01-27 | 2026-03-16 | 2026-01-27 | 2026-03-26 | 2026-01-27 | 2026-04-15 | 2026-02-07 | 2026-04-22 | 2026-02-25 | 2026-04-29 | 2026-03-02 | 2026-05-04 |  | 2026-05-14 |  | - | 95 |  |  | 240628464 | 266400000 | -25771536 | ARCO | 15 | 2026-05-04 | 29 |  | 2026-05-04 | 29 | 2026-04-05 | 10. Issued to Contractor | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
Aluminum & Metal Works
4 |  | Fiber cement board | Prabhu | 2026-03-30 |  | 2026-04-06 |  | 2026-04-12 |  | 2026-04-15 |  | 2026-05-15 |  | 2026-05-25 |  | 2026-06-14 |  | 2026-06-21 |  | 2026-06-28 |  | 2026-07-03 |  | 2026-07-13 |  | 94 | 95 |  |  | 14036660 |  |  |  | 75 | 2026-07-03 | -1 |  | 2026-07-03 | -1 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
5 |  | GRC Cladding | Prabhu | 2026-03-30 |  | 2026-04-06 |  | 2026-04-12 |  | 2026-04-15 |  | 2026-05-15 |  | 2026-05-25 |  | 2026-06-14 |  | 2026-06-21 |  | 2026-06-28 |  | 2026-07-03 |  | 2026-07-13 |  | 94 | 95 |  |  | incl. above |  |  |  | 75 | 2026-07-03 | -1 |  | 2026-07-03 | -1 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
6 |  | Pergola Louver | Prabhu | 2026-03-30 |  | 2026-04-06 |  | 2026-04-12 |  | 2026-04-15 |  | 2026-05-15 |  | 2026-05-25 |  | 2026-06-14 |  | 2026-06-21 |  | 2026-06-28 |  | 2026-07-03 |  | 2026-07-13 |  | 94 | 95 |  |  | incl. above |  |  |  | 75 | 2026-07-03 | -1 |  | 2026-07-03 | -1 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
7 |  | External Wall Metal Work(Alumini Rofilel) | Prabhu | 2026-03-30 |  | 2026-04-06 |  | 2026-04-12 |  | 2026-04-15 |  | 2026-05-15 |  | 2026-05-25 |  | 2026-06-14 |  | 2026-06-21 |  | 2026-06-28 |  | 2026-07-03 |  | 2026-07-13 |  | 94 | 95 |  |  | 12833518 |  |  |  | 75 | 2026-07-03 | -1 |  | 2026-07-03 | -1 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
8 |  | Alum Doors.Curtain Wall.Balustrade | Prabhu | 2026-03-30 |  | 2026-04-06 |  | 2026-04-12 |  | 2026-04-15 |  | 2026-05-15 |  | 2026-05-25 |  | 2026-06-14 |  | 2026-06-21 |  | 2026-06-28 |  | 2026-07-03 |  | 2026-07-13 |  | 94 | 95 |  |  | 72188539 |  |  |  | 75 | 2026-07-03 | -1 |  | 2026-07-03 | -1 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
9 |  | Metal Doors | Prabhu | 2026-04-24 |  | 2026-05-01 |  | 2026-05-07 |  | 2026-05-10 |  | 2026-06-09 |  | 2026-06-19 |  | 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-08-07 |  | 119 | 95 |  |  | 2005237 |  |  |  | 100 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Joinery and Carpentry
10 |  | Timber Doors | Suhail | 2026-04-24 |  | 2026-05-01 |  | 2026-05-07 |  | 2026-05-10 |  | 2026-06-09 |  | 2026-06-19 |  | 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-08-07 |  | 119 | 95 |  |  | 14036660 |  |  |  | 100 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
11 |  | Ironmongery | Suhail | 2026-04-24 |  | 2026-05-01 |  | 2026-05-07 |  | 2026-05-10 |  | 2026-06-09 |  | 2026-06-19 |  | 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-08-07 |  | 119 | 95 |  |  | 2807332 |  |  |  | 100 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
12 |  | Woodworks | Suhail | 2026-04-24 |  | 2026-05-01 |  | 2026-05-07 |  | 2026-05-10 |  | 2026-06-09 |  | 2026-06-19 |  | 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-08-07 |  | 119 | 95 |  |  | 40104744 |  |  |  | 100 | 2026-07-28 | 24 |  | 2026-07-28 | 24 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Finishes
13 |  | Epoxy Flooring | Reyoon | 2026-04-04 |  | 2026-04-11 |  | 2026-04-17 |  | 2026-04-20 |  | 2026-05-20 |  | 2026-05-30 |  | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-08 |  | 2026-07-18 |  | 99 | 95 |  |  | 42511029 |  |  |  | 80 | 2026-07-08 | 4 |  | 2026-07-08 | 4 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
14 |  | Tiles - Floor, Walls, Skirting, Threshold |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-17 |  | 2026-04-20 |  | 2026-05-20 |  | 2026-05-30 |  | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-08 |  | 2026-07-18 |  | 99 | 95 |  |  | incl. above |  |  |  | 80 | 2026-07-08 | 4 |  | 2026-07-08 | 4 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
15 |  | Wooden Finishes |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-17 |  | 2026-04-20 |  | 2026-05-20 |  | 2026-05-30 |  | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-08 |  | 2026-07-18 |  | 99 | 95 |  |  | incl. above |  |  |  | 80 | 2026-07-08 | 4 |  | 2026-07-08 | 4 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
16 |  | Metal Trim |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-17 |  | 2026-04-20 |  | 2026-05-20 |  | 2026-05-30 |  | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-08 |  | 2026-07-18 |  | 99 | 95 |  |  | incl. above |  |  |  | 80 | 2026-07-08 | 4 |  | 2026-07-08 | 4 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
17 |  | Paint - Internal and External |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-17 |  | 2026-04-20 |  | 2026-05-20 |  | 2026-05-30 |  | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-08 |  | 2026-07-18 |  | 99 | 95 |  |  | incl. above |  |  |  | 80 | 2026-07-08 | 4 |  | 2026-07-08 | 4 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
18 |  | Wallpaper |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-17 |  | 2026-04-20 |  | 2026-05-20 |  | 2026-05-30 |  | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-08 |  | 2026-07-18 |  | 99 | 95 |  |  | incl. above |  |  |  | 80 | 2026-07-08 | 4 |  | 2026-07-08 | 4 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
19 |  | Stone Cladding |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-17 |  | 2026-04-20 |  | 2026-05-20 |  | 2026-05-30 |  | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-08 |  | 2026-07-18 |  | 99 | 95 |  |  | incl. above |  |  |  | 80 | 2026-07-08 | 4 |  | 2026-07-08 | 4 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
20 |  | Suspended Ceiling |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-17 |  | 2026-04-20 |  | 2026-05-20 |  | 2026-05-30 |  | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-08 |  | 2026-07-18 |  | 99 | 95 |  |  | incl. above |  |  |  | 80 | 2026-07-08 | 4 |  | 2026-07-08 | 4 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
21 |  | Finishes - Screed and Plaster | Reyoon | 2026-04-04 |  | 2026-04-11 |  | 2026-04-17 |  | 2026-04-20 |  | 2026-05-20 |  | 2026-05-30 |  | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-08 |  | 2026-07-18 |  | 99 | 95 |  |  | 31081177 |  |  |  | 80 | 2026-07-08 | 4 |  | 2026-07-08 | 4 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
External Works
22 |  | Hardscape | Suhail | 2026-04-14 |  | 2026-04-21 |  | 2026-04-27 |  | 2026-04-30 |  | 2026-05-30 |  | 2026-06-09 |  | 2026-06-29 |  | 2026-07-06 |  | 2026-07-13 |  | 2026-07-18 |  | 2026-07-28 |  | 109 | 95 |  |  | 14253226 |  |  |  | 90 | 2026-07-18 | 14 |  | 2026-07-18 | 14 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
23 |  | Softscape | Suhail | 2026-04-14 |  | 2026-04-21 |  | 2026-04-27 |  | 2026-04-30 |  | 2026-05-30 |  | 2026-06-09 |  | 2026-06-29 |  | 2026-07-06 |  | 2026-07-13 |  | 2026-07-18 |  | 2026-07-28 |  | 109 | 95 |  |  | incl. above |  |  |  | 90 | 2026-07-18 | 14 |  | 2026-07-18 | 14 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
24 |  | Fencing and Railing | Prabhu | 2026-04-14 |  | 2026-04-21 |  | 2026-04-27 |  | 2026-04-30 |  | 2026-05-30 |  | 2026-06-09 |  | 2026-06-29 |  | 2026-07-06 |  | 2026-07-13 |  | 2026-07-18 |  | 2026-07-28 |  | 109 | 95 |  |  | incl. above |  |  |  | 90 | 2026-07-18 | 14 |  | 2026-07-18 | 14 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
25 |  | Steel Shade Structure | Prabhu | 2026-04-14 |  | 2026-04-21 |  | 2026-04-27 |  | 2026-04-30 |  | 2026-05-30 |  | 2026-06-09 |  | 2026-06-29 |  | 2026-07-06 |  | 2026-07-13 |  | 2026-07-18 |  | 2026-07-28 |  | 109 | 95 |  |  | incl. above |  |  |  | 90 | 2026-07-18 | 14 |  | 2026-07-18 | 14 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
26 |  | Road marking and Road signs | Jayantha | 2026-04-14 |  | 2026-04-21 |  | 2026-04-27 |  | 2026-04-30 |  | 2026-05-30 |  | 2026-06-09 |  | 2026-06-29 |  | 2026-07-06 |  | 2026-07-13 |  | 2026-07-18 |  | 2026-07-28 |  | 109 | 95 |  |  | incl. above |  |  |  | 90 | 2026-07-18 | 14 |  | 2026-07-18 | 14 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
27 |  | External Srvices (MEP) | Manoj | 2026-04-14 |  | 2026-04-21 |  | 2026-04-27 |  | 2026-04-30 |  | 2026-05-30 |  | 2026-06-09 |  | 2026-06-29 |  | 2026-07-06 |  | 2026-07-13 |  | 2026-07-18 |  | 2026-07-28 |  | 109 | 95 |  |  | incl. above |  |  |  | 90 | 2026-07-18 | 14 |  | 2026-07-18 | 14 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
28 |  | Landscape Lighting | Manoj | 2026-04-14 |  | 2026-04-21 |  | 2026-04-27 |  | 2026-04-30 |  | 2026-05-30 |  | 2026-06-09 |  | 2026-06-29 |  | 2026-07-06 |  | 2026-07-13 |  | 2026-07-18 |  | 2026-07-28 |  | 109 | 95 |  |  | incl. above |  |  |  | 90 | 2026-07-18 | 14 |  | 2026-07-18 | 14 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
29 |  | SPA | Jayantha | 2026-05-14 |  | 2026-05-21 |  | 2026-05-27 |  | 2026-05-30 |  | 2026-06-29 |  | 2026-07-09 |  | 2026-07-29 |  | 2026-08-05 |  | 2026-08-12 |  | 2026-08-17 |  | 2026-08-27 |  | 139 | 95 |  |  | 5614664 |  |  |  | 120 | 2026-08-17 | 44 |  | 2026-08-17 | 44 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
30 |  | Squash Court |  | 2026-05-14 |  | 2026-05-21 |  | 2026-05-27 |  | 2026-05-30 |  | 2026-06-29 |  | 2026-07-09 |  | 2026-07-29 |  | 2026-08-05 |  | 2026-08-12 |  | 2026-08-17 |  | 2026-08-27 |  | 139 | 95 |  |  | incl. above |  |  |  | 120 | 2026-08-17 | 44 |  | 2026-08-17 | 44 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
31 |  | Cinema |  | 2026-05-14 |  | 2026-05-21 |  | 2026-05-27 |  | 2026-05-30 |  | 2026-06-29 |  | 2026-07-09 |  | 2026-07-29 |  | 2026-08-05 |  | 2026-08-12 |  | 2026-08-17 |  | 2026-08-27 |  | 139 | 95 |  |  | incl. above |  |  |  | 120 | 2026-08-17 | 44 |  | 2026-08-17 | 44 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
32 |  | Swimming Pool | Suhail | 2026-05-14 |  | 2026-05-21 |  | 2026-05-27 |  | 2026-05-30 |  | 2026-06-29 |  | 2026-07-09 |  | 2026-07-29 |  | 2026-08-05 |  | 2026-08-12 |  | 2026-08-17 |  | 2026-08-27 |  | 139 | 95 |  |  | incl. above |  |  |  | 120 | 2026-08-17 | 44 |  | 2026-08-17 | 44 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Equipments & Accessories
33 |  | Lifts | Manoj | 2026-02-13 | 2026-01-27 | 2026-02-20 | 2026-01-27 | 2026-02-26 | 2026-01-27 | 2026-03-01 | 2026-01-27 | 2026-03-31 | 2026-01-27 | 2026-04-10 | 2026-01-27 | 2026-04-30 | 2026-02-16 | 2026-05-07 |  | 2026-05-14 |  | 2026-05-19 |  | 2026-05-29 |  | 49 | 95 |  |  | 6417366 |  |  |  | 30 | 2026-05-19 | 30 |  | 2026-05-19 | 30 | 2026-04-19 | 8. Tech & Com Review | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE
34 |  | Accessories (MIRROR,PARTITION ) | Prabhu | 2026-05-14 |  | 2026-05-21 |  | 2026-05-27 |  | 2026-05-30 |  | 2026-06-29 |  | 2026-07-09 |  | 2026-07-29 |  | 2026-08-05 |  | 2026-08-12 |  | 2026-08-17 |  | 2026-08-27 |  | 139 | 95 |  |  | 601571 |  |  |  | 120 | 2026-08-17 | 44 |  | 2026-08-17 | 44 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
35 |  | Supply of White Goods | Jayantha | 2026-05-14 |  | 2026-05-21 |  | 2026-05-27 |  | 2026-05-30 |  | 2026-06-29 |  | 2026-07-09 |  | 2026-07-29 |  | 2026-08-05 |  | 2026-08-12 |  | 2026-08-17 |  | 2026-08-27 |  | 139 | 95 |  |  | 8622520 |  |  |  | 120 | 2026-08-17 | 44 |  | 2026-08-17 | 44 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
36 |  | Parking Accessories | Jayantha | 2026-05-14 |  | 2026-05-21 |  | 2026-05-27 |  | 2026-05-30 |  | 2026-06-29 |  | 2026-07-09 |  | 2026-07-29 |  | 2026-08-05 |  | 2026-08-12 |  | 2026-08-17 |  | 2026-08-27 |  | 139 | 95 |  |  | 4010474 |  |  |  | 120 | 2026-08-17 | 44 |  | 2026-08-17 | 44 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
37 |  | Garbage Chute | Jayantha | 2026-05-14 |  | 2026-05-21 |  | 2026-05-27 |  | 2026-05-30 |  | 2026-06-29 |  | 2026-07-09 |  | 2026-07-29 |  | 2026-08-05 |  | 2026-08-12 |  | 2026-08-17 |  | 2026-08-27 |  | 139 | 95 |  |  | 1804713 |  |  |  | 120 | 2026-08-17 | 44 |  | 2026-08-17 | 44 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
38 |  | BMU | Jayantha | 2026-05-14 |  | 2026-05-21 |  | 2026-05-27 |  | 2026-05-30 |  | 2026-06-29 |  | 2026-07-09 |  | 2026-07-29 |  | 2026-08-05 |  | 2026-08-12 |  | 2026-08-17 |  | 2026-08-27 |  | 139 | 95 |  |  | incl. above |  |  |  | 120 | 2026-08-17 | 44 |  | 2026-08-17 | 44 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
39 |  | Loose Furniture | Jayantha | 2026-11-10 |  | 2026-11-17 |  | 2026-11-23 |  | 2026-11-26 |  | 2026-12-26 |  | 2027-01-05 |  | 2027-01-25 |  | 2027-02-01 |  | 2027-02-08 |  | 2027-02-13 |  | 2027-02-23 |  | 319 | 95 |  |  | 2005237 |  |  |  | 300 | 2027-02-13 | 224 |  | 2027-02-13 | 224 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
40 |  | Outdoor Furniture | Jayantha | 2026-11-10 |  | 2026-11-17 |  | 2026-11-23 |  | 2026-11-26 |  | 2026-12-26 |  | 2027-01-05 |  | 2027-01-25 |  | 2027-02-01 |  | 2027-02-08 |  | 2027-02-13 |  | 2027-02-23 |  | 319 | 95 |  |  | 501309 |  |  |  | 300 | 2027-02-13 | 224 |  | 2027-02-13 | 224 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
41 |  | Supply and installation of gym equipment | Jayantha | 2026-11-10 |  | 2026-11-17 |  | 2026-11-23 |  | 2026-11-26 |  | 2026-12-26 |  | 2027-01-05 |  | 2027-01-25 |  | 2027-02-01 |  | 2027-02-08 |  | 2027-02-13 |  | 2027-02-23 |  | 319 | 95 |  |  | 401047 |  |  |  | 300 | 2027-02-13 | 224 |  | 2027-02-13 | 224 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
42 |  | supply and installation of play equipment | Jayantha | 2026-11-10 |  | 2026-11-17 |  | 2026-11-23 |  | 2026-11-26 |  | 2026-12-26 |  | 2027-01-05 |  | 2027-01-25 |  | 2027-02-01 |  | 2027-02-08 |  | 2027-02-13 |  | 2027-02-23 |  | 319 | 95 |  |  | 56147 |  |  |  | 300 | 2027-02-13 | 224 |  | 2027-02-13 | 224 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
43 |  | Furnishings | Jayantha | 2026-11-10 |  | 2026-11-17 |  | 2026-11-23 |  | 2026-11-26 |  | 2026-12-26 |  | 2027-01-05 |  | 2027-01-25 |  | 2027-02-01 |  | 2027-02-08 |  | 2027-02-13 |  | 2027-02-23 |  | 319 | 95 |  |  | 1002619 |  |  |  | 300 | 2027-02-13 | 224 |  | 2027-02-13 | 224 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | Total | [25 empty] | 0 | 0 | 533566151 | 266400000 | -25771536
| 1 | MEP works | [25 empty] | S?C agreement issued and siged expected this week
| 2 | Lifts
3
4
5
6
7
8
Formulas:
LDC = [Supervision]-H7
Supervision = [BUA (m2)]-J7
BUA (m2) = [Award Date]-L7
Award Date = [Plan]-N7
Plan = [Value Summary]-P7
Plan = [Plan]-T7
Value Summary = [Plan]-R7

## Fahid TA3-5
Project |  | Components | Category | LDC | PMC | Supervision | Contractor | BUA (m2) | GFA (m2) | Award Date | Commencement |  |  | Value Summary |  |  |  |  | Actual to date Impact on Value | [5 empty] | Packages Summary |  |  | Delay Summary |  | nos. | Max delay
[14 empty] | Project Lump Sum Value in LAFO |  |  |  |  | Awards up to date (incl. OHP) |  |  | 0 | 0% |  | Total Packages (nos) |  | 24 | Current delayed remaining packages |  | 0 | 159
Fahid TA3-5 |  | 6 Buildings B+G+10 | Resi Buildings |  | Atkins | Atkins | Shapoorji |  | 122125 | 2025-12-31 | 2026-08-23 |  |  | PS - Lump Sum Value in LAFO |  |  | 0 |  | Remaining to award |  |  | 612041901 | 100% |  | Finalized Packages (nos) |  | 0 | Forecast Delay to Contract |  | 0 | 79
[14 empty] | PS - Contract Value (incl. OHP) |  |  | 612041901 |  | Finalized Packages Savings against Lump Sum |  |  | 0 | #DIV/0! |  | Days Since Award (days) |  | 90 | Forecast Delay to Baseline |  | 0 | 79
[19 empty] | Finalized Packages Savings against contract PS |  |  | 0 | #DIV/0!
Data Date |  | 2026-03-31 | [31 empty] | Tentative
SN | Pkg No. | Package | Package Manager | 15 |  | 7 |  | 6 |  | 3 |  | 30 |  | 10 |  | 20 |  | 7 |  | 7 |  | 5 |  | 10 |  | Variance from Today | PS Procurement Duration | PS - Lump Sum Value in LAFO | PS - Contract Value (excl. OHP) | PS - Contract Value (incl. OHP) | PS - Award Value (incl. OHP) | Saving (against PS in contract) | Awarded Sub-contractor | Cont Dur | Contract Date Nomination | Var | Float | Late Date in Programme | Var | Actual / Forecast Award | Current Stage (from 1-11) | 1. Tender Docs & BOQ | 2. Bidder List | 3. EOI | 4. Tender Float | 5. Initial submission | 6. Tech & Com Review | 7. BAFO | 8. Tech & Com Review | 9. Award Rec. Approval | 10. Issued to Contractor | 11. Subcontract signed
|  |  |  | 1. Tender Docs & BOQ |  | 2. Bidder List |  | 3. EOI |  | 4. Tender Float |  | 5. Initial submission |  | 6. Tech & Com Review |  | 7. BAFO |  | 8. Tech & Com Review |  | 9. Award Rec. Approval |  | 10. Issued to Contractor |  | 11. Subcontract Agreement signed
|  |  |  | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast
PC Rate Items
1 |  | Sanitary Fixture | Manoj | 2026-09-16 |  | 2026-09-23 |  | 2026-09-29 |  | 2026-10-02 |  | 2026-11-01 |  | 2026-11-11 |  | 2026-12-01 |  | 2026-12-08 |  | 2026-12-15 |  | 2026-12-20 |  | 2026-12-30 |  | 264 | 95 |  |  | 11500821 |  |  |  | 120 | 2026-12-20 | 169 |  | 2026-12-20 | 169 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2 |  | Lighting fixtures | Manoj | 2026-09-16 |  | 2026-09-23 |  | 2026-09-29 |  | 2026-10-02 |  | 2026-11-01 |  | 2026-11-11 |  | 2026-12-01 |  | 2026-12-08 |  | 2026-12-15 |  | 2026-12-20 |  | 2026-12-30 |  | 264 | 95 |  |  | 6900537 |  |  |  | 120 | 2026-12-20 | 169 |  | 2026-12-20 | 169 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
MEP Works
3 |  | MEP Works | Manoj | 2026-06-03 | 2026-01-27 | 2026-06-10 | 2026-01-27 | 2026-06-16 | 2026-01-27 | 2026-06-19 | 2026-01-27 | 2026-07-19 |  | 2026-07-29 |  | 2026-08-18 |  | 2026-08-25 |  | 2026-09-01 |  | 2026-09-06 |  | 2026-09-16 |  | 159 | 95 |  |  | 276019704 |  |  |  | 15 | 2026-09-06 | 80 |  | 2026-09-06 | 80 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Aluminum & Metal Works
4 |  | External Wall Finishes (Grc,Tiles,Cem Board) | Prabhu | 2026-08-02 |  | 2026-08-09 |  | 2026-08-15 |  | 2026-08-18 |  | 2026-09-17 |  | 2026-09-27 |  | 2026-10-17 |  | 2026-10-24 |  | 2026-10-31 |  | 2026-11-05 |  | 2026-11-15 |  | 219 | 95 |  |  | 16101105 |  |  |  | 75 | 2026-11-05 | 124 |  | 2026-11-05 | 124 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
5 |  | External Wall Metal Work(Alumini Rofilel) | Prabhu | 2026-08-02 |  | 2026-08-09 |  | 2026-08-15 |  | 2026-08-18 |  | 2026-09-17 |  | 2026-09-27 |  | 2026-10-17 |  | 2026-10-24 |  | 2026-10-31 |  | 2026-11-05 |  | 2026-11-15 |  | 219 | 95 |  |  | 14721042 |  |  |  | 75 | 2026-11-05 | 124 |  | 2026-11-05 | 124 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
6 |  | Alum Doors.Curtain Wall.Balustrade | Prabhu | 2026-08-02 |  | 2026-08-09 |  | 2026-08-15 |  | 2026-08-18 |  | 2026-09-17 |  | 2026-09-27 |  | 2026-10-17 |  | 2026-10-24 |  | 2026-10-31 |  | 2026-11-05 |  | 2026-11-15 |  | 219 | 95 |  |  | 82805889 |  |  |  | 75 | 2026-11-05 | 124 |  | 2026-11-05 | 124 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
7 |  | Metal Doors | Prabhu | 2026-08-27 |  | 2026-09-03 |  | 2026-09-09 |  | 2026-09-12 |  | 2026-10-12 |  | 2026-10-22 |  | 2026-11-11 |  | 2026-11-18 |  | 2026-11-25 |  | 2026-11-30 |  | 2026-12-10 |  | 244 | 95 |  |  | 2300142 |  |  |  | 100 | 2026-11-30 | 149 |  | 2026-11-30 | 149 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Joinery and Carpentry
8 |  | Timber Doors | Suhail | 2026-08-27 |  | 2026-09-03 |  | 2026-09-09 |  | 2026-09-12 |  | 2026-10-12 |  | 2026-10-22 |  | 2026-11-11 |  | 2026-11-18 |  | 2026-11-25 |  | 2026-11-30 |  | 2026-12-10 |  | 244 | 95 |  |  | 16101105 |  |  |  | 100 | 2026-11-30 | 149 |  | 2026-11-30 | 149 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
9 |  | Ironmongery | Suhail | 2026-08-27 |  | 2026-09-03 |  | 2026-09-09 |  | 2026-09-12 |  | 2026-10-12 |  | 2026-10-22 |  | 2026-11-11 |  | 2026-11-18 |  | 2026-11-25 |  | 2026-11-30 |  | 2026-12-10 |  | 244 | 95 |  |  | 3220221 |  |  |  | 100 | 2026-11-30 | 149 |  | 2026-11-30 | 149 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
10 |  | Woodworks | Suhail | 2026-08-27 |  | 2026-09-03 |  | 2026-09-09 |  | 2026-09-12 |  | 2026-10-12 |  | 2026-10-22 |  | 2026-11-11 |  | 2026-11-18 |  | 2026-11-25 |  | 2026-11-30 |  | 2026-12-10 |  | 244 | 95 |  |  | 46003284 |  |  |  | 100 | 2026-11-30 | 149 |  | 2026-11-30 | 149 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Finishes
11 |  | Internal Finishes | Reyoon | 2026-08-07 |  | 2026-08-14 |  | 2026-08-20 |  | 2026-08-23 |  | 2026-09-22 |  | 2026-10-02 |  | 2026-10-22 |  | 2026-10-29 |  | 2026-11-05 |  | 2026-11-10 |  | 2026-11-20 |  | 224 | 95 |  |  | 48763521 |  |  |  | 80 | 2026-11-10 | 129 |  | 2026-11-10 | 129 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
12 |  | Finishes - Screed and Plaster | Reyoon | 2026-08-07 |  | 2026-08-14 |  | 2026-08-20 |  | 2026-08-23 |  | 2026-09-22 |  | 2026-10-02 |  | 2026-10-22 |  | 2026-10-29 |  | 2026-11-05 |  | 2026-11-10 |  | 2026-11-20 |  | 224 | 95 |  |  | 35652534 |  |  |  | 80 | 2026-11-10 | 129 |  | 2026-11-10 | 129 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
External Works
13 |  | External works (Landscape & irrigation) | Suhail | 2026-08-17 |  | 2026-08-24 |  | 2026-08-30 |  | 2026-09-02 |  | 2026-10-02 |  | 2026-10-12 |  | 2026-11-01 |  | 2026-11-08 |  | 2026-11-15 |  | 2026-11-20 |  | 2026-11-30 |  | 234 | 95 |  |  | 16349523 |  |  |  | 90 | 2026-11-20 | 139 |  | 2026-11-20 | 139 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
14 |  | Special Construction | Suhail | 2026-09-16 |  | 2026-09-23 |  | 2026-09-29 |  | 2026-10-02 |  | 2026-11-01 |  | 2026-11-11 |  | 2026-12-01 |  | 2026-12-08 |  | 2026-12-15 |  | 2026-12-20 |  | 2026-12-30 |  | 264 | 95 |  |  | 6440442 |  |  |  | 120 | 2026-12-20 | 169 |  | 2026-12-20 | 169 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Equipments & Accessories
15 |  | Lifts | Manoj | 2026-06-18 |  | 2026-06-25 |  | 2026-07-01 |  | 2026-07-04 |  | 2026-08-03 |  | 2026-08-13 |  | 2026-09-02 |  | 2026-09-09 |  | 2026-09-16 |  | 2026-09-21 |  | 2026-10-01 |  | 174 | 95 |  |  | 7361187 |  |  |  | 30 | 2026-09-21 | 79 |  | 2026-09-21 | 79 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
16 |  | Accessories (MIRROR,PARTITION ) | Prabhu | 2026-09-16 |  | 2026-09-23 |  | 2026-09-29 |  | 2026-10-02 |  | 2026-11-01 |  | 2026-11-11 |  | 2026-12-01 |  | 2026-12-08 |  | 2026-12-15 |  | 2026-12-20 |  | 2026-12-30 |  | 264 | 95 |  |  | 690087 |  |  |  | 120 | 2026-12-20 | 169 |  | 2026-12-20 | 169 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
17 |  | Supply of White Goods | Jayantha | 2026-09-16 |  | 2026-09-23 |  | 2026-09-29 |  | 2026-10-02 |  | 2026-11-01 |  | 2026-11-11 |  | 2026-12-01 |  | 2026-12-08 |  | 2026-12-15 |  | 2026-12-20 |  | 2026-12-30 |  | 264 | 95 |  |  | 9890655 |  |  |  | 120 | 2026-12-20 | 169 |  | 2026-12-20 | 169 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
18 |  | Accessories | Jayantha | 2026-09-16 |  | 2026-09-23 |  | 2026-09-29 |  | 2026-10-02 |  | 2026-11-01 |  | 2026-11-11 |  | 2026-12-01 |  | 2026-12-08 |  | 2026-12-15 |  | 2026-12-20 |  | 2026-12-30 |  | 264 | 95 |  |  | 4600284 |  |  |  | 120 | 2026-12-20 | 169 |  | 2026-12-20 | 169 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
19 |  | Garbage chute and BMU | Suhail | 2026-09-16 |  | 2026-09-23 |  | 2026-09-29 |  | 2026-10-02 |  | 2026-11-01 |  | 2026-11-11 |  | 2026-12-01 |  | 2026-12-08 |  | 2026-12-15 |  | 2026-12-20 |  | 2026-12-30 |  | 264 | 95 |  |  | 2070150 |  |  |  | 120 | 2026-12-20 | 169 |  | 2026-12-20 | 169 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
20 |  | Loose Furniture | Jayantha | 2027-03-15 |  | 2027-03-22 |  | 2027-03-28 |  | 2027-03-31 |  | 2027-04-30 |  | 2027-05-10 |  | 2027-05-30 |  | 2027-06-06 |  | 2027-06-13 |  | 2027-06-18 |  | 2027-06-28 |  | 444 | 95 |  |  | 2300142 |  |  |  | 300 | 2027-06-18 | 349 |  | 2027-06-18 | 349 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
21 |  | Outdoor Furniture | Jayantha | 2027-03-15 |  | 2027-03-22 |  | 2027-03-28 |  | 2027-03-31 |  | 2027-04-30 |  | 2027-05-10 |  | 2027-05-30 |  | 2027-06-06 |  | 2027-06-13 |  | 2027-06-18 |  | 2027-06-28 |  | 444 | 95 |  |  | 575091 |  |  |  | 300 | 2027-06-18 | 349 |  | 2027-06-18 | 349 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
22 |  | supply and installation of gym equipment | Jayantha | 2027-03-15 |  | 2027-03-22 |  | 2027-03-28 |  | 2027-03-31 |  | 2027-04-30 |  | 2027-05-10 |  | 2027-05-30 |  | 2027-06-06 |  | 2027-06-13 |  | 2027-06-18 |  | 2027-06-28 |  | 444 | 95 |  |  | 459984 |  |  |  | 300 | 2027-06-18 | 349 |  | 2027-06-18 | 349 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
23 |  | supply and installation of play equipment | Jayantha | 2027-03-15 |  | 2027-03-22 |  | 2027-03-28 |  | 2027-03-31 |  | 2027-04-30 |  | 2027-05-10 |  | 2027-05-30 |  | 2027-06-06 |  | 2027-06-13 |  | 2027-06-18 |  | 2027-06-28 |  | 444 | 95 |  |  | 64380 |  |  |  | 300 | 2027-06-18 | 349 |  | 2027-06-18 | 349 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
24 |  | Furnishings | Jayantha | 2027-03-15 |  | 2027-03-22 |  | 2027-03-28 |  | 2027-03-31 |  | 2027-04-30 |  | 2027-05-10 |  | 2027-05-30 |  | 2027-06-06 |  | 2027-06-13 |  | 2027-06-18 |  | 2027-06-28 |  | 444 | 95 |  |  | 1150071 |  |  |  | 300 | 2027-06-18 | 349 |  | 2027-06-18 | 349 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | Total | [25 empty] | 0 | 0 | 612041901 | 0 | 0
Formulas:
LDC = [Supervision]-H7
Supervision = [BUA (m2)]-J7
BUA (m2) = [Award Date]-L7
Award Date = [Plan]-N7
Plan = [Value Summary]-P7
Plan = [Plan]-T7
Value Summary = [Plan]-R7

## Fahid TA6-8
Project |  | Components | Category | LDC | PMC | Supervision | Contractor | BUA (m2) | GFA (m2) | Award Date | Commencement |  |  | Value Summary |  |  |  |  | Actual to date Impact on Value | [5 empty] | Packages Summary |  |  | Delay Summary |  | nos. | Max delay
[14 empty] | Project Lump Sum Value in LAFO |  |  |  |  | Awards up to date (incl. OHP) |  |  | 0 | 0% |  | Total Packages (nos) |  | 24 | Current delayed remaining packages |  | 0 | 76
Fahid TA6-8 |  | 11 Buildings B+G+9 | Resi Buildings |  | Atkins | Atkins | Shapoorji |  | 119685 | 2025-12-31 | 2026-06-01 |  |  | PS - Lump Sum Value in LAFO |  |  | 0 |  | Remaining to award |  |  | 588986535 | 100% |  | Finalized Packages (nos) |  | 0 | Forecast Delay to Contract |  | 2 | -4
[14 empty] | PS - Contract Value (incl. OHP) |  |  | 588986535 |  | Finalized Packages Savings against Lump Sum |  |  | 0 | #DIV/0! |  | Days Since Award (days) |  | 90 | Forecast Delay to Baseline |  | 2 | -4
[19 empty] | Finalized Packages Savings against contract PS |  |  | 0 | #DIV/0!
Data Date |  | 2026-03-31 | [31 empty] | Tentative
SN | Pkg No. | Package | Package Manager | 15 |  | 7 |  | 6 |  | 3 |  | 30 |  | 10 |  | 20 |  | 7 |  | 7 |  | 5 |  | 10 |  | Variance from Today | PS Procurement Duration | PS - Lump Sum Value in LAFO | PS - Contract Value (excl. OHP) | PS - Contract Value (incl. OHP) | PS - Award Value (incl. OHP) | Saving (against PS in contract) | Awarded Sub-contractor | Cont Dur | Contract Date Nomination | Var | Float | Late Date in Programme | Var | Actual / Forecast Award | Current Stage (from 1-11) | 1. Tender Docs & BOQ | 2. Bidder List | 3. EOI | 4. Tender Float | 5. Initial submission | 6. Tech & Com Review | 7. BAFO | 8. Tech & Com Review | 9. Award Rec. Approval | 10. Issued to Contractor | 11. Subcontract signed
|  |  |  | 1. Tender Docs & BOQ |  | 2. Bidder List |  | 3. EOI |  | 4. Tender Float |  | 5. Initial submission |  | 6. Tech & Com Review |  | 7. BAFO |  | 8. Tech & Com Review |  | 9. Award Rec. Approval |  | 10. Issued to Contractor |  | 11. Subcontract Agreement signed
|  |  |  | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast
PC Rate Items
1 |  | Sanitary Fixture | Ifthiqar | 2026-06-25 |  | 2026-07-02 |  | 2026-07-08 |  | 2026-07-11 |  | 2026-08-10 |  | 2026-08-20 |  | 2026-09-09 |  | 2026-09-16 |  | 2026-09-23 |  | 2026-09-28 |  | 2026-10-08 |  | 181 | 95 |  |  | 11067588 |  |  |  | 120 | 2026-09-28 | 86 |  | 2026-09-28 | 86 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2 |  | Lighting fixtures | Ifthiqar | 2026-06-25 |  | 2026-07-02 |  | 2026-07-08 |  | 2026-07-11 |  | 2026-08-10 |  | 2026-08-20 |  | 2026-09-09 |  | 2026-09-16 |  | 2026-09-23 |  | 2026-09-28 |  | 2026-10-08 |  | 181 | 95 |  |  | 6640575 |  |  |  | 120 | 2026-09-28 | 86 |  | 2026-09-28 | 86 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
MEP Works
3 |  | MEP Works | Manoj | 2026-03-12 | 2026-01-27 | 2026-03-19 | 2026-01-27 | 2026-03-25 | 2026-01-27 | 2026-03-28 | 2026-01-27 | 2026-04-27 |  | 2026-05-07 |  | 2026-05-27 |  | 2026-06-03 |  | 2026-06-10 |  | 2026-06-15 |  | 2026-06-25 |  | 76 | 95 |  |  | 265622112 |  |  |  | 15 | 2026-06-15 | -3 |  | 2026-06-15 | -3 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Aluminum & Metal Works
4 |  | External Wall Finishes (Grc,Tiles,Cem Board) | Prabhu | 2026-05-11 |  | 2026-05-18 |  | 2026-05-24 |  | 2026-05-27 |  | 2026-06-26 |  | 2026-07-06 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-08-09 |  | 2026-08-14 |  | 2026-08-24 |  | 136 | 95 |  |  | 15494601 |  |  |  | 75 | 2026-08-14 | 41 |  | 2026-08-14 | 41 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
5 |  | External Wall Metal Work(Alumini Rofilel) | Prabhu | 2026-05-11 |  | 2026-05-18 |  | 2026-05-24 |  | 2026-05-27 |  | 2026-06-26 |  | 2026-07-06 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-08-09 |  | 2026-08-14 |  | 2026-08-24 |  | 136 | 95 |  |  | 14166486 |  |  |  | 75 | 2026-08-14 | 41 |  | 2026-08-14 | 41 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
6 |  | Alum Doors.Curtain Wall.Balustrade | Prabhu | 2026-05-11 |  | 2026-05-18 |  | 2026-05-24 |  | 2026-05-27 |  | 2026-06-26 |  | 2026-07-06 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-08-09 |  | 2026-08-14 |  | 2026-08-24 |  | 136 | 95 |  |  | 79686678 |  |  |  | 75 | 2026-08-14 | 41 |  | 2026-08-14 | 41 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
7 |  | Metal Doors | Prabhu | 2026-06-05 |  | 2026-06-12 |  | 2026-06-18 |  | 2026-06-21 |  | 2026-07-21 |  | 2026-07-31 |  | 2026-08-20 |  | 2026-08-27 |  | 2026-09-03 |  | 2026-09-08 |  | 2026-09-18 |  | 161 | 95 |  |  | 2213562 |  |  |  | 100 | 2026-09-08 | 66 |  | 2026-09-08 | 66 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Joinery and Carpentry
8 |  | Timber Doors | Suhail | 2026-06-05 |  | 2026-06-12 |  | 2026-06-18 |  | 2026-06-21 |  | 2026-07-21 |  | 2026-07-31 |  | 2026-08-20 |  | 2026-08-27 |  | 2026-09-03 |  | 2026-09-08 |  | 2026-09-18 |  | 161 | 95 |  |  | 15494601 |  |  |  | 100 | 2026-09-08 | 66 |  | 2026-09-08 | 66 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
9 |  | Ironmongery | Suhail | 2026-06-05 |  | 2026-06-12 |  | 2026-06-18 |  | 2026-06-21 |  | 2026-07-21 |  | 2026-07-31 |  | 2026-08-20 |  | 2026-08-27 |  | 2026-09-03 |  | 2026-09-08 |  | 2026-09-18 |  | 161 | 95 |  |  | 3098898 |  |  |  | 100 | 2026-09-08 | 66 |  | 2026-09-08 | 66 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
10 |  | Woodworks | Suhail | 2026-06-05 |  | 2026-06-12 |  | 2026-06-18 |  | 2026-06-21 |  | 2026-07-21 |  | 2026-07-31 |  | 2026-08-20 |  | 2026-08-27 |  | 2026-09-03 |  | 2026-09-08 |  | 2026-09-18 |  | 161 | 95 |  |  | 44270352 |  |  |  | 100 | 2026-09-08 | 66 |  | 2026-09-08 | 66 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Finishes
11 |  | Internal Finishes | Reyoon | 2026-05-16 |  | 2026-05-23 |  | 2026-05-29 |  | 2026-06-01 |  | 2026-07-01 |  | 2026-07-11 |  | 2026-07-31 |  | 2026-08-07 |  | 2026-08-14 |  | 2026-08-19 |  | 2026-08-29 |  | 141 | 95 |  |  | 46926582 |  |  |  | 80 | 2026-08-19 | 46 |  | 2026-08-19 | 46 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
12 |  | Finishes - Screed and Plaster | Reyoon | 2026-05-16 |  | 2026-05-23 |  | 2026-05-29 |  | 2026-06-01 |  | 2026-07-01 |  | 2026-07-11 |  | 2026-07-31 |  | 2026-08-07 |  | 2026-08-14 |  | 2026-08-19 |  | 2026-08-29 |  | 141 | 95 |  |  | 34309545 |  |  |  | 80 | 2026-08-19 | 46 |  | 2026-08-19 | 46 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
External Works
13 |  | External works (Landscape & irrigation) | Suhail | 2026-05-26 |  | 2026-06-02 |  | 2026-06-08 |  | 2026-06-11 |  | 2026-07-11 |  | 2026-07-21 |  | 2026-08-10 |  | 2026-08-17 |  | 2026-08-24 |  | 2026-08-29 |  | 2026-09-08 |  | 151 | 95 |  |  | 15733695 |  |  |  | 90 | 2026-08-29 | 56 |  | 2026-08-29 | 56 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
14 |  | Special Construction | Suhail | 2026-06-25 |  | 2026-07-02 |  | 2026-07-08 |  | 2026-07-11 |  | 2026-08-10 |  | 2026-08-20 |  | 2026-09-09 |  | 2026-09-16 |  | 2026-09-23 |  | 2026-09-28 |  | 2026-10-08 |  | 181 | 95 |  |  | 6197796 |  |  |  | 120 | 2026-09-28 | 86 |  | 2026-09-28 | 86 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Equipments & Accessories
15 |  | Lifts | Manoj | 2026-03-27 |  | 2026-04-03 |  | 2026-04-09 |  | 2026-04-12 |  | 2026-05-12 |  | 2026-05-22 |  | 2026-06-11 |  | 2026-06-18 |  | 2026-06-25 |  | 2026-06-30 |  | 2026-07-10 |  | 91 | 95 |  |  | 7083909 |  |  |  | 30 | 2026-06-30 | -4 |  | 2026-06-30 | -4 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
16 |  | Accessories (MIRROR,PARTITION ) | Prabhu | 2026-06-25 |  | 2026-07-02 |  | 2026-07-08 |  | 2026-07-11 |  | 2026-08-10 |  | 2026-08-20 |  | 2026-09-09 |  | 2026-09-16 |  | 2026-09-23 |  | 2026-09-28 |  | 2026-10-08 |  | 181 | 95 |  |  | 664002 |  |  |  | 120 | 2026-09-28 | 86 |  | 2026-09-28 | 86 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
17 |  | Supply of White Goods | Jayantha | 2026-06-25 |  | 2026-07-02 |  | 2026-07-08 |  | 2026-07-11 |  | 2026-08-10 |  | 2026-08-20 |  | 2026-09-09 |  | 2026-09-16 |  | 2026-09-23 |  | 2026-09-28 |  | 2026-10-08 |  | 181 | 95 |  |  | 9518139 |  |  |  | 120 | 2026-09-28 | 86 |  | 2026-09-28 | 86 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
18 |  | Accessories | Jayantha | 2026-06-25 |  | 2026-07-02 |  | 2026-07-08 |  | 2026-07-11 |  | 2026-08-10 |  | 2026-08-20 |  | 2026-09-09 |  | 2026-09-16 |  | 2026-09-23 |  | 2026-09-28 |  | 2026-10-08 |  | 181 | 95 |  |  | 4427013 |  |  |  | 120 | 2026-09-28 | 86 |  | 2026-09-28 | 86 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
19 |  | Garbage chute and BMU | Suhail | 2026-06-25 |  | 2026-07-02 |  | 2026-07-08 |  | 2026-07-11 |  | 2026-08-10 |  | 2026-08-20 |  | 2026-09-09 |  | 2026-09-16 |  | 2026-09-23 |  | 2026-09-28 |  | 2026-10-08 |  | 181 | 95 |  |  | 1992117 |  |  |  | 120 | 2026-09-28 | 86 |  | 2026-09-28 | 86 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
20 |  | Loose Furniture | Jayantha | 2026-12-22 |  | 2026-12-29 |  | 2027-01-04 |  | 2027-01-07 |  | 2027-02-06 |  | 2027-02-16 |  | 2027-03-08 |  | 2027-03-15 |  | 2027-03-22 |  | 2027-03-27 |  | 2027-04-06 |  | 361 | 95 |  |  | 2213562 |  |  |  | 300 | 2027-03-27 | 266 |  | 2027-03-27 | 266 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
21 |  | Outdoor Furniture | Jayantha | 2026-12-22 |  | 2026-12-29 |  | 2027-01-04 |  | 2027-01-07 |  | 2027-02-06 |  | 2027-02-16 |  | 2027-03-08 |  | 2027-03-15 |  | 2027-03-22 |  | 2027-03-27 |  | 2027-04-06 |  | 361 | 95 |  |  | 553335 |  |  |  | 300 | 2027-03-27 | 266 |  | 2027-03-27 | 266 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
22 |  | supply and installation of gym equipment | Jayantha | 2026-12-22 |  | 2026-12-29 |  | 2027-01-04 |  | 2027-01-07 |  | 2027-02-06 |  | 2027-02-16 |  | 2027-03-08 |  | 2027-03-15 |  | 2027-03-22 |  | 2027-03-27 |  | 2027-04-06 |  | 361 | 95 |  |  | 442668 |  |  |  | 300 | 2027-03-27 | 266 |  | 2027-03-27 | 266 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
23 |  | supply and installation of play equipment | Jayantha | 2026-12-22 |  | 2026-12-29 |  | 2027-01-04 |  | 2027-01-07 |  | 2027-02-06 |  | 2027-02-16 |  | 2027-03-08 |  | 2027-03-15 |  | 2027-03-22 |  | 2027-03-27 |  | 2027-04-06 |  | 361 | 95 |  |  | 61938 |  |  |  | 300 | 2027-03-27 | 266 |  | 2027-03-27 | 266 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
24 |  | Furnishings | Jayantha | 2026-12-22 |  | 2026-12-29 |  | 2027-01-04 |  | 2027-01-07 |  | 2027-02-06 |  | 2027-02-16 |  | 2027-03-08 |  | 2027-03-15 |  | 2027-03-22 |  | 2027-03-27 |  | 2027-04-06 |  | 361 | 95 |  |  | 1106781 |  |  |  | 300 | 2027-03-27 | 266 |  | 2027-03-27 | 266 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | Total | [25 empty] | 0 | 0 | 588986535 | 0 | 0
Formulas:
LDC = [Supervision]-H7
Supervision = [BUA (m2)]-J7
BUA (m2) = [Award Date]-L7
Award Date = [Plan]-N7
Plan = [Value Summary]-P7
Plan = [Plan]-T7
Value Summary = [Plan]-R7

## Verdes
Project |  | Components | Category | LDC | PMC | Supervision | Contractor | BUA (m2) | GFA (m2) | Award Date | Commencement |  |  | Value Summary |  |  |  |  | Actual to date Impact on Value | [5 empty] | Packages Summary |  |  | Delay Summary |  | nos. | Max delay
[14 empty] | Project Lump Sum Value in LAFO |  |  |  |  | Awards up to date (incl. OHP) |  |  | 0 | 0% |  | Total Packages (nos) |  | 7 | Current delayed remaining packages |  | 5 | -84
Haven Apartments (Verdes) |  | 7 Buildings G+P + 4-17 floors | Resi Buildings | Atkins | Jll | Atkins | Nurol | 179478.21 | 136,787 m2 | 2025-06-30 | 2025-08-18 |  |  | PS - Lump Sum Value in LAFO |  |  | 0 |  | Remaining to award |  |  | 60504168 | 100% |  | Finalized Packages (nos) |  | 0 | Forecast Delay to Contract |  | 5 | -144
[14 empty] | PS - Contract Value (incl. OHP) |  |  | 60504168 |  | Finalized Packages Savings against Lump Sum |  |  | 0 | #DIV/0! |  | Days Since Award (days) |  | 274 | Forecast Delay to Baseline |  | 5 | -144
[19 empty] | Finalized Packages Savings against contract PS |  |  | 0 | #DIV/0!
Data Date |  | 2026-03-31 | [31 empty] | Tentative
SN | Pkg No. | Package | Package Manager | 15 |  | 7 |  | 6 |  | 3 |  | 30 |  | 10 |  | 20 |  | 7 |  | 7 |  | 5 |  | 10 |  | Variance from Today | PS Procurement Duration | PS - Lump Sum Value in LAFO | PS - Contract Value (excl. OHP) | PS - Contract Value (incl. OHP) | PS - Award Value (incl. OHP) | Saving (against PS in contract) | Awarded Sub-contractor | Cont Dur | Contract Date Nomination | Var | Float | Late Date in Programme | Var | Actual / Forecast Award | Current Stage (from 1-11) | 1. Tender Docs & BOQ | 2. Bidder List | 3. EOI | 4. Tender Float | 5. Initial submission | 6. Tech & Com Review | 7. BAFO | 8. Tech & Com Review | 9. Award Rec. Approval | 10. Issued to Contractor | 11. Subcontract signed
|  |  |  | 1. Tender Docs & BOQ |  | 2. Bidder List |  | 3. EOI |  | 4. Tender Float |  | 5. Initial submission |  | 6. Tech & Com Review |  | 7. BAFO |  | 8. Tech & Com Review |  | 9. Award Rec. Approval |  | 10. Issued to Contractor |  | 11. Subcontract Agreement signed
|  |  |  | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast
PC Rate Items
1 |  | Sanitaryware | Ifthiqar | 2025-10-03 | 2025-12-09 | 2025-10-10 | 2025-12-15 | 2025-10-16 | 2025-12-20 | 2025-10-19 | 2026-02-10 | 2025-11-18 | 2026-02-17 | 2025-11-28 | 2026-04-01 | 2025-12-18 |  | 2025-12-25 |  | 2026-01-01 |  | 2026-01-06 |  | 2026-01-16 |  | -84 | 95 |  |  | 17000000 |  |  |  | 142 | 2026-01-06 | -124 |  | 2026-01-06 | -124 | 2026-05-10 | 7. BAFO | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2 |  | Light fittings | Ifthiqar | 2025-11-25 | 2026-02-11 | 2025-12-02 | 2025-10-02 | 2025-12-08 | 2026-02-10 | 2025-12-11 | 2026-02-13 | 2026-01-10 | 2026-02-17 | 2026-01-20 | 2026-03-16 | 2026-02-09 | 2026-04-01 | 2026-02-16 | 2026-04-02 | 2026-02-23 |  | 2026-02-28 |  | 2026-03-10 |  | -31 | 95 |  |  | 14000000 |  |  |  | 195 | 2026-02-28 | -45 |  | 2026-02-28 | -45 | 2026-04-14 | 9. Award Rec. Approval | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE
3 |  | Tiles | Reyoon | 2025-10-25 | 2025-12-09 | 2025-11-01 | 2025-12-15 | 2025-11-07 | 2025-12-20 | 2025-11-10 |  | 2025-12-10 |  | 2025-12-20 |  | 2026-01-09 |  | 2026-01-16 |  | 2026-01-23 |  | 2026-01-28 |  | 2026-02-07 |  | -62 | 95 |  |  | 8004168 |  |  |  | 164 | 2026-01-28 | -144 |  | 2026-01-28 | -144 | 2026-06-21 | 4. Tender Float | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Equipments & Accessories
4 |  | Lifts | Manoj | 2025-11-02 | 2026-01-28 | 2025-11-09 | 2025-12-15 | 2025-11-15 | 2025-12-26 | 2025-11-18 | 2026-02-02 | 2025-12-18 | 2026-02-13 | 2025-12-28 | 2026-02-13 | 2026-01-17 | 2026-02-13 | 2026-01-24 |  | 2026-01-31 | 2026-03-30 | 2026-02-05 |  | 2026-02-15 |  | -54 | 95 |  |  | 8000000 |  |  |  | 172 | 2026-02-05 | -73 |  | 2026-02-05 | -73 | 2026-04-19 | 8. Tech & Com Review | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | FALSE
5 |  | White Goods | Jayantha | 2025-12-10 |  | 2025-12-17 |  | 2025-12-23 |  | 2025-12-26 |  | 2026-01-25 |  | 2026-02-04 |  | 2026-02-24 |  | 2026-03-03 |  | 2026-03-10 |  | 2026-03-15 |  | 2026-03-25 |  | -16 | 95 |  |  | 10200000 |  |  |  | 210 | 2026-03-15 | -111 |  | 2026-03-15 | -111 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
6 |  | Loose Furniture | Jayantha | 2026-09-06 |  | 2026-09-13 |  | 2026-09-19 |  | 2026-09-22 |  | 2026-10-22 |  | 2026-11-01 |  | 2026-11-21 |  | 2026-11-28 |  | 2026-12-05 |  | 2026-12-10 |  | 2026-12-20 |  | 254 | 95 |  |  | 1600000 |  |  |  | 480 | 2026-12-10 | 159 |  | 2026-12-10 | 159 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
7 |  | Gym Equipments | Jayantha | 2026-10-07 |  | 2026-10-14 |  | 2026-10-20 |  | 2026-10-23 |  | 2026-11-22 |  | 2026-12-02 |  | 2026-12-22 |  | 2026-12-29 |  | 2027-01-05 |  | 2027-01-10 |  | 2027-01-20 |  | 285 | 95 |  |  | 1700000 |  |  |  | 511 | 2027-01-10 | 190 |  | 2027-01-10 | 190 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | Total | [25 empty] | 0 | 0 | 60504168 | 0 | 0
| 1 | Lift | [25 empty] | awarded schiendler
| 2 | Sanitaryware | [25 empty] | Slectrion with Donia agreed , award this
| 3 | Light fitting
| 4 | Tiles
5
Formulas:
LDC = [Supervision]-H7
Supervision = [BUA (m2)]-J7
BUA (m2) = [Award Date]-L7
Award Date = [Plan]-N7
Plan = [Value Summary]-P7
Plan = [Plan]-T7
Value Summary = [Plan]-R7

## Wilds
Project |  | Components | Category | LDC | PMC | Supervision | Contractor | BUA (m2) | GFA (m2) | Award Date | Commencement |  |  | Value Summary |  |  |  |  | Actual to date Impact on Value | [5 empty] | Packages Summary |  |  | Delay Summary |  | nos. | Max delay
[14 empty] | Project Lump Sum Value in LAFO |  |  |  |  | Awards up to date (incl. OHP) |  |  | 0 | 0% |  | Total Packages (nos) |  | 24 | Current delayed remaining packages |  | 0 | 75
The Wilds |  | 941 Villas | Villas | Atkins | Jll | Atkins | Genco |  | 275413 | 2025-10-31 | 2026-05-01 |  |  | PS - Lump Sum Value in LAFO |  |  | 0 |  | Remaining to award |  |  | 513100000 | 100% |  | Finalized Packages (nos) |  | 0 | Forecast Delay to Contract |  | 1 | -20
[14 empty] | PS - Contract Value (incl. OHP) |  |  | 513100000 |  | Finalized Packages Savings against Lump Sum |  |  | 0 | #DIV/0! |  | Days Since Award (days) |  | 151 | Forecast Delay to Baseline |  | 1 | -20
[19 empty] | Finalized Packages Savings against contract PS |  |  | 0 | #DIV/0!
Data Date |  | 2026-03-31 | [31 empty] | Tentative
SN | Pkg No. | Package | Package Manager | 15 |  | 7 |  | 6 |  | 3 |  | 30 |  | 10 |  | 20 |  | 7 |  | 7 |  | 5 |  | 10 |  | Variance from Today | PS Procurement Duration | PS - Lump Sum Value in LAFO | PS - Contract Value (excl. OHP) | PS - Contract Value (incl. OHP) | PS - Award Value (incl. OHP) | Saving (against PS in contract) | Awarded Sub-contractor | Cont Dur | Contract Date Nomination | Var | Float | Late Date in Programme | Var | Actual / Forecast Award | Current Stage (from 1-11) | 1. Tender Docs & BOQ | 2. Bidder List | 3. EOI | 4. Tender Float | 5. Initial submission | 6. Tech & Com Review | 7. BAFO | 8. Tech & Com Review | 9. Award Rec. Approval | 10. Issued to Contractor | 11. Subcontract signed
|  |  |  | 1. Tender Docs & BOQ |  | 2. Bidder List |  | 3. EOI |  | 4. Tender Float |  | 5. Initial submission |  | 6. Tech & Com Review |  | 7. BAFO |  | 8. Tech & Com Review |  | 9. Award Rec. Approval |  | 10. Issued to Contractor |  | 11. Subcontract Agreement signed
|  |  |  | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast
PC Rate Items
1 |  | Sanitary ware - Package 1 & 3 | Ifthiqar | 2026-04-25 |  | 2026-05-02 |  | 2026-05-08 |  | 2026-05-11 |  | 2026-06-10 |  | 2026-06-20 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-07-29 |  | 2026-08-08 |  | 120 | 95 |  |  | 19800000 |  |  |  | 90 | 2026-07-29 | 25 |  | 2026-07-29 | 25 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2 |  | Light Fittings - Package 1 & 3 | Ifthiqar | 2026-04-25 |  | 2026-05-02 |  | 2026-05-08 |  | 2026-05-11 |  | 2026-06-10 |  | 2026-06-20 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-07-29 |  | 2026-08-08 |  | 120 | 95 |  |  | 14100000 |  |  |  | 90 | 2026-07-29 | 25 |  | 2026-07-29 | 25 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3 |  | Wiring accessories - Package 1 & 3 | Manoj | 2026-05-25 |  | 2026-06-01 |  | 2026-06-07 |  | 2026-06-10 |  | 2026-07-10 |  | 2026-07-20 |  | 2026-08-09 |  | 2026-08-16 |  | 2026-08-23 |  | 2026-08-28 |  | 2026-09-07 |  | 150 | 95 |  |  | 6300000 |  |  |  | 120 | 2026-08-28 | 55 |  | 2026-08-28 | 55 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4 |  | Sanitary ware, Lighting Fixtures, Wiring Accessories - Premium Villas | Manoj | 2026-04-25 |  | 2026-05-02 |  | 2026-05-08 |  | 2026-05-11 |  | 2026-06-10 |  | 2026-06-20 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-07-29 |  | 2026-08-08 |  | 120 | 95 |  |  | 6162860 |  |  |  | 90 | 2026-07-29 | 25 |  | 2026-07-29 | 25 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
5 |  | Sanitary ware, Lighting Fixtures, Wiring Accessories - Ultra Luxury Villas | Manoj | 2026-04-25 |  | 2026-05-02 |  | 2026-05-08 |  | 2026-05-11 |  | 2026-06-10 |  | 2026-06-20 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-07-29 |  | 2026-08-08 |  | 120 | 95 |  |  | 21337140 |  |  |  | 90 | 2026-07-29 | 25 |  | 2026-07-29 | 25 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Aluminum & Metal Works
6 |  | Metal Works - Premium Villas | Prabhu | 2026-04-10 |  | 2026-04-17 |  | 2026-04-23 |  | 2026-04-26 |  | 2026-05-26 |  | 2026-06-05 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-07-14 |  | 2026-07-24 |  | 105 | 95 |  |  | 5265150 |  |  |  | 75 | 2026-07-14 | 10 |  | 2026-07-14 | 10 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
7 |  | Doors and Windows - Premium Villas | Prabhu | 2026-04-10 |  | 2026-04-17 |  | 2026-04-23 |  | 2026-04-26 |  | 2026-05-26 |  | 2026-06-05 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-07-14 |  | 2026-07-24 |  | 105 | 95 |  |  | 18387380 |  |  |  | 75 | 2026-07-14 | 10 |  | 2026-07-14 | 10 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
8 |  | Metal Works - Ultra Luxury Villas | Prabhu | 2026-04-10 |  | 2026-04-17 |  | 2026-04-23 |  | 2026-04-26 |  | 2026-05-26 |  | 2026-06-05 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-07-14 |  | 2026-07-24 |  | 105 | 95 |  |  | 54684850 |  |  |  | 75 | 2026-07-14 | 10 |  | 2026-07-14 | 10 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
9 |  | Doors and Windows - Ultra Luxury Villas | Prabhu | 2026-04-10 |  | 2026-04-17 |  | 2026-04-23 |  | 2026-04-26 |  | 2026-05-26 |  | 2026-06-05 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-07-14 |  | 2026-07-24 |  | 105 | 95 |  |  | 48712620 |  |  |  | 75 | 2026-07-14 | 10 |  | 2026-07-14 | 10 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Joinery and Carpentry
10 |  | Wood Works - Premium Villas | Suhail | 2026-06-24 |  | 2026-07-01 |  | 2026-07-07 |  | 2026-07-10 |  | 2026-08-09 |  | 2026-08-19 |  | 2026-09-08 |  | 2026-09-15 |  | 2026-09-22 |  | 2026-09-27 |  | 2026-10-07 |  | 180 | 95 |  |  | 1668150 |  |  |  | 150 | 2026-09-27 | 85 |  | 2026-09-27 | 85 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
11 |  | Wood Works - Ultra Luxury Villas | Suhail | 2026-05-25 |  | 2026-06-01 |  | 2026-06-07 |  | 2026-06-10 |  | 2026-07-10 |  | 2026-07-20 |  | 2026-08-09 |  | 2026-08-16 |  | 2026-08-23 |  | 2026-08-28 |  | 2026-09-07 |  | 150 | 95 |  |  | 15381850 |  |  |  | 120 | 2026-08-28 | 55 |  | 2026-08-28 | 55 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Finishes
12 |  | Finishes - Premium Villas | Reyoon | 2026-04-25 |  | 2026-05-02 |  | 2026-05-08 |  | 2026-05-11 |  | 2026-06-10 |  | 2026-06-20 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-07-29 |  | 2026-08-08 |  | 120 | 95 |  |  | 42652060 |  |  |  | 90 | 2026-07-29 | 25 |  | 2026-07-29 | 25 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
13 |  | Finishes - Ultra Luxury Villas | Reyoon | 2026-04-25 |  | 2026-05-02 |  | 2026-05-08 |  | 2026-05-11 |  | 2026-06-10 |  | 2026-06-20 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-07-29 |  | 2026-08-08 |  | 120 | 95 |  |  | 112887940 |  |  |  | 90 | 2026-07-29 | 25 |  | 2026-07-29 | 25 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
External Works
14 |  | External Site Works - Premium Villas | Suhail | 2026-06-24 |  | 2026-07-01 |  | 2026-07-07 |  | 2026-07-10 |  | 2026-08-09 |  | 2026-08-19 |  | 2026-09-08 |  | 2026-09-15 |  | 2026-09-22 |  | 2026-09-27 |  | 2026-10-07 |  | 180 | 95 |  |  | 1190750 |  |  |  | 150 | 2026-09-27 | 85 |  | 2026-09-27 | 85 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
15 |  | External Landsccape, Lighting Fitiiings, Swimming pool MEP works, Lateral Irrigation, MEP Works - Ultra Luxury Villas | Suhail | 2026-05-25 |  | 2026-06-01 |  | 2026-06-07 |  | 2026-06-10 |  | 2026-07-10 |  | 2026-07-20 |  | 2026-08-09 |  | 2026-08-16 |  | 2026-08-23 |  | 2026-08-28 |  | 2026-09-07 |  | 150 | 95 |  |  | 57109250 |  |  |  | 120 | 2026-08-28 | 55 |  | 2026-08-28 | 55 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Equipments & Accessories
16 |  | Conveying Systems - Ultra Luxury Villas | Jayantha | 2026-03-11 |  | 2026-03-18 |  | 2026-03-24 |  | 2026-03-27 |  | 2026-04-26 |  | 2026-05-06 |  | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-06-14 |  | 2026-06-24 |  | 75 | 95 |  |  | 4070000 |  |  |  | 45 | 2026-06-14 | -20 |  | 2026-06-14 | -20 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
17 |  | Furnishings - Package 1 & 3 | Jayantha | 2026-11-21 |  | 2026-11-28 |  | 2026-12-04 |  | 2026-12-07 |  | 2027-01-06 |  | 2027-01-16 |  | 2027-02-05 |  | 2027-02-12 |  | 2027-02-19 |  | 2027-02-24 |  | 2027-03-06 |  | 330 | 95 |  |  | 49500000 |  |  |  | 300 | 2027-02-24 | 235 |  | 2027-02-24 | 235 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
18 |  | Accessories - Premium Villas | Jayantha | 2026-07-24 |  | 2026-07-31 |  | 2026-08-06 |  | 2026-08-09 |  | 2026-09-08 |  | 2026-09-18 |  | 2026-10-08 |  | 2026-10-15 |  | 2026-10-22 |  | 2026-10-27 |  | 2026-11-06 |  | 210 | 95 |  |  | 3787850 |  |  |  | 180 | 2026-10-27 | 115 |  | 2026-10-27 | 115 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
19 |  | Equipments - Premium Villas | Jayantha | 2026-07-24 |  | 2026-07-31 |  | 2026-08-06 |  | 2026-08-09 |  | 2026-09-08 |  | 2026-09-18 |  | 2026-10-08 |  | 2026-10-15 |  | 2026-10-22 |  | 2026-10-27 |  | 2026-11-06 |  | 210 | 95 |  |  | 3525280 |  |  |  | 180 | 2026-10-27 | 115 |  | 2026-10-27 | 115 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
20 |  | Furnishings - Premium Villas | Jayantha | 2026-11-21 |  | 2026-11-28 |  | 2026-12-04 |  | 2026-12-07 |  | 2027-01-06 |  | 2027-01-16 |  | 2027-02-05 |  | 2027-02-12 |  | 2027-02-19 |  | 2027-02-24 |  | 2027-03-06 |  | 330 | 95 |  |  | 7571850 |  |  |  | 300 | 2027-02-24 | 235 |  | 2027-02-24 | 235 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
21 |  | White Goods - Package 1 & 3 | Jayantha | 2026-06-24 |  | 2026-07-01 |  | 2026-07-07 |  | 2026-07-10 |  | 2026-08-09 |  | 2026-08-19 |  | 2026-09-08 |  | 2026-09-15 |  | 2026-09-22 |  | 2026-09-27 |  | 2026-10-07 |  | 180 | 95 |  |  | 9800000 |  |  |  | 150 | 2026-09-27 | 85 |  | 2026-09-27 | 85 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
22 |  | Accessories - Premium Villas | Jayantha | 2026-07-24 |  | 2026-07-31 |  | 2026-08-06 |  | 2026-08-09 |  | 2026-09-08 |  | 2026-09-18 |  | 2026-10-08 |  | 2026-10-15 |  | 2026-10-22 |  | 2026-10-27 |  | 2026-11-06 |  | 210 | 95 |  |  | 3692150 |  |  |  | 180 | 2026-10-27 | 115 |  | 2026-10-27 | 115 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
23 |  | Equipments - Ultra Luxury Villas | Jayantha | 2026-07-24 |  | 2026-07-31 |  | 2026-08-06 |  | 2026-08-09 |  | 2026-09-08 |  | 2026-09-18 |  | 2026-10-08 |  | 2026-10-15 |  | 2026-10-22 |  | 2026-10-27 |  | 2026-11-06 |  | 210 | 95 |  |  | 4724720 |  |  |  | 180 | 2026-10-27 | 115 |  | 2026-10-27 | 115 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
24 |  | Furnishings - Ultra Luxury Villas | Jayantha | 2026-11-21 |  | 2026-11-28 |  | 2026-12-04 |  | 2026-12-07 |  | 2027-01-06 |  | 2027-01-16 |  | 2027-02-05 |  | 2027-02-12 |  | 2027-02-19 |  | 2027-02-24 |  | 2027-03-06 |  | 330 | 95 |  |  | 788150 |  |  |  | 300 | 2027-02-24 | 235 |  | 2027-02-24 | 235 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | Total | [25 empty] | 0 | 0 | 513100000 | 0 | 0
| 1 | Lifts | [25 empty] | offers received , ID received form design team and revised offer waiting, next week to finailize
2
3
4
5
6
Formulas:
LDC = [Supervision]-H7
Supervision = [BUA (m2)]-J7
BUA (m2) = [Award Date]-L7
Award Date = [Plan]-N7
Plan = [Value Summary]-P7
Plan = [Plan]-T7
Value Summary = [Plan]-R7

## Marjan
Project |  | Components | Category | LDC | PMC | Supervision | Contractor | BUA (m2) | GFA (m2) | Award Date | Commencement |  |  | Value Summary |  |  |  |  | Actual to date Impact on Value | [5 empty] | Packages Summary |  |  | Delay Summary |  | nos. | Max delay
[14 empty] | Project Lump Sum Value in LAFO |  |  |  |  | Awards up to date (incl. OHP) |  |  | 710860601 | 52.83% |  | Total Packages (nos) |  | 22 | Current delayed remaining packages |  | 9 | -154
Marjan |  | 6 Buildings 2B+G+23 | Resi & Branded Buildings | AECOM | JLL | AECOM | Shapoorji |  | 235462 | 2025-06-01 | 2025-07-31 |  |  | PS - Lump Sum Value in LAFO |  |  | 1791734727 |  | Remaining to award |  |  | 634579000 | 47.17% |  | Finalized Packages (nos) |  | 6 | Forecast Delay to Contract |  | 17 | -249
[14 empty] | PS - Contract Value (incl. OHP) |  |  | 1414895476 |  | Finalized Packages Savings against Lump Sum |  |  | 192036455 | #DIV/0! |  | Days Since Award (days) |  | 303 | Forecast Delay to Baseline |  | 17 | -249
[19 empty] | Finalized Packages Savings against contract PS |  |  | 69455875 | #DIV/0!
Data Date |  | 2026-03-31
SN | Pkg No. | Package | Package Manager | 15 |  | 7 |  | 6 |  | 3 |  | 30 |  | 10 |  | 20 |  | 7 |  | 7 |  | 5 |  | 10 |  | Variance from Today | PS Procurement Duration | PS - Lump Sum Value in LAFO | PS - Contract Value (excl. OHP) | PS - Contract Value (incl. OHP) | PS - Award Value (incl. OHP) | Saving (against PS in contract) | Awarded Sub-contractor | Cont Dur | Contract Date Nomination | Var | Float | Late Date in Programme | Var | Actual / Forecast Award | Current Stage (from 1-11) | 1. Tender Docs & BOQ | 2. Bidder List | 3. EOI | 4. Tender Float | 5. Initial submission | 6. Tech & Com Review | 7. BAFO | 8. Tech & Com Review | 9. Award Rec. Approval | 10. Issued to Contractor | 11. Subcontract signed
|  |  |  | 1. Tender Docs & BOQ |  | 2. Bidder List |  | 3. EOI |  | 4. Tender Float |  | 5. Initial submission |  | 6. Tech & Com Review |  | 7. BAFO |  | 8. Tech & Com Review |  | 9. Award Rec. Approval |  | 10. Issued to Contractor |  | 11. Subcontract Agreement signed
|  |  |  | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast
PC Rate Items
1 |  | Sanitary Fixture | Manoj | 2025-09-23 | 2025-08-06 | 2025-09-30 | 2025-08-14 | 2025-10-06 | 2025-08-08 | 2025-10-09 | 2025-08-13 | 2025-11-08 | 2025-08-13 | 2025-11-18 | 2025-08-13 | 2025-12-08 | 2025-09-17 | 2025-12-15 | 2025-09-24 | 2025-12-22 | 2026-01-23 | 2025-12-27 | 2026-02-03 | 2026-01-06 |  | - | 95 | 51030205 |  | 36300000 | 26978980 | 9321020 | Al hashmiya general trading & Sarieddine Trading Est | 150 | 2025-12-27 | -38 |  | 2025-12-27 | -38 | 2026-02-03 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
2 |  | Lighting fixtures | Manoj | 2026-04-26 | 2025-09-30 | 2026-05-03 | 2025-10-02 | 2026-05-09 | 2025-10-06 | 2026-05-12 | 2025-10-06 | 2026-06-11 | 2025-10-06 | 2026-06-21 | 2025-10-06 | 2026-07-11 | 2025-11-12 | 2026-07-18 | 2025-11-12 | 2026-07-25 | 2025-12-10 | 2026-07-30 |  | 2026-08-09 |  | - | 95 | 34030863 |  | 24200000 | 5459621 | 18740379 | Frater (AW Rostamani) | 365 | 2026-07-30 | 116 |  | 2026-07-30 | 116 | 2026-04-05 | 10. Issued to Contractor | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE
MEP Works
3 |  | MEP Works | Manoj | 2025-05-26 | 2025-04-13 | 2025-06-02 | 2025-04-13 | 2025-06-08 | 2025-04-16 | 2025-06-11 | 2025-04-30 | 2025-07-11 | 2025-04-30 | 2025-07-21 | 2025-04-30 | 2025-08-10 | 2025-07-01 | 2025-08-17 | 2025-07-31 | 2025-08-24 | 2025-08-13 | 2025-08-29 | 2025-09-24 | 2025-09-08 |  | - | 95 | 733781168 |  | 661336476 | 659900000 | 1436476 | Shapoorji | 30 | 2025-08-29 | -26 |  | 2025-08-29 | -26 | 2025-09-24 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
Aluminum & Metal Works
4 |  | Aluminium Doors, Curtain Wall, Balustrate etc. | Prabhu | 2025-09-23 | 2025-09-30 | 2025-09-30 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-09 | 2025-10-06 | 2025-11-08 | 2025-10-06 | 2025-11-18 | 2025-10-06 | 2025-12-08 | 2026-01-04 | 2025-12-15 | 2026-01-18 | 2025-12-22 | 2026-03-14 | 2025-12-27 | 2026-03-18 | 2026-01-06 |  | - | 95 | 329201751 |  | 203500000 |  |  | Jangho | 150 | 2025-12-27 | -81 |  | 2025-12-27 | -81 | 2026-03-18 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
5 |  | External Wall Metal Works(Aluminium Profile) | Prabhu | 2025-09-23 | 2025-09-30 | 2025-09-30 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-09 | 2025-10-06 | 2025-11-08 | 2025-10-06 | 2025-11-18 | 2025-10-06 | 2025-12-08 | 2026-01-04 | 2025-12-15 | 2026-01-18 | 2025-12-22 | 2026-03-14 | 2025-12-27 | 2026-03-18 | 2026-01-06 |  | - | 95 | 58092083 |  | 38500000 | incl. above | 38500000 | Jangho | 150 | 2025-12-27 | -81 |  | 2025-12-27 | -81 | 2026-03-18 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
6 |  | GRC | Prabhu | 2025-09-23 | 2025-09-30 | 2025-09-30 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-09 | 2025-10-06 | 2025-11-08 | 2025-11-07 | 2025-11-18 |  | 2025-12-08 |  | 2025-12-15 |  | 2025-12-22 |  | 2025-12-27 |  | 2026-01-06 |  | -94 | 95 | 78503380 |  | 46200000 |  |  |  | 150 | 2025-12-27 | -143 |  | 2025-12-27 | -143 | 2026-05-19 | 6. Tech & Com Review | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
7 |  | Cement Board (External Walls) | Prabhu | 2025-09-23 | 2025-09-30 | 2025-09-30 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-09 | 2025-10-06 | 2025-11-08 | 2025-11-07 | 2025-11-18 |  | 2025-12-08 |  | 2025-12-15 |  | 2025-12-22 |  | 2025-12-27 |  | 2026-01-06 |  | -94 | 95 | incl. Above |  | incl. Above |  |  |  | 150 | 2025-12-27 | -143 |  | 2025-12-27 | -143 | 2026-05-19 | 6. Tech & Com Review | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
8 |  | Terracot Paint (External Wall) | Prabhu | 2025-09-23 | 2025-09-30 | 2025-09-30 | 2025-10-02 | 2025-10-06 | 2025-10-06 | 2025-10-09 | 2025-10-06 | 2025-11-08 | 2025-11-07 | 2025-11-18 |  | 2025-12-08 |  | 2025-12-15 |  | 2025-12-22 |  | 2025-12-27 |  | 2026-01-06 |  | -94 | 95 | incl. Above |  | incl. Above |  |  |  | 150 | 2025-12-27 | -143 |  | 2025-12-27 | -143 | 2026-05-19 | 6. Tech & Com Review | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
9 |  | Wooden Cladding | Suhail | 2025-12-22 | 2025-10-20 | 2025-12-29 | 2025-10-23 | 2026-01-04 | 2025-10-23 | 2026-01-07 | 2025-12-20 | 2026-02-06 |  | 2026-02-16 |  | 2026-03-08 |  | 2026-03-15 |  | 2026-03-22 |  | 2026-03-27 |  | 2026-04-06 |  | -4 | 95 | 140228873 |  | 132000000 |  |  |  | 240 | 2026-03-27 | -83 |  | 2026-03-27 | -83 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
10 |  | Kitchen Cabinet & Wardrobes | Suhail | 2025-12-22 | 2025-10-20 | 2025-12-29 | 2025-10-23 | 2026-01-04 | 2025-10-23 | 2026-01-07 | 2025-12-20 | 2026-02-06 |  | 2026-02-16 |  | 2026-03-08 |  | 2026-03-15 |  | 2026-03-22 |  | 2026-03-27 |  | 2026-04-06 |  | -4 | 95 | incl. Above |  | incl. Above |  |  |  | 240 | 2026-03-27 | -83 |  | 2026-03-27 | -83 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
11 |  | Timber Doors | Suhail | 2025-12-22 | 2025-10-20 | 2025-12-29 | 2025-10-23 | 2026-01-04 | 2025-10-23 | 2026-01-07 | 2025-12-20 | 2026-02-06 |  | 2026-02-16 |  | 2026-03-08 |  | 2026-03-15 |  | 2026-03-22 |  | 2026-03-27 |  | 2026-04-06 |  | -4 | 95 | 102391194 |  | 49500000 |  |  |  | 240 | 2026-03-27 | -83 |  | 2026-03-27 | -83 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
12 |  | Ironmongery | Suhail | 2025-12-22 | 2025-10-20 | 2025-12-29 | 2025-10-23 | 2026-01-04 | 2025-10-23 | 2026-01-07 | 2025-12-20 | 2026-02-06 |  | 2026-02-16 |  | 2026-03-08 |  | 2026-03-15 |  | 2026-03-22 |  | 2026-03-27 |  | 2026-04-06 |  | -4 | 95 | 12057628 |  | 15400000 |  |  |  | 240 | 2026-03-27 | -83 |  | 2026-03-27 | -83 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Finishes
13 |  | Internal Finishes | Reyoon | 2025-10-23 | 2025-08-06 | 2025-10-30 | 2025-08-14 | 2025-11-05 | 2025-07-25 | 2025-11-08 | 2025-08-14 | 2025-12-08 |  | 2025-12-18 |  | 2026-01-07 |  | 2026-01-14 |  | 2026-01-21 |  | 2026-01-26 |  | 2026-02-05 |  | -64 | 95 | 143788079 |  | 126500000 |  |  |  | 180 | 2026-01-26 | -143 |  | 2026-01-26 | -143 | 2026-06-18 | 5. Initial submission | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
External Works
14 |  | Swimming Pools | Suhail | 2025-07-25 |  | 2025-08-01 |  | 2025-08-07 |  | 2025-08-10 |  | 2025-09-09 |  | 2025-09-19 |  | 2025-10-09 |  | 2025-10-16 |  | 2025-10-23 |  | 2025-10-28 |  | 2025-11-07 |  | -154 | 95 | 15000000 | [5 empty] | 90 | 2025-10-28 | -249 |  | 2025-10-28 | -249 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
15 |  | External Play Equipment | Jayantha | 2026-04-26 |  | 2026-05-03 |  | 2026-05-09 |  | 2026-05-12 |  | 2026-06-11 |  | 2026-06-21 |  | 2026-07-11 |  | 2026-07-18 |  | 2026-07-25 |  | 2026-07-30 |  | 2026-08-09 |  | 121 | 95 | Included |  | 2200000 |  |  |  | 365 | 2026-07-30 | 26 |  | 2026-07-30 | 26 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Equipments & Accessories
16 |  | Lifts | Manoj | 2025-06-25 | 2025-06-10 | 2025-07-02 | 2025-06-14 | 2025-07-08 | 2025-06-24 | 2025-07-11 | 2025-06-30 | 2025-08-10 | 2025-06-30 | 2025-08-20 | 2025-06-30 | 2025-09-09 | 2025-07-10 | 2025-09-16 | 2025-08-19 | 2025-09-23 | 2025-09-04 | 2025-09-28 | 2025-09-24 | 2025-10-08 |  | - | 95 | 25962737 |  | 19980000 | 18522000 | 1458000 | TKE | 60 | 2025-09-28 | 4 |  | 2025-09-28 | 4 | 2025-09-24 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
17 |  | Specialist Installations -Allowance for Siemens Use Cases ( as per the orginal tender BOQ) | Manoj | 2026-04-21 |  | 2026-04-28 |  | 2026-05-04 |  | 2026-05-07 |  | 2026-06-06 |  | 2026-06-16 |  | 2026-07-06 |  | 2026-07-13 |  | 2026-07-20 |  | 2026-07-25 |  | 2026-08-04 |  | 116 | 95 | 8890000 |  | 9779000 |  |  |  | 360 | 2026-07-25 | 21 |  | 2026-07-25 | 21 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
18 |  | External Walls- Feature Digital Signage ( as per the orginal tender BOQ) | Jayantha | 2026-04-21 |  | 2026-04-28 |  | 2026-05-04 |  | 2026-05-07 |  | 2026-06-06 |  | 2026-06-16 |  | 2026-07-06 |  | 2026-07-13 |  | 2026-07-20 |  | 2026-07-25 |  | 2026-08-04 |  | 116 | 95 | 2800000 |  | 3080000 |  |  |  | 360 | 2026-07-25 | 21 |  | 2026-07-25 | 21 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
19 |  | Accessories(Inc. Shower Partition) | Prabhu | 2026-02-20 |  | 2026-02-27 |  | 2026-03-05 |  | 2026-03-08 |  | 2026-04-07 |  | 2026-04-17 |  | 2026-05-07 |  | 2026-05-14 |  | 2026-05-21 |  | 2026-05-26 |  | 2026-06-05 |  | 56 | 95 | 26463830 |  | 16500000 |  |  |  | 300 | 2026-05-26 | -39 |  | 2026-05-26 | -39 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
20 |  | Equipments(White Goods & Kitchen Equipments) | Jayantha | 2026-02-20 |  | 2026-02-27 |  | 2026-03-05 |  | 2026-03-08 |  | 2026-04-07 |  | 2026-04-17 |  | 2026-05-07 |  | 2026-05-14 |  | 2026-05-21 |  | 2026-05-26 |  | 2026-06-05 |  | 56 | 95 | 28312936 |  | 28600000 |  |  |  | 300 | 2026-05-26 | -39 |  | 2026-05-26 | -39 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
21 |  | Fixtures, Fittings and Equipment (FF&E) -Gym Equipment ( as per the orginal tender BOQ) | Jayantha | 2026-02-20 |  | 2026-02-27 |  | 2026-03-05 |  | 2026-03-08 |  | 2026-04-07 |  | 2026-04-17 |  | 2026-05-07 |  | 2026-05-14 |  | 2026-05-21 |  | 2026-05-26 |  | 2026-06-05 |  | 56 | 95 | 1200000 |  | 1320000 |  |  |  | 300 | 2026-05-26 | -39 |  | 2026-05-26 | -39 | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
22 |  | Pods | Saathieth | 2025-07-25 | 2025-07-29 | 2025-08-01 | 2025-07-15 | 2025-08-07 | 2025-07-22 | 2025-08-10 | 2025-08-05 | 2025-09-09 | 2025-08-05 | 2025-09-19 | 2025-08-05 | 2025-10-09 | 2025-09-09 | 2025-10-16 | 2025-11-17 | 2025-10-23 | 2025-11-20 | 2025-10-28 | 2025-12-05 | 2025-11-07 |  | - | 95 | incl. Above |  | incl. Above |  |  | Du Pods | 90 | 2025-10-28 | -38 |  | 2025-10-28 | -38 | 2025-12-05 | 11. Subcontract Agreement signed | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
|  | Total | [25 empty] | 1791734727 | 0 | 1414895476 | 710860601 | 69455875
2026-04-14
| 1 | Joinery package | [25 empty] | Awarding issued today
| 2 | GRC | [25 empty] | Planning this week , three building GRC and the other buildings fiber cement
| 3 | Ironmongery | [25 empty] | will be next week awarding
| 4 | Pools | [25 empty] | Next week will be ready
5
6
7
8
Formulas:
LDC = [Supervision]-H7
Supervision = [BUA (m2)]-J7
BUA (m2) = [Award Date]-L7
Award Date = [Plan]-N7
Plan = [Value Summary]-P7
Plan = [Plan]-T7
Value Summary = [Plan]-R7

## Blank (hidden)
Project |  | Components | Category | LDC | PMC | Supervision | Contractor | BUA (m2) | GFA (m2) | Award Date | Commencement |  |  | Value Summary |  |  |  |  | Actual to date Impact on Value | [5 empty] | Packages Summary |  |  | Delay Summary |  | nos. | Max delay
[14 empty] | Project Lump Sum Value in LAFO |  |  |  |  | Awards up to date (incl. OHP) |  |  | 0 | #DIV/0! |  | Total Packages (nos) |  | 39 | Current delayed remaining packages |  | 39 | -46113
[14 empty] | PS - Lump Sum Value in LAFO |  |  | 0 |  | Remaining to award |  |  | 0 | #DIV/0! |  | Finalized Packages (nos) |  | 0
[14 empty] | PS - Contract Value (incl. OHP) |  |  | 0 |  | Finalized Packages Savings against Lump Sum |  |  | 0 | #DIV/0! |  | Days Since Award (days) |  | 46112 | Delay to Baseline |  | 0 | #VALUE!
[19 empty] | Finalized Packages Savings against contract PS |  |  | 0 | #DIV/0!
Data Date |  | 2026-03-31
SN | Pkg No. | Package | Package Manager | 15 |  | 7 |  | 6 |  | 3 |  | 30 |  | 10 |  | 20 |  | 7 |  | 7 |  | 5 |  | 10 |  | Variance from Today | PS Procurement Duration | PS - Lump Sum Value in LAFO | PS - Contract Value (excl. OHP) | PS - Contract Value (incl. OHP) | PS - Award Value (incl. OHP) | Saving (against PS in contract) | Awarded Sub-contractor | Cont Dur | Contract Date Nomination | Var | Float | Late Date in Programme | Var | Actual / Forecast Award | Current Stage (from 1-11) | 1. Tender Docs & BOQ | 2. Bidder List | 3. EOI | 4. Tender Float | 5. Initial submission | 6. Tech & Com Review | 7. BAFO | 8. Tech & Com Review | 9. Award Rec. Approval | 10. Issued to Contractor | 11. Subcontract signed
|  |  |  | 1. Tender Docs & BOQ |  | 2. Bidder List |  | 3. EOI |  | 4. Tender Float |  | 5. Initial submission |  | 6. Tech & Com Review |  | 7. BAFO |  | 8. Tech & Com Review |  | 9. Award Rec. Approval |  | 10. Issued to Contractor |  | 11. Subcontract Agreement signed
|  |  |  | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast | Plan | Actual / Forecast
PC Rate Items
1 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
MEP Works
Aluminum & Metal Works
4 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
5 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
6 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
7 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
8 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Joinery and Carpentry
9 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
10 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
11 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
12 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Finishes
13 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
14 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
15 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
16 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
17 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
18 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
19 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
20 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
21 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
22 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
23 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
24 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
25 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
External Works
26 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
27 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Equipments & Accessories
28 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
29 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
30 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
31 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
32 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
33 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
34 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
35 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
36 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
37 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
38 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
39 |  |  |  | -96 |  | -89 |  | -83 |  | -80 |  | -50 |  | -40 |  | -20 |  | -13 |  | -6 |  | -1 |  | 1900-01-08 |  | -46113 | 95 | [7 empty] | -1 | -46208 |  |  | #VALUE! | 2026-07-04 | 1. Tender Docs & BOQ | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | Total | [25 empty] | 0 | 0 | 0 | 0 | 0
Formulas:
LDC = [Supervision]-H7
Supervision = [BUA (m2)]-J7
BUA (m2) = [Award Date]-L7
Award Date = [Plan]-N7
Plan = [Value Summary]-P7
Plan = [Plan]-T7
Value Summary = [Plan]-R7